## Priority Sheet
JOB # | PO # | Custemer | Description | Part # | Qty. | Ship Date | Memo | Status | 6/16/2025+J:BF | time axis 2025-06-17 to 2026-01-01
69605 | 1109596 | BWXT Med | Vial Shield Assy | K125912-003 | 2850 | 2023-07-28 | Ask Vandu | Receive,INS | Material | 2025-07-08: Receive,INS; 2025-07-09: Receive,INS; 2025-07-10: Receive,INS; 2025-07-24: Pack; 2025-07-25: Pack; 2025-07-28: Ship？
|  |  | Vial Shield Assy | K125912-003 | 2850 | 2002-08-30 |  | Material | Material
|  |  | Vial Shield Assy | K125912-003 | 2850 | 2023-09-29 |  | Material | Material
|  |  | Vial Shield Assy | K125912-003 | 2850 | 2023-10-30 |  | Material | Material
|  |  | Vial Shield Assy | K125912-003 | 2850 | 2023-11-30 |  | Material | Material
|  |  | Vial Shield Assy | K125912-003 | 2850 | 2023-12-22 |  | Material | Material
70131 | 804554 | Kipling | Servo Guard Assy | 052PLNAY01 | 1 | 2023-10-05
70586 | 634828-18000-52X-R231- R.03 | SNC-Lavalin | Toggle Clamp | RT38-88080-0104-001-DD-1 | 1 | 2024-02-06
71276 | 98-35215-PN-R019 | Candu | Link Holder F/I To Sink EDM | 98-35215-9-1-DD-D | 3 | 2024-09-20 | ★外注あり | Return to Profile EDM |  | 2025-07-15: DEBURR; 2025-07-25: Return to Profile EDM; 2025-07-28: Return to Profile EDM; 2025-07-29: Return to Profile EDM; 2025-07-30: Return to Profile EDM; 2025-07-31: Return to Profile EDM; 2025-08-01: Return to Profile EDM; 2025-08-04: Return to Profile EDM; 2025-08-05: Deburr; 2025-08-06: INS; 2025-08-07: INS; 2025-08-08: Submit Document; 2025-08-11: Submit Document; 2025-08-12: Approved; 2025-08-13: Approved; 2025-08-14: Approved; 2025-08-15: Approved; 2025-08-18: Approved; 2025-08-19: Pack; 2025-08-20: Pack; 2025-08-21: Ship
71374 | 20030822 | Woodbridge | Mz2x2-D Injector Nozzle | MZ2x2-D-N-S7N | 3 | 2024-10-25
71512 | 634828-15000-52BX-R079-Cor.007 | DJ Ind. | SS. Air Curtain - Modified | Sample | 2 | 2024-11-08
71609 | 87-63500-PN-R010 | Candu | Insert Housing Size 36-NEL-IH-36-00 | 08-63500-0233-01-DD-2 | 46 | 2025-04-14 |  | DONE
71610 | 87-63500-PN-R010 | Candu | Insert Housing Size 24-NEL-IH-24-00 | 08-63500-0525-01-DD-2 | 65 | 2025-04-14 |  | DONE
71611 | 87-63500-PN-R010 | Candu | Pin Size 16-16 - NEL-PN-00-1616 | 08-63500-0224-01-DD-2 | 1100 | 2025-04-14 |  | DONE
71612 | 87-63500-PN-R010 | Candu | Pin Size 16,20 - NEL-PN-00-1620 | 08-63500-0222-01-DD-2 | 1600 | 2025-04-14 |  | DONE
71613 | 87-63500-PN-R010 | Candu | Contact Clip Size 16- NEL-CC-00-16 | 08-63500-0229-01-DD-3 | 3500 | 2025-04-14 | Ask Gus | DONE？
71635 | RT79-88010-PN-R003 | Candu | Helium Leak Test Tool | RT-88000-70066-000-1-GA-D | 1 | 2025-07-16 | Awating Candu release | DONE
|  |  | Tygon Tube (31910-807-1) | 12918-0066-0008 (RT-88000-70066-008-1-DD-B) | 1 |  |  | DONE
|  |  | Centerring Disc (31910-854-1) | 12918-0066-0010 (RT-88000-70066-010-1-DD-B) | 3 |  |  | DONE
|  |  | Tube (31910-807-1) | 12918-0066-0011 (RT-88000-70066-011-1-DD-B) | 1 |  |  | DONE
|  |  | Spacer (31910-819-1) | 12918-0066-0021 (RT-88000-70066-021-1-DD-B) | 1 |  |  | DONE
|  |  | Tube (31910-823-1) | 12918-0066-0022 (RT-88000-70066-022-1-DD-B) | 1 |  |  | DONE
|  |  | Seal Ring (31910-814-1) | 12918-0066-0001 (RT-88000-70066-001-1-DD-B) | 2 |  |  | DONE
|  |  | Spacer (31910-823-1) | 12918-0066-0002 (RT-88000-70066-002-1-DD-D) | 1 |  |  | DONE
|  |  | Spacer (31910-819-1) | 12918-0066-0021 (RT-88000-70066-021-1-DD-B) | 1 |  |  | DONE
|  |  | Tube (31910-823-1) | 12918-0066-0022 (RT-88000-70066-022-1-DD-B) | 1 |  |  | DONE
|  |  | Inner Tube ASSY | 12918-6610-0000 (RT-88000-76610-000-1-GA-D) | 1 |  |  | DONE
|  |  | GUIDE RING (31910-811-1) | 12918-6610-0001 (RT-88000-76610-001-1-DD-B) | 1 |  |  | DONE
|  |  | PLATE PT.1 (31910-809-1) | 12918-6610-0002 (RT-88000-76610-002-1-DD-B) | 1 |  |  | DONE
|  |  | INNER PIPE (31910-818-1) | 12918-6610-0003 (RT-88000-76610-003-1-DD-B) | 1 |  |  | DONE
|  |  | SHAFT END (31910-816-1) | 12918-6610-0004 (RT-88000-76610-004-1-DD-B) | 1 |  |  | DONE
|  |  | PIPE & PLATES | 12918-6610-0007 (RT-88000-76610-007-1-DD-D) | 1 |  |  | DONE
|  |  | PLATE PT.1 (31910-809-1) | 12918-6610-0002 (RT-88000-76610-002-1-DD-B) | 1 |  |  | DONE
|  |  | INNER PIPE (31910-818-1) | 12918-6610-0003 (RT-88000-76610-003-1-DD-B) | 1 |  |  | DONE
|  |  | Outer Tube ASSY | 12918-6620-0000 (RT-88000-76620-000-1-GA-D) | 1 |  |  | DONE
|  |  | PLATE PT.2 (31910-809-1) | 12918-6620-0001 (RT-88000-76620-001-1-DD-B) | 1 |  |  | DONE
|  |  | GUIDE RING (31910-811-1) | 12918-6620-0002 (RT-88000-76620-002-1-DD-B) | 1 |  |  | DONE
|  |  | GUIDE RING (31910-848-1) | 12918-6620-0003 (RT-88000-76620-003-1-DD-B) | 1 |  |  | DONE
|  |  | PLATE (31910-815-1) | 12918-6620-0004 (RT-88000-76620-004-1-DD-B) | 1 |  |  | DONE
|  |  | OUTER PIPE (31910-817-1) | 12918-6620-0005 (RT-88000-76620-005-1-DD-B) | 1 |  |  | DONE
|  |  | OUTER HOUSING END (31910-812-1) | 12918-6620-0006 (RT-88000-76620-006-1-DD-B) | 1 |  |  | DONE
|  |  | PIPE & PLATES | 12918-6620-0009 (RT-88000-76620-009-1-DD-D/RT-88000-76610-009-2-DD-D) | 1 |  |  | DONE
71636 | RT79-88010-PN-R003 | Candu | Liner Tube Protective Sleeve | RT-88000-70146-000-1-GA-E | 7 | 2025-07-16 | Awating Candu release | DONE
|  |  | PROTECTIVE SLLEVE (31910 52-1) | RT-88000-70146-002-1-DD-D | 1 |  |  | DONE
71637 | RT79-88010-PN-R003 | Candu | Helium Spray Tool | RT-88000-70069-000-1-GA-D | 2 | 2025-07-16 | Awating Candu release | DONE
71638 | RT79-88010-PN-R003 | Candu | E/F Protective Sleeve | RT-88000-70038-000-1-GA-D | 17 | 2025-07-16 | Awating Candu release | DONE
|  |  | Steel Tube (98-31910-21-1) | 12918-0038-0001 | 1 |  |  | DONE
|  |  | Sleeve Guide (98-31910-21-1) | 12918-0038-0002 | 1 |  |  | DONE
|  |  | Sleeve Guide (98-31910-21-1) | 12918-0038-0003 | 1 |  |  | DONE
|  |  | Retaining Latch (98-31910-21-1) SUB ASSY | 12918-0038-0004 | 1 |  |  | DONE
|  |  | Spring (98-31910-21-1) | 12918-0038-0100 | 1 |  |  | DONE
|  |  | Block (98-31910-21-1) | 12918-0038-0101 | 1 |  |  | DONE
71639 | RT79-88010-PN-R003 | Candu | Spring Loaded Centre Punch | 80-01-00001-PRT- (Purchase) | 4 | 2025-07-16 | Awating Candu release | DONE
71640 | RT79-88010-PN-R003 | Candu | Vacuum Hose for Helium Leak Test | RT-88000-70068-000-1-GA-D | 2 | 2025-07-16 | Awating Candu release | DONE
|  |  | Vacuum Line Adapter (31910-47-1) | 12918-0068-0005 | 1 |  |  | DONE
|  |  | Elbow (31910-47-1) | 12918-0068-0007 | 1 |  |  | DONE
71641 | RT79-88010-PN-R003 | Candu | Air Motor Socket | RT-0055-000-PRT ( Purchase) | 5 | 2025-07-16 | Awating Candu release | DONE
71642 | RT79-88010-PN-R003 | Candu | Calibrated Measuring Tape | RT-88010-0005-01-GA-E | 2 | 2025-08-08 | Awating Candu release | DONE |  | 2025-07-28: Setup; 2025-07-29: Setup; 2025-07-30: Laser-Etching; 2025-07-31: Laser-Etching; 2025-08-01: Clean; 2025-08-04: INS,DIR; 2025-08-05: INS,DIR; 2025-08-06: Pack; 2025-08-07: Pack
|  |  | Calibrated Tape Holder | RT-88010-0008-01-DD-C | 2 |  |  | DONE
|  |  | Plate | RT-88010-0006-01-DD-C | 2 |  |  | DONE
|  |  | Pulley Shaft | RT-88010-0007-01-DD-C | 4 |  |  | DONE
|  |  | Pulley Bracket | RT-88010-0013-01-GA-C | 1 |  |  | DONE
|  |  | PULLEY BRACKET | RT-88010-0014-01-GA-C | 1 |  |  | DONE
|  |  | PULLEY BRACKET | RT-88010-0015-01-GA-C | 1 |  |  | DONE
|  |  | PULLEY BRACKET | RT-88010-0016-01-GA-C | 1 |  |  | DONE
71644 | RT79-88010-PN-R003 | Candu | Seal Face Protective Sleeve | RT-88000-70047-000-1-GA-D | 6 | 2025-07-16 | Awating Candu release | DONE
|  |  | SLEEVE TUBE | RT-88000-70047-001-1-DD-B | 1 |  |  | DONE
|  |  | SLEEVE GUIDE 1 | RT-88000-70047-002-1-DD-B | 1 |  |  | DONE
|  |  | SLEEVE GUIDE 2 | RT-88000-70047-003-1-DD-B | 1 |  |  | DONE
|  |  | RETAINING LATCH | RT-88000-70047-004-1-DD-B | 1 |  |  | DONE
71645 | RT79-87540-PN-R003 | Candu | Removal PA Tool Cart-RT-7538-000-PRT | RT-87540-0206-01-GA-E | 2 | 2025-07-16 | 2025-08-25 | DONE
|  |  | TOOL CART GENERAL ASSEMBLY | RT-87540-0200-01-GA-0 | 1 |  |  | DONE |  | 2025-06-24: DEBURR
|  |  | Tool Cart Frame Weldment | RT-87540-0201-01-DD-0 | 11 |  |  | DONE |  | 2025-06-20: DEBURR
|  |  | Tool Cart Top Tray | RT-87540-0202-01-DD-1 | 11 |  |  | DONE | DEBURR
|  |  | Tool Cart Bottom Tray | RT-87540-0203-01-DD-1 | 11 |  |  | DONE | DEBURR
|  |  | Tool Cart Tray Shim | RT-87540-0204-01-DD-1 | 44 |  |  | DONE
71646 | RT79-87540-PN-R003 | Candu | Yoke Removal/Inst Tool- RT-7545-000-PRT | RT-87540-0105-01-GA-0 | 16 | 2025-07-23 | 2025-08-25 | DONE
|  |  | BRACKET | RT-87540-0131-01-DD-2 | 1 |  |  | DONE
|  |  | SHORT STUD | RT-87540-0136-01-DD-2 | 1 |  |  | DONE
|  |  | LONG STUD | RT-87540-0135-01-DD-2 | 1 |  |  | DONE
|  |  | COUPLING | RT-87540-0134-01-DD-2 | 1 |  |  | DONE
|  |  | OUTER TUBE | RT-87540-0133-01-DD-2 | 1 |  |  | DONE | Receive,INS
|  |  | INNER TUBE | RT-87540-0132-01-DD-2 | 1 |  |  | DONE
71647 | RT79-87540-PN-R003 | Candu | Sheared Pin Punch Tool | RT-87540-0112-01-GA-2 | 8 | 2025-07-23 | 2025-08-25 | DONE
|  |  | SLIDE HAMMER | RT-87540-0116-01-DD-2 | 16 |  |  | DONE
|  |  | SHAFT WELDMENT | RT-87540-0113-01-DD-2 | 1 |  |  | DONE
|  |  | SUPPORT BRACKET | RT-87540-0114-01-DD-2 | 1 |  |  | DONE
|  |  | PIN HOLDER | RT-87540-0115-01-DD-2 | 1 |  |  | DONE
71648 | RT79-87540-PN-R003 | Candu | Pin Holder- RT-8544-001- PRT | RT-87540-0115-01-DD-2 | 7 | 2025-07-23 | 2025-08-25 | DONE
71649 | RT79-87540-PN-R003 | Candu | Punch Pin- RT-8063-001-PRT | RT-87540-0111-01-DD-2 | 28 | 2025-07-23 | 2025-08-25 | DONE
71650 | RT79-87540-PN-R003 | Candu | Thread Hole Insp Tool LG- RT-7536-000-PRT | RT-87540-0148-01-GA-2 | 10 | 2025-07-23 | 2025-08-25 | DONE
|  |  | HANDLE WELDMENT (LONG) | RT-87540-0149-01-DD-2 | 1 |  |  | DONE
|  |  | COUPLING, TOOL HOLDER | RT-87540-0146-01-DD-2 | 1 |  |  | DONE
|  |  | MODIFIED THREADED PLUG GAUGE SET 1.25-8 UN-2B | RT-87540-0147-01-GA-2 | 1 |  |  | DONE
71651 | RT79-87540-PN-R003 | Candu | Thread Hole Repair Tool- RT-7536-000-PRT | RT-87540-0184-01-GA-2 | 10 | 2025-07-23 | 2025-08-25 | DONE
|  |  | HANDLE WELDMENT (LONG) | RT-87540-0183-01-DD-2 | 1 |  |  | DONE
71652 | RT79-87540-PN-R003 | Candu | Threaded Hole Insp Tool Lg- MOD | RT-87540-0147-01-GA-2 | 14 | 2025-07-23 | 2025-08-25 | DONE
71653 | RT79-87540-PN-R003 | Candu | Foam Tray - RT-7547-001-PRT | RT-87540-0196-1-GA-E | 8 | 2025-07-23 | 2025-08-25 | DONE
71654 | RT79-87540-PN-R003 | Candu | Nut Adjuster - RT-7542 | RT-87540-0107-1-DD-2 | 8 | 2025-07-23 | 2025-08-25 | DONE
71655 | RT79-87540-PN-R003 | Candu | Spirol Pin Rem. Tool- RT-7543-000-PRT (ASSY) | RT-87540-0109-01-GA-2 | 8 | 2025-07-23 | 2025-08-25 | DONE
|  |  | ADAPTOR WELDMENT | RT-87540-0110-01-DD-2 | 1 |  |  | DONE
|  |  | PIN | RT-87540-0111-01-DD-2 | 1 |  |  | DONE
|  |  | SLIDE HAMMER ASSEMBLY | RT-87540-0142-01-GA-2 | 1 |  |  | DONE
71656 | RT79-87540-PN-R003 | Candu | Catch Tray - RT-7547-000-PRT | RT-87540-0118-01-GA-D | 8 | 2025-07-23 | 2025-08-25 | DONE
71657 | RT79-87540-PN-R003 | Candu | Stud Removal Tool - RT-7546-000-PRT | RT-87540-0117-1-GA-2 | 8 | 2025-07-23 | 2025-08-25 | DONE
71658 | RT79-87540-PN-R003 | Candu | Spring Pin Removal Tool - RT-7549-000-PRT | RT-87540-0174-1-GA-0 | 8 | 2025-07-23 | 2025-08-25 | DONE
|  |  | ACME NUT HOLDER | RT-87540-0160-01-DD-2 | 1 |  |  | DONE
|  |  | HANDLE | RT-87540-0161-01-DD-2 | 1 |  |  | DONE
|  |  | BRONZE BEARING | RT-87540-0162-01-DD-2 | 1 |  |  | DONE
|  |  | TUBING WELDMENT | RT-87540-0163-01-DD-2 | 1 |  |  | DONE
|  |  | SHAFT SUPPORT | RT-87540-0164-01-DD-2 | 1 |  |  | DONE
|  |  | HANDLE BAR | RT-87540-0165-01-DD-2 | 1 |  |  | DONE
|  |  | ACME SCREW-MODIFIED | RT-87540-0170-01-DD-2 | 1 |  |  | DONE
|  |  | REACTION PLATE | RT-87540-0171-01-DD-2 | 1 |  |  | DONE
|  |  | BAR | RT-87540-0172-01-DD-2 | 1 |  |  | DONE
|  |  | TAP HOLDER | RT-87540-0173-01-DD-2 | 1 |  |  | DONE
71659 | RT79-87540-PN-R003 | Candu | Yoke Ret. Clamp - RT-7541-000-PRT | RT-87540-0101-01-GA-2 | 8 | 2025-07-23 | 2025-08-25 | DONE
71660 | RT79-87540-PN-R003 | Candu | Spacer Clip Rem. Tool - RT-7541-000-PRT | RT-87540-0178-01-GA-2 | 8 | 2025-07-23 | 2025-08-25 | DONE
|  |  | BLOCK | RT-87540-0177-01-DD-2 | 1 |  |  | DONE
|  |  | PIN | RT-87540-0175-01-DD-2 | 1 |  |  | DONE
|  |  | HANDLE WELDMENT | RT-87540-0176-01-DD-2 | 1 |  |  | DONE
71669 | RT79-87920-PN-R005 | Candu | CTI Bore Gauge | RT-87920-0351-01-GA-D | 5 | 2025-08-08 | 2025-08-25 | DONE |  | 2025-07-25: ASSY; 2025-08-04: DEBURR; 2025-08-05: DEBURR; 2025-08-06: INS,DIR; 2025-08-07: INS,DIR; 2025-08-08: Pack; 2025-08-11: Pack
|  |  | CENTERING RING CTRJ | RT38-16300-033_000-0000-001-01-DD-B | 1 |  |  | DONE
|  |  | MODIFIED COLLAR | RT38-87920-0651-1-DD-B | 3 |  |  | DONE
|  |  | LANDING TIP | RT38-16300-033_000-0000-002-01-DD-B | 3 |  |  | DONE
|  |  | MKII BORE GAUGE (VENDOR SUPPLIED) | RT-87920-0352-01-DD-D | 1 |  |  | DONE
|  |  | BUSHING | RT38-15300-032_000-0000-006-01-DD-C | 1 |  |  | DONE
|  |  | DIGIMATIC INDICATOR PROTECTIVE COVER ASSEMBLY | RT38-17000-054_000-1000-000-01-GA-C | 1 |  |  | DONE
|  |  | DIGIMATIC INDICATOR PROTECTIVE COVER BASE | RT38-17000-054_000-1000-001-01-DD-C | 1 |  |  | DONE
|  |  | DIGIMATIC INDICATOR PROTECTIVE COVER CLAMP | RT38-17000-054_000-1000-002-01-DD-B | 1 |  |  | DONE
|  |  | DIGITAL INDICATOR PROTECTIVE COVER | RT-87920-0358-01-GA-D | 1 |  |  | DONE
71699 | MCR-17000-PN-R047- Rev.4 | Candu | Anul Spacer Det.Tol-It#6,7,10,12,13,14,15,16,19,20,22,&23 | MCR-17300-030-00000-01-GA-E | 2 | 2025-12-28
|  |  | U3 CENTERING RING- NO THRU CUT | MCR-17300-030-000001-01-DD-C | 7
|  |  | U3 CENTERING RING-THRU CUT | MCR-17300-030-000002-01-DD-C | 11
|  |  | U3 SHIELD PLUG-THRU CUT | MCR-17300-030-000003-01-DD-C | 4
|  |  | U3 SHIELD PLUG | MCR-17300-030-000004-01-DD-C | 2
|  |  | U3 MARKER RING | MCR-17300-030-000005-01-DD-C | 8
|  |  | U3 OUTBOARD PIECE | MCR-17300-030-000006-01-DD-C | 1
|  |  | U3 SLIDER BLOCK | MCR-17300-030-000007-01-DD-C | 1
|  |  | U3 PIPE WELDMENT 1 | 2 MCR-17300-030-100000-01-GA-C | 2
|  |  | U3 PIPE WELDMENT 2 | MCR-17300-030-200000-01-GA-C | 1
|  |  | U3 BALL PIN ASSEMBLY | MCR-17300-030-300000-01-GA-C | 1
|  |  | QUICK RELEASE PIN, MODIFIED | MCR-17000-030-400000-01-GA-C | 2
|  |  | HEAD ADAPTER | MCR-17300-008-000001-01-DD-C | 1
|  |  | COILFORMER BODY | MCR-17300-008-000004-01-DD-C | 1
|  |  | INBOARD PIECE | MCR-17300-008-000007-01-DD-C | 1
|  |  | STAND OFF | MCR-17300-008-000008-01-DD-C | 2
71710 | RT79-88040-PN-R002 | Candu | PT Straightening Tool | RT-88000-70085-000-1-GA-E | 3 | 2025-07-23 | 2025-08-28 | DONE |  | 2025-08-25: ASSY; 2025-08-26: INS,DIR; 2025-08-27: INS,DIR
|  |  | PIVOT PIN-PART 1 (31910-637-1) | 12918-0085-0002 (RT-88000-70085-002-1-DD-B) | 1 |  |  | DONE
|  |  | ADJUSTING SCREW-PART1 (31910-643-1) | 12918-0085-0003 (RT-88000-70085-003-1-DD-D) | 1 |  |  | DONE
|  |  | NUT (31910-640-1) | 12918-0085-0005 (RT-88000-70085-005-1-DD-B) | 1 |  |  | DONE | Receeive,INS
|  |  | ADJUSTING SCREW-PART2 (31910-643-1) | 12918-0085-0006 (RT-88000-70085-006-1-DD-D) | 1 |  |  | DONE
|  |  | SPACER (31910-639-1) | 12918-0085-0007 (RT-88000-70085-007-1-DD-B) | 2 |  |  | DONE
|  |  | PIVOT PIN-PART 2 (31910-637-1) | 12918-0085-0008 (RT-88000-70085-008-1-DD-B) | 1 |  |  | DONE
|  |  | SPIGOT (31910-641-1) | 12918-0085-0011 | 2 |  |  | DONE
|  |  | SHAFT (31910-644-1) | 12918-0085-0012 | 1 |  |  | DONE
|  |  | RT-0085-PT STRAIGHTENING TOOL ASSEMBLY | 12918-8530-0000 (RT-88000-78530-000-1-GA-E) | 2 |  |  | DONE
|  |  | SHAFT END (31910-573-1) | 12918-8530-0001 (RT-88000-78530-001-1-DD-B) | 1 |  |  | DONE
|  |  | SHAFT (31910-573-1) | 12918-8530-0002 (RT-88000-78530-002-1-DD-B) | 1 |  |  | DONE
|  |  | SHAFT ASSY (31910-573-1) | 12918-8530-0003 (RT-88000-78530-003-1-DD-D) | 1 |  |  | DONE
|  |  | SHAFT END (31910-573-1) | 12918-8530-0001 (RT-88000-78530-001-1-DD-B) | 1 |  |  | DONE
|  |  | SHAFT (31910-573-1) | 12918-8530-0002 (RT-88000-78530-002-1-DD-B) | 1 |  |  | DONE
|  |  | RT-0085-PT STRAIGHTENING TOOL ASSEMBLY | 12918-8510-0000 (RT-88000-78510-000-1-GA-D) | 2 |  |  | DONE
|  |  | RT-0085-PT STRAIGHTENING TOOL ASSEMBLY | 12918-8520-0000 (RT-88000-78520-000-1-GA-D) | 1 |  |  | DONE
|  |  | HOUSING CENTER (31910-634-1) | 12918-8520-0001 (RT-88000-78530-001-1-GA-E) | 1 |  |  | DONE
|  |  | HOUSING END (31910-635-1) | 12918-8520-0002 (RT-88000-78530-002-1-GA-E) | 2 |  |  | DONE
|  |  | HOUSING ASSY (31910-632-1) | 12918-8520-0003 (RT-88000-78520-003-1-DD-D/RT-88000-78520-003-2-DD-D) | 1 |  |  | DONE
|  |  | HOUSING BUSHING (31910-638-1) 4.5DIA. X 1.3 LG. | 12918-8510-0002 (RT-88000-78510-002-1-DD-B) | 2 |  |  | DONE
|  |  | HOUSING ASSEMBLY (31910-645-1) | 12918-8510-0003 (RT-88000-78510-003-1-DD-D) | 1 |  |  | DONE
|  |  | RT-0085-PT STRAIGHTENING TOOL ASSEMBLY | 12918-8520-0000 (RT-88000-78520-000-1-GA-D) | 1 |  |  | DONE
|  |  | HOUSING CENTER (31910-634-1) | 12918-8520-0001 (RT-88000-78530-001-1-GA-E) | 1 |  |  | DONE
|  |  | HOUSING END (31910-635-1) | 12918-8520-0002 (RT-88000-78530-002-1-GA-E) | 2 |  |  | DONE
|  |  | HOUSING ASSY (31910-632-1) | 12918-8520-0003 (RT-88000-78520-003-1-DD-D/RT-88000-78520-003-2-DD-D) | 1 |  |  | DONE
71711 | RT79-88040-PN-R002 | Candu | Actuator Tool | RT-88000-70086-000-1-GA-E | 3 | 2025-07-23 | 2025-08-28 | DONE
|  |  | CENTERING DISC (98-31910-723-1) | 12918-0086-0003 (RT-88000-70086-003-1-DD-B) | 3 |  |  | DONE
|  |  | REAR RADIATION SHIELD | 12918-0086-0004 (RT-88000-70086-004-1-DD-B) | 1 |  |  | DONE
|  |  | FRONT RADIATION SHIELD | 12918-0086-0005 (RT-88000-70086-005-1-DD-B) | 1 |  |  | DONE
|  |  | LONG ADJUSTING WRENCH ASSY (98-31910-580-1) | 12918-8610-0000 (RT-88000-78610-000-1-GA-E) | 1 |  |  | DONE
|  |  | HANDLE (98-31910-578-1) | 12918-8610-0001 | 1 |  |  | DONE
|  |  | SHAFT (98-31910-580-1) | 12918-8610-0002 | 1 |  |  | DONE
|  |  | ADJUSTING WRENCH (98-31910-580-1) ASSY | 12918-8610-0003 (RT-88000-78610-003-1-DD-D) | 1 |  |  | DONE
|  |  | HANDLE (98-31910-578-1) | 12918-8610-0001 | 1 |  |  | DONE
|  |  | SHAFT (98-31910-580-1) | 12918-8610-0002 | 1 |  |  | DONE
|  |  | SHIELD PLUG | 12918-8610-0004 (RT-88000-78610-004-1-DD-B) | 1 |  |  | DONE
|  |  | SHIELD PLUG | 12918-8610-0004 (RT-88000-78610-004-1-DD-B) | 1 |  |  | DONE
|  |  | TORQUE RESTRAINING TOOL ASSY (31910-578-1) | 12918-8620-0000 (RT-88000-78620-000-1-GA-E) | 1 |  |  | DONE
|  |  | HANDLE (98-31910-578-1) | 12918-8620-0001 (RT-88000-78620-001-1-DD-B) | 1 |  |  | DONE
|  |  | SHAFT 2 (98-31910-578-1) | 12918-8620-0002 (RT-88000-78620-002-1-DD-B) | 1 |  |  | DONE
|  |  | HEAD (98-31910-578-1) | 12918-8620-0003 (RT-88000-78620-003-1-DD-B) | 1 |  |  | DONE
|  |  | PIN (98-31910-578-1) | 12918-8620-0004 (RT-88000-78620-004-1-DD-B) | 2 |  |  | DONE
|  |  | TRQUE RESTRAINING TOOL (31910-578-1) ASSY | 12918-8620-0005 (RT-88000-78620-005-1-DD-D) | 1 |  |  | DONE
|  |  | HANDLE (98-31910-578-1) | 12918-8620-0001 (RT-88000-78620-001-1-DD-B) | 1 |  |  | DONE
|  |  | SHAFT 2 (98-31910-578-1) | 12918-8620-0002 (RT-88000-78620-002-1-DD-B) | 1 |  |  | DONE
|  |  | HEAD (98-31910-578-1) | 12918-8620-0003 (RT-88000-78620-003-1-DD-B) | 1 |  |  | DONE
|  |  | PIN (98-31910-578-1) | 12918-8620-0004 (RT-88000-78620-004-1-DD-B) | 2 |  |  | DONE
|  |  | SHIELD PLUG | 12918-8620-0006 | 1 |  |  | DONE
71712 | RT79-88040-PN-R002 | Candu | EF/PT Guide Tool ( New) | RT-88000-70118-000-1-GA-E | 3 | 2025-07-23 | 2025-08-28 | Need to fix |  | 2025-07-28: INS; 2025-07-29: INS; 2025-07-30: ASSY; 2025-07-31: ASSY; 2025-08-01: Fit,Tack,Weld; 2025-08-04: Fit,Tack,Weld; 2025-08-05: INS,DIR; 2025-08-06: INS,DIR; 2025-08-07: Pack; 2025-08-08: Pack; 2025-08-11: Ship; 2025-08-22: ASSSY; 2025-08-25: ASSSY
|  |  | SUPPORT ASSY | RT-88000-70118-001-1-DD-D | 1 |  |  | DONE
|  |  | Support Shaft | RT-88000-70118-071-1-DD-B | 6 |  |  | DONE
|  |  | SHAFT EXTENSION | RT-88000-70118-072-1-DD-B | 6 |  |  | DONE
|  |  | INBOARD GUIDE ASSY | RT-88000-70118-042-1-DD-B | 1 |  |  | DONE
|  |  | GUIDE RING | RT-88000-70118-038-1-DD-B | 1 |  |  | DONE
|  |  | ECCENTRIC LOCATOR | RT-88000-70118-050-1-DD-B | 1 |  |  | DONE
|  |  | ECCENTRIC LOCATOR | RT-88000-70118-040-1-DD-B | 2 |  |  | DONE
|  |  | CENTERING RING | RT-88000-70118-037-1-DD-B | 3 |  |  | DONE
|  |  | CENTERING RING | RT-88000-70118-036-1-DD-B | 1 |  |  | DONE
|  |  | ADJUSTABLE STOP | RT-88000-70118-019-1-DD-B | 1 |  |  | DONE
|  |  | HANDLE | RT-88000-70118-021-1-DD-B | 1 |  |  | DONE
|  |  | ARM | RT-88000-70118-005-1-DD-B | 2 |  |  | DONE
|  |  | TUBE POSITION INDICATOR | RT-88000-70118-051-1-DD-B | 1 |  |  | DONE
|  |  | TUBE | RT-88000-70118-049-1-DD-B | 1 |  |  | DONE
|  |  | TUBE STOP SET-UP TOOL | RT-88000-70118-004-1-DD-B | 1 |  |  | DONE
|  |  | SPROCKET | RT-88000-70118-016-1-DD-B | 1 |  |  | DONE
|  |  | ADJUSTER BLOCK | RT-88000-70118-011-1-DD-B | 1 |  |  | DONE
|  |  | SHAFT | RT-88000-70118-034-1-DD-B | 2 |  |  | DONE
|  |  | SHAFT | RT-88000-70118-010-1-DD-B | 2 |  |  | DONE
|  |  | SHAFT | RT-88000-70118-014-1-DD-B | 1 |  |  | DONE
|  |  | SHAFT EXTENSION | RT-88000-70118-031-1-DD-B | 1 |  |  | DONE
|  |  | SHAFT EXTENSION | RT-88000-70118-030-1-DD-B | 1 |  |  | DONE
|  |  | SHAFT EXTENSION | RT-88000-70118-029-1-DD-B | 1 |  |  | DONE
|  |  | ROLLER | RT-88000-70118-008-1-DD-B | 1 |  |  | DONE
|  |  | ROLLER | RT-88000-70118-006-1-DD-B | 2 |  |  | DONE
|  |  | ROLLER SUPPORT | RT-88000-70118-007-1-DD-B | 1 |  |  | DONE
|  |  | ROLLER SHAFT | RT-88000-70118-046-1-DD-B | 1 |  |  | DONE
|  |  | PIVOT PIN | RT-88000-70118-009-1-DD-B | 2 |  |  | DONE
|  |  | PLUNGER | RT-88000-70118-022-1-DD-B | 1 |  |  | DONE
|  |  | SPACER | RT-88000-70118-045-1-DD-B | 1 |  |  | DONE
|  |  | SPACER | RT-88000-70118-013-1-DD-B | 2 |  |  | DONE
|  |  | THRUST WASHER | RT-88000-70118-043-1-DD-B | 1 |  |  | DONE
|  |  | PIVOT | RT-88000-70118-073-1-DD-B | 12 |  |  | DONE
|  |  | PLATE | RT-88000-70118-070-1-DD-D | 6 |  |  | DONE
|  |  | SHIELD | RT-88000-70118-083-1-DD-D | 2 |  |  | DONE
71713 | RT79-88040-PN-R002 | Candu | SSDO Saddle | RT-88030-0080-01-GA-C | 4 | 2025-07-23 | 2025-08-28 | DONE | Assemble
|  |  | HANDLE WELDMENT | RT-88030-0086-01-DD-D | 1 |  |  | DONE
|  |  | PIVOT FORK | RT-88030-0082-01-DD-B | 1 |  |  | DONE
|  |  | SUPPORT SADDLE | RT-88030-0084-01-DD-B | 1 |  |  | DONE
|  |  | PIVOT BASE | RT-88030-0085-01-DD-B | 1 |  |  | DONE
|  |  | BASE PLATE | RT-88030-0081-01-DD-B | 1 |  |  | DONE
|  |  | SPACER | RT-88030-0083-01-DD-B | 1 |  |  | DONE
|  |  | RETAINING WASHER | RT-88030-0087-01-DD-B | 2 |  |  | DONE
71714 | RT79-88040-PN-R002 | Candu | Removal Tool Trough | RT-88000-70103-016-1-GA-D | 1 | 2025-07-23 | 2025-08-28 | DONE
|  |  | CONNECTION BLOCK | RT-88000-70103-015-1-DD-C | 1 |  |  | DONE
|  |  | TROUGH ASSEMBLY | RT-88000-70103-010-1-GA-D | 1 |  |  | DONE
|  |  | ANGLE WELDMENT | RT-88000-70103-008-1-DD-D | 1 |  |  | DONE
|  |  | ANGLE, CONNECTOR | RT-88000-70103-009-1-DD-C | 1 |  |  | DONE
|  |  | AXIAL ALIGNMENT BRACKET ASSEMBLY | RT-88000-70103-014-1-GA-C | 1 |  |  | DONE
|  |  | BAR | RT-88000-70103-011-1-DD-C | 1 |  |  | DONE
|  |  | BASE PLATE | RT-88000-70103-012-1-DD-C | 1 |  |  | DONE
|  |  | SLIDER BLOCK | RT-88000-70103-013-1-DD-C | 1 |  |  | DONE
71717 | PD-20551 | Woodbridge | Puffer Caps & Nozzles 34 x 40 mesh | RTD-3040/3033 | 168000 | 2025-12-01
71718 | PD-20551 | Woodbridge | Puffer Caps & Nozzles 34 x 50 Mesh | RTD-3040/3033 | 32000 | 2025-12-01
71730 | RT79-87540-PN-R001 | Candu | Positioning Stud Rotation tool | RT-87540-0169-1-DD-2 | 3 | 2025-07-11 | Awating Candu release | DONE
71731 | RT79-87540-PN-R001 | Candu | Spacer Clip Installation Tool | RT-87540-0123-1-GA-1 | 3 | 2025-07-11 | Awating Candu release | DONE
|  |  | HANDLE WELDMENT | RT-87540-0124-01-DD-2 | 1 |  |  | DONE
|  |  | MODIFIED DETENT PIN | RT-87540-0125-01-DD-2 | 1 |  |  | DONE
|  |  | ADAPTOR | RT-87540-0126-01-DD-2 | 1 |  |  | DONE
|  |  | MODIFIED MAGNET, RING | RT-87540-0143-01-DD-3 | 1 |  |  | DONE
71732 | RT79-87540-PN-R001 | Candu | Temporary Yoke Pin | RT-87540-0120-1-GA-2 | 3 | 2025-07-11 | Awating Candu release | DONE
|  |  | PIN | RT-87540-0121-01-DD-2 | 1 |  |  | DONE
|  |  | HANDLE | RT-87540-0122-01-DD-2 | 1 |  |  | DONE
71733 | RT79-87540-PN-R001 | Candu | Spring Pin Installation Spacer | RT-87540-0205-1-DD-2 | 3 | 2025-07-11 | Awating Candu release | DONE
71734 | RT79-87540-PN-R001 | Candu | Threaded Hole Insp. Tool ( Short) | RT-87540-0144-1-GA-2 | 7 | 2025-07-11 | Awating Candu release | DONE
|  |  | COUPLING, TOOL HOLDER | RT-87540-0146-01-DD-2 |  |  |  | DONE
|  |  | HANDLE ASSEMBLY (SHORT) | RT-87540-0145-01-GA-1
|  |  | MODIFIED THREADED PLUG GAUGE SET 1.25-8 UN-2B | RT-87540-0147-01-GA-2 |  |  |  | DONE
71735 | RT79-87540-PN-R001 | Candu | Threaded Hole Repairing tool ( Short) | RT-87540-0186-1-GA-2 | 7 | 2025-07-11 | Awating Candu release | DONE
|  |  | HANDLE WELDMENT (SHORT) | RT-87540-0180-01-DD-2 | 1 |  |  | DONE
71736 | RT79-87540-PN-R001 | Candu | Spring Pin Insetion Tool | RT-87540-0137-1-GA-2 | 7 | 2025-07-11 | Awating Candu release | DONE
|  |  | SHAFT WELDMENT | RT-87540-0113-01-DD-2 | 1 |  |  | DONE
|  |  | SUPPORT BRACKET | RT-87540-0114-01-DD-2 | 1 |  |  | DONE
|  |  | SPRING PIN HOLDER | RT-87540-0140-01-DD-2 | 1 |  |  | DONE
71737 | RT79-87540-PN-R001 | Candu | Spring Pin Holder | RT-87540-0140-1-DD-2 | 14 | 2025-07-11 | Awating Candu release | DONE
71738 | RT79-87540-PN-R001 | Candu | PA Spacer Clip Inst. Tool- Detent Pin Mod | RT-87540-0125-1-DD-2 | 14 | 2025-07-11 | Awating Candu release | DONE
71739 | RT79-87540-PN-R001 | Candu | Lattice Sleeve Rem. Tool HWT Mounted | RT-87600-0250-1-GA-E | 1 | 2025-07-11 | Awating Candu release | DONE
|  |  | BASE WELDMENT | RT-87600-0251-1-DD-E | 1 |  |  | DONE
|  |  | FLANGE BEAM WELDMENT | RT-87600-0252-1-DD-E | 1 |  |  | DONE
|  |  | SLEEVE BRACKET WELDMENT | RT-87600-0253-1-DD-D | 1 |  |  | DONE
|  |  | CYLINDER PUSH BRACKET WELDMENT | RT-87600-0254-1-DD-D | 1 |  |  | DONE
|  |  | CYLINDER MOUNTING BRACKET WELDMENT (RH) | RT-87600-0255-1-DD-D | 1 |  |  | DONE
|  |  | GUARD WELDMENT | RT-87600-0256-1-DD-D | 1 |  |  | DONE
|  |  | PIPE WELDMENT | RT-87600-0257-1-DD-C | 2 |  |  | DONE
|  |  | RING | RT-87600-0257-1-DD-C | 1 |  |  | DONE
|  |  | SPACER BLOCK | RT-87600-0259-1-DD-C | 2 |  |  | DONE
|  |  | STOP PLATE | RT-87600-0260-1-DD-C | 1 |  |  | DONE
|  |  | STOP PLATE 2 | RT-87600-0261-1-DD-C | 1 |  |  | DONE
|  |  | PUMP MOUNTING BRACKET | RT-87600-0262-1-DD-C | 1 |  |  | DONE
|  |  | SPACER PLATE | RT-87600-0263-1-DD-C | 1 |  |  | DONE
|  |  | CYLINDER NOSE | RT-87600-0264-1-DD-C | 1 |  |  | DONE
|  |  | TOOL STORAGE BRACKET | RT-87600-0265-1-DD-C | 2 |  |  | DONE
|  |  | TOOL BOX WELDMENT | RT-87600-0268-1-DD-D | 1 |  |  | DONE
|  |  | HEX BAR ASSEMBLY | RT-87600-0280-1-GA-C | 1 |  |  | DONE
|  |  | HEX BAR | RT-87600-0281-1-DD-C | 1 |  |  | DONE
71742 | RT98-87920-PN-R005 | Candu | CTI Bore Gauge | RT-87920-0351-01-GA-D | 5 | 2025-08-08 | 2025-08-25 | DONE |  | 2025-07-25: ASSY; 2025-07-28: ASSY; 2025-08-04: DEBURR; 2025-08-05: DEBURR; 2025-08-06: INS,DIR; 2025-08-07: INS,DIR; 2025-08-08: Pack; 2025-08-11: Pack
|  |  | CENTERING RING CTRJ | RT38-16300-033_000-0000-001-01-DD-B | 1 |  |  | DONE
|  |  | MODIFIED COLLAR | RT38-87920-0651-1-DD-B | 3 |  |  | DONE
|  |  | LANDING TIP | RT38-16300-033_000-0000-002-01-DD-B | 3 |  |  | DONE
|  |  | MKII BORE GAUGE (VENDOR SUPPLIED) | RT-87920-0352-01-DD-D | 1 |  |  | DONE
|  |  | BUSHING | RT38-15300-032_000-0000-006-01-DD-C | 1 |  |  | DONE
|  |  | DIGIMATIC INDICATOR PROTECTIVE COVER ASSEMBLY | RT38-17000-054_000-1000-000-01-GA-C | 1 |  |  | DONE
|  |  | DIGIMATIC INDICATOR PROTECTIVE COVER BASE | RT38-17000-054_000-1000-001-01-DD-C | 1 |  |  | DONE
|  |  | DIGIMATIC INDICATOR PROTECTIVE COVER CLAMP | RT38-17000-054_000-1000-002-01-DD-B | 1 |  |  | DONE
|  |  | DIGITAL INDICATOR PROTECTIVE COVER | RT-87920-0358-01-GA-D | 1 |  |  | DONE
71743 | RT79-87920-PN-R006 | Candu | Leak Test Vacuum Grease Clean'g tool | RT-87920-0353-01-GA-C | 3 | 2025-07-11 | 2025-08-20 | INS,DIR |  | 2025-07-14: Tack weld; 2025-07-28: Debbur; 2025-07-29: INS; 2025-07-30: INS
|  |  | HANDLE | RT38-87920-70627-1-DD-C | 2 |  |  | DONE
|  |  | BODY WELDMENT | RT-87920-0356-01-GA-D | 1 |  |  | DONE
71744 | RT79-87920-PN-R006 | Candu | CTI Cleaning Tool | RT-87920-0357-01-GA-C | 4 | 2025-07-25 | 2025-08-20 | DONE |  | 2025-07-14: Tack weld; 2025-07-18: Deburr; 2025-07-21: INS; 2025-07-22: INS; 2025-07-23: L-Etch; 2025-07-24: L-Etch; 2025-07-25: Paint; 2025-07-28: Paint; 2025-08-06: INS; 2025-08-07: INS; 2025-08-08: Pack; 2025-08-11: Pack; 2025-08-12: Ship
|  |  | HANDLE | RT-87920-70627-1-DD-C | 2 |  |  | DONE
|  |  | SHAFT COLLAR, 1.5 DIA |  | 3 |  |  | DONE
|  |  | SWAB HEAD ASSEMBLY | RT38-16300-024_000-0000-000-01-GA-C | 1 |  |  | DONE
|  |  | CLAMPING ROD | RT38-16300-024_000-0000-001-01-DD-C | 1 |  |  | DONE
|  |  | NUT | RT38-16300-024_000-0000-002-01-DD-C | 1 |  |  | DONE
|  |  | CLAMPING LINK | RT38-16300-024_000-0000-003-01-DD-C | 1 |  |  | DONE
|  |  | SWAB HEAD | RT38-16300-024_000-1000-000-01-GA-C | 1 |  |  | DONE
|  |  | BODY WELDMENT | RT-87920-0356-01-GA-D | 1 |  |  | DONE
71745 | RT79-87920-PN-R006 | Candu | CTI Cleaning Tool - Head | RT38-16300-024-00-00-000-01-GA-C | 8 | 2025-07-11 | 2025-08-20 | DONE
71746 | RT79-87920-PN-R006 | Candu | Vacuum Grease Cleaning Tool | RT-87920-0355-01-GA-C | 4 | 2025-07-11 | 2025-08-20 | DONE |  | 2025-07-25: INS
|  |  | CLAMPING ROD | RT38-16400-007_000-0000-001-01 | 1 |  |  | DONE
|  |  | NUT | RT38-16400-007_000-0000-002-01 | 1 |  |  | DONE
|  |  | CLAMPING DISK | RT38-16400-007_000-0000-003-01 | 1 |  |  | DONE
|  |  | CLAMPING LINK | RT38-16400-007_000-0000-004-01 | 1 |  |  | DONE
|  |  | SMALL HEAD ASSEMBLY | RT38-16400-007_000-1000-000-01-GA-C | 1 |  |  | DONE
71829 | RT98-87540-PN-R001 | Candu | Removal PA Tool Cart-RT-7538-000-PRT | RT-87540-0206-01-GA-E | 9 | 2025-07-23 | 2025-08-25 | DONE
|  |  | TOOL CART GENERAL ASSEMBLY | RT-87540-0200-01-GA-0 | 1 |  |  | DONE
|  |  | CATCH TRAY ASSEMBLY | RT-87540-0118-01-GA-0 | 1 |  |  | DONE
71830 | RT98-87540-PN-R001 | Candu | Yoke Removal/Inst Tool- RT-7545-000-PRT | RT-87540-0105-01-GA-0 | 16 | 2025-07-23 | 2025-08-25 | DONE
|  |  | BRACKET | RT-87540-0131-01-DD-2 | 1 |  |  | DONE
|  |  | SHORT STUD | RT-87540-0136-01-DD-2 | 1 |  |  | DONE
|  |  | LONG STUD | RT-87540-0135-01-DD-2 | 1 |  |  | DONE
|  |  | COUPLING | RT-87540-0134-01-DD-2 | 1 |  |  | DONE
|  |  | OUTER TUBE | RT-87540-0133-01-DD-2 | 1 |  |  | DONE
|  |  | INNER TUBE | RT-87540-0132-01-DD-2 | 1 |  |  | DONE
71831 | RT98-87540-PN-R001 | Candu | Sheared Pin Punch Tool | RT-87540-0112-01-GA-2 | 8 | 2025-07-23 | 2025-08-25 | DONE
|  |  | SHAFT WELDMENT | RT-87540-0113-01-DD-2 | 1 |  |  | DONE
|  |  | SUPPORT BRACKET | RT-87540-0114-01-DD-2 | 1 |  |  | DONE
|  |  | PIN HOLDER |  | 1 |  |  | DONE
71832 | RT98-87540-PN-R001 | Candu | Pin Holder- RT-7544-001- PRT | RT-87540-0115-01-DD-2 | 7 | 2025-07-23 | 2025-08-25 | DONE
71833 | RT98-87540-PN-R001 | Candu | Punch Pin- RT-8063-001-PRT | RT-87540-0111-01-DD-2 | 28 | 2025-07-23 | 2025-08-25 | DONE
71834 | RT98-87540-PN-R001 | Candu | Thread Hole Insp Tool LG- RT-7536-000-PRT | RT-87540-0148-01-GA-2 | 11 | 2025-07-23 | 2025-08-25 | DONE
|  |  | HANDLE WELDMENT (LONG) | RT-87540-0149-01-DD-2 | 1 |  |  | DONE
|  |  | COUPLING, TOOL HOLDER | RT-87540-0146-01-DD-2 | 1 |  |  | DONE
|  |  | MODIFIED THREADED PLUG GAUGE SET 1.25-8 UN-2B | RT-87540-0147-01-GA-2 | 1 |  |  | DONE
71835 | RT98-87540-PN-R001 | Candu | Thread Hole Repair Tool- RT-7539-000-PRT | RT-87540-0184-01-GA-2 | 11 | 2025-07-23 | 2025-08-25 | DONE
|  |  | HANDLE WELDMENT (LONG) | RT-87540-0183-01-DD-2 | 1 |  |  | DONE
71836 | RT98-87540-PN-R001 | Candu | Threaded Hole Insp Tool Lg- MOD | RT-87540-0147-01-GA-2 | 14 | 2025-07-23 | 2025-08-25 | DONE
71837 | RT98-87540-PN-R001 | Candu | Foam Tray - RT-7547-001-PRT | RT-87540-0196-1-GA-E | 8 | 2025-07-23 | 2025-08-25 | DONE
|  |  | RUBBER FOAM 36" X 36" X 3/8" THK | SBR FOAM RUBBER / # 8647K45 | 1 |  |  | DONE
|  |  | TUBE, 1/2" OD X .049" THK x 48" LG | STAINLESS STEEL, TYPE-304 / # 8989K25 | 2 |  |  | DONE
71838 | RT98-87540-PN-R001 | Candu | Nut Adjuster - RT-7542 | RT-87540-0107-1-DD-2 | 8 | 2025-07-23 | 2025-08-25 | DONE
|  |  | ADJUSTER | RT-87540-0108-1-DD-2 | 16 |  |  | DONE
71839 | RT98-87540-PN-R001 | Candu | Spirol Pin Rem. Tool- ASSY | RT-87540-0109-01-GA-2 | 8 | 2025-07-23 | 2025-08-25 | DONE
|  |  | ADAPTOR WELDMENT | RT-87540-0110-01-DD-2 | 1 |  |  | DONE
|  |  | PIN | RT-87540-0111-01-DD-2 | 1 |  |  | DONE
|  |  | SLIDE HAMMER ASSEMBLY | RT-87540-0142-01-GA-2 | 1 |  |  | DONE
|  |  | SCREW SET HEX SOC CUP POINT #10-24UNC-3A X 3/16 LG | ALLOY STL. / #HK358-1044 | 1 |  |  | DONE
|  |  | GUIDE ASSY | RT-88030-0018-01-GA-2 |  |  |  | DONE
71840 | RT98-87540-PN-R001 | Candu | Catch Tray - RT-7547-000-PRT | RT-87540-0118-01-GA-D | 8 | 2025-07-23 | 2025-08-25 | DONE
71841 | RT98-87540-PN-R001 | Candu | Stud Removal Tool - RT-7546-000-PRT | RT-87540-0117-1-GA-2 | 8 | 2025-07-23 | 2025-08-25 | DONE
71842 | RT98-87540-PN-R001 | Candu | Spring Pin Removal Tool - RT-7549-000-PRT | RT-87540-0174-1-GA-0 | 6 | 2025-07-23 | 2025-08-25 | DONE
|  |  | ACME NUT HOLDER | RT-87540-0160-01-DD-2 | 1 |  |  | DONE
|  |  | HANDLE | RT-87540-0161-01-DD-2 | 1 |  |  | DONE
|  |  | BRONZE BEARING | RT-87540-0162-01-DD-2 | 1 |  |  | DONE
|  |  | TUBING WELDMENT | RT-87540-0163-01-DD-2 | 1 |  |  | DONE
|  |  | SHAFT SUPPORT | RT-87540-0164-01-DD-2 | 1 |  |  | DONE
|  |  | HANDLE BAR | RT-87540-0165-01-DD-2 | 1 |  |  | DONE
|  |  | ACME SCREW-MODIFIED | RT-87540-0170-01-DD-2 | 1 |  |  | DONE
|  |  | REACTION PLATE | RT-87540-0171-01-DD-2 | 1 |  |  | DONE
|  |  | BAR | RT-87540-0172-01-DD-2 | 1 |  |  | DONE
|  |  | TAP HOLDER | RT-87540-0173-01-DD-2 | 1 |  |  | DONE
71843 | RT98-87540-PN-R001 | Candu | Yoke Ret. Clamp - RT-7541-000-PRT | RT-87540-0101-01-GA-2 | 8 | 2025-07-23 | 2025-08-25 | DONE
71844 | RT98-87540-PN-R001 | Candu | Spacer Clip Rem. Tool - RT-7541-000-PRT | RT-87540-0178-01-GA-2 | 8 | 2025-07-23 | 2025-08-25 | DONE
|  |  | BLOCK | RT-87540-0177-01-DD-2 | 1 |  |  | DONE
|  |  | PIN | RT-87540-0175-01-DD-2 | 1 |  |  | DONE
|  |  | HANDLE WELDMENT | RT-87540-0176-01-DD-2 | 1 |  |  | DONE
71845 | RT98-87540-PN-R002 | Candu | PT Straightening Tool | RT-88000-70085-000-1-GA-E | 3 | 2025-07-23 | 2025-08-25 | ASSY Almost Done |  | 2025-07-28: Gather All items; 2025-07-29: ASSY; 2025-07-30: ASSY; 2025-07-31: INS,DIR; 2025-08-01: INS,DIR; 2025-08-04: Pack; 2025-08-05: Pack; 2025-08-25: ASSY; 2025-08-26: INS,DIR; 2025-08-27: INS,DIR
|  |  | PIVOT PIN-PART 1 (31910-637-1) | 12918-0085-0002 (RT-88000-70085-002-1-DD-B) | 1 |  |  | DONE
|  |  | ADJUSTING SCREW-PART1 (31910-643-1) | 12918-0085-0003 (RT-88000-70085-003-1-DD-D) | 1 |  |  | DONE
|  |  | NUT (31910-640-1) | 12918-0085-0005 (RT-88000-70085-005-1-DD-B) | 1 |  |  | DONE
|  |  | ADJUSTING SCREW-PART2 (31910-643-1) | 12918-0085-0006 (RT-88000-70085-006-1-DD-D) | 1 |  |  | DONE
|  |  | SPACER (31910-639-1) | 12918-0085-0007 (RT-88000-70085-007-1-DD-B) | 2 |  |  | DONE
|  |  | PIVOT PIN-PART 2 (31910-637-1) | 12918-0085-0008 (RT-88000-70085-008-1-DD-B) | 1 |  |  | DONE
|  |  | SPIGOT (31910-641-1) | 12918-0085-0011 | 2 |  |  | DONE
|  |  | SHAFT (31910-644-1) | 12918-0085-0012 | 1 |  |  | DONE
|  |  | RT-0085-PT STRAIGHTENING TOOL ASSEMBLY | 12918-8530-0000 (RT-88000-78530-000-1-GA-E) | 2 |  |  | DONE
|  |  | SHAFT END (31910-573-1) | 12918-8530-0001 (RT-88000-78530-001-1-DD-B) | 1 |  |  | DONE
|  |  | SHAFT (31910-573-1) | 12918-8530-0002 (RT-88000-78530-002-1-DD-B) | 1 |  |  | DONE
|  |  | SHAFT ASSY (31910-573-1) | 12918-8530-0003 (RT-88000-78530-003-1-DD-D) | 1 |  |  | DONE
|  |  | SHAFT END (31910-573-1) | 12918-8530-0001 (RT-88000-78530-001-1-DD-B) | 1 |  |  | DONE
|  |  | SHAFT (31910-573-1) | 12918-8530-0002 (RT-88000-78530-002-1-DD-B) | 1 |  |  | DONE
|  |  | RT-0085-PT STRAIGHTENING TOOL ASSEMBLY | 12918-8510-0000 (RT-88000-78510-000-1-GA-D) | 2 |  |  | DONE
|  |  | RT-0085-PT STRAIGHTENING TOOL ASSEMBLY | 12918-8520-0000 (RT-88000-78520-000-1-GA-D) | 1 |  |  | DONE
|  |  | HOUSING CENTER (31910-634-1) | 12918-8520-0001 (RT-88000-78530-001-1-GA-E) | 1 |  |  | DONE
|  |  | HOUSING END (31910-635-1) | 12918-8520-0002 (RT-88000-78530-002-1-GA-E) | 2 |  |  | DONE
|  |  | HOUSING ASSY (31910-632-1) | 12918-8520-0003 (RT-88000-78520-003-1-DD-D/RT-88000-78520-003-2-DD-D) | 1 |  |  | DONE
|  |  | HOUSING BUSHING (31910-638-1) 4.5DIA. X 1.3 LG. | 12918-8510-0002 (RT-88000-78510-002-1-DD-B) | 2 |  |  | DONE
|  |  | HOUSING ASSEMBLY (31910-645-1) | 12918-8510-0003 (RT-88000-78510-003-1-DD-D) | 1 |  |  | DONE | Receive or Stock
|  |  | RT-0085-PT STRAIGHTENING TOOL ASSEMBLY | 12918-8520-0000 (RT-88000-78520-000-1-GA-D) | 1 |  |  | DONE
|  |  | HOUSING CENTER (31910-634-1) | 12918-8520-0001 (RT-88000-78530-001-1-GA-E) | 1 |  |  | DONE
|  |  | HOUSING END (31910-635-1) | 12918-8520-0002 (RT-88000-78530-002-1-GA-E) | 2 |  |  | DONE
|  |  | HOUSING ASSY (31910-632-1) | 12918-8520-0003 (RT-88000-78520-003-1-DD-D/RT-88000-78520-003-2-DD-D) | 1 |  |  | DONE
71846 | RT98-87540-PN-R002 | Candu | Actuator Tool | RT-88000-70086-000-1-GA-E | 3 | 2025-07-23 | 2025-08-25 | DONE
|  |  | SHIELD PLUG | 12918-8620-0006 (RT-88000-78620-006-1-DD-B) | 1 |  |  | DONE
|  |  | SOLOTTED SPRING TENSION PIN-STAINLES… | 240-012 (SPAENAUR) | 1 |  |  | DONE
|  |  | CENTERING DISC (98-31910-723-1) | 12918-0086-0003 (RT-88000-70086-003-1-DD-B) | 3 |  |  | DONE
|  |  | REAR RADIATION SHIELD | 12918-0086-0004 (RT-88000-70086-004-1-DD-D) | 1 |  |  | DONE
|  |  | FRONT RADIATION SHIELD | 12918-0086-0005 (RT-88000-70086-005-1-DD-D) | 1 |  |  | DONE
|  |  | SPCKET HEAD CAP SCREW | SHCS 1/4-20X1 (HARDWARE) | 6 |  |  | DONE
|  |  | SOCKET HEAD CAP SCREW-STAINLESS STEEL | 73496 (FASTENAL) | 8 |  |  | DONE
|  |  | SHIELD PLUG | 12918-8610-0004 | 1 |  |  | DONE
|  |  | 9/16",6-POINT DEEP SOCKET | SFS-181 (SNAP-ON) | 1 |  |  | DONE
|  |  | SOLOTTED SPRING TENSION PIN-STAINLES… | 240-012 (SPAENAUR) | 1 |  |  | DONE
|  |  | LONG ADJUSTING WRENCH ASSY (9831910-580-1) | 12918-8610-0000 (RT-88000-78610-000-A-GA-E) | 1 |  |  | DONE
|  |  | HANDLE (98-31910-578-1) | 12918-8610-0001 (RT- | 1 |  |  | DONE
|  |  | SHAFT (98-31910-580-1) | 12918-8610-0002 | 1 |  |  | DONE
|  |  | ADJUSTING WRENCH (98-31910-580-1) ASSY | 12918-8610-0003 (RT-88000-78610-003-1-DD-D) | 1 |  |  | DONE
|  |  | HANDLE (98-31910-578-1) | 12918-8610-0001 (RT- | 1 |  |  | DONE
|  |  | SHAFT (98-31910-580-1) | 12918-8610-0002 | 1 |  |  | DONE
|  |  | SHIELD PLUG | 12918-8610-0004 | 1 |  |  | DONE
|  |  | 9/16",6-POINT DEEP SOCKET | SFS-181 (SNAP-ON) | 1 |  |  | DONE
|  |  | SOLOTTED SPRING TENSION PIN-STAINLES… | 240-012 (SPAENAUR) | 1 |  |  | DONE
|  |  | TORQUE RESTRAINING TOOL ASSY (31910-578-1) | 12918-8620-0000 (RT-88000-78620-000-1-GA-E) | 1 |  |  | DONE
|  |  | HANDLE (98-31910-578-1) | 12918-8620-0001 (RT-88000-78620-001-1-DD-B) | 1 |  |  | DONE
|  |  | SHAFT 2 (98-31910-578-1) | 12918-8620-0002 (RT-88000-78620-002-1-DD-B) | 1 |  |  | DONE
|  |  | HEAD (98-31910-578-1) | 12918-8620-0003 (RT-88000-78620-003-1-DD-B) | 1 |  |  | DONE
|  |  | PIN (98-31910-578-1) | 12918-8620-0004 (RT-88000-78620-004-1-DD-B) | 2 |  |  | DONE
|  |  | TORQUE RESTRAINING TOOL ASSY (31910-578-1) | 12918-8620-0005 (RT-88000-78620-005-1-DD-D) | 1 |  |  | DONE
|  |  | HANDLE (98-31910-578-1) | 12918-8620-0001 (RT-88000-78620-001-1-DD-B) | 1 |  |  | DONE
|  |  | SHAFT 2 (98-31910-578-1) | 12918-8620-0002 (RT-88000-78620-002-1-DD-B) | 1 |  |  | DONE
|  |  | HEAD (98-31910-578-1) | 12918-8620-0003 (RT-88000-78620-003-1-DD-B) | 1 |  |  | DONE
|  |  | PIN (98-31910-578-1) | 12918-8620-0004 (RT-88000-78620-004-1-DD-B) | 2 |  |  | DONE
71847 | RT98-87540-PN-R002 | Candu | EF/PT Guide Tool ( New) | RT-88000-70118-000-1-GA-E | 3 | 2025-07-23 | 2025-08-25 | ASSY |  | 2025-07-28: INS; 2025-07-29: INS; 2025-07-30: ASSY; 2025-07-31: ASSY; 2025-08-01: Fit,Tack,Weld; 2025-08-04: Fit,Tack,Weld; 2025-08-05: INS,DIR; 2025-08-06: INS,DIR
|  |  | SUPPORT ASSY | RT-88000-70118-001-1-DD-D | 1 |  |  | DONE
|  |  | INBOARD GUIDE ASSY | RT-88000-70118-042-1-DD-B | 1 |  |  | DONE
|  |  | INBOARD GUIDE INSERT | RT-88000-70118-074-1-DD-B | 18 |  |  | DONE
|  |  | INBOARD GUIDE BODY | RT-88000-70118-075-1-DD-B | 6 |  |  | DONE
|  |  | GUIDE RING | RT-88000-70118-038-1-DD-B | 1 |  |  | DONE
|  |  | ECCENTRIC LOCATOR | RT-88000-70118-050-1-DD-B | 1 |  |  | DONE
|  |  | ECCENTRIC LOCATOR | RT-88000-70118-040-1-DD-B | 2 |  |  | DONE
|  |  | CENTERING RING | RT-88000-70118-037-1-DD-B | 3 |  |  | DONE
|  |  | CENTERING RING | RT-88000-70118-036-1-DD-B | 1 |  |  | DONE
|  |  | ADJUSTABLE STOP | RT-88000-70118-019-1-DD-B | 1 |  |  | DONE
|  |  | HANDLE | RT-88000-70118-021-1-DD-B | 1 |  |  | DONE
|  |  | ARM | RT-88000-70118-005-1-DD-B | 2 |  |  | DONE
|  |  | TUBE POSITION INDICATOR | RT-88000-70118-051-1-DD-B | 1 |  |  | DONE
|  |  | TUBE | RT-88000-70118-049-1-DD-B | 1 |  |  | DONE
|  |  | TUBE STOP SET-UP TOOL | RT-88000-70118-004-1-DD-B | 1 |  |  | DONE
|  |  | SPROCKET | RT-88000-70118-016-1-DD-B | 1 |  |  | DONE
|  |  | ADJUSTER BLOCK | RT-88000-70118-011-1-DD-B | 1 |  |  | DONE
|  |  | SHAFT | RT-88000-70118-034-1-DD-B | 2 |  |  | DONE
|  |  | SHAFT | RT-88000-70118-010-1-DD-B | 2 |  |  | DONE
|  |  | SHAFT | RT-88000-70118-014-1-DD-B | 1 |  |  | DONE
|  |  | SHAFT EXTENSION | RT-88000-70118-031-1-DD-B | 1 |  |  | DONE
|  |  | SHAFT EXTENSION | RT-88000-70118-030-1-DD-B | 1 |  |  | DONE
|  |  | SHAFT EXTENSION | RT-88000-70118-029-1-DD-B | 1 |  |  | DONE
|  |  | ROLLER | RT-88000-70118-008-1-DD-B | 1 |  |  | DONE
|  |  | ROLLER | RT-88000-70118-006-1-DD-B | 2 |  |  | DONE
|  |  | ROLLER SUPPORT | RT-88000-70118-007-1-DD-B | 1 |  |  | DONE
|  |  | ROLLER SHAFT | RT-88000-70118-046-1-DD-B | 1 |  |  | DONE
|  |  | PIVOT PIN | RT-88000-70118-009-1-DD-B | 2 |  |  | DONE
|  |  | PLUNGER | RT-88000-70118-022-1-DD-B | 1 |  |  | DONE
|  |  | SPACER | RT-88000-70118-045-1-DD-B | 1 |  |  | DONE
|  |  | SPACER | RT-88000-70118-013-1-DD-B | 2 |  |  | DONE
|  |  | THRUST WASHER | RT-88000-70118-043-1-DD-B | 1 |  |  | DONE
|  |  | SHIELD | RT-88000-70118-083-1-DD-D | 2 |  |  | DONE
71848 | RT98-87540-PN-R002 | Candu | SSDO Saddle | RT-88030-0080-01-GA-C | 4 | 2025-07-23 | 2025-08-25 | DONE
|  |  | HANDLE WELDMENT | RT-88030-0086-01-DD-D | 1 |  |  | DONE | DEBURR
|  |  | PIVOT FORK | RT-88030-0082-01-DD-B | 1 |  |  | DONE
|  |  | SUPPORT SADDLE | RT-88030-0084-01-DD-B | 1 |  |  | DONE
|  |  | PIVOT BASE | RT-88030-0085-01-DD-B | 1 |  |  | DONE
|  |  | BASE PLATE | RT-88030-0081-01-DD-B | 1 |  |  | DONE
|  |  | SPACER | RT-88030-0083-01-DD-B | 1 |  |  | DONE
|  |  | RETAINING WASHER | RT-88030-0087-01-DD-B | 2 |  |  | DONE
71849 | RT98-87540-PN-R002 | Candu | Removal Tool Trough | RT-88000-70103-016-1-GA-D | 3 | 2025-07-23 | 2025-08-25 | DONE
|  |  | TROUGH ASSEMBLY | RT-88000-70103-010-1-GA-D | 1 |  |  | DONE
|  |  | ANGLE WELDMENT | RT-88000-70103-008-1-DD-D | 1 |  |  | DONE
|  |  | ANGLE, CONNECTOR | RT-88000-70103-009-1-DD-C | 1 |  |  | DONE
|  |  | AXIAL ALIGNMENT BRACKET ASSEMBLY | RT-88000-70103-014-1-GA-C | 1 |  |  | DONE
|  |  | BAR | RT-88000-70103-011-1-DD-C | 1 |  |  | DONE
|  |  | BASE PLATE | RT-88000-70103-012-1-DD-C | 1 |  |  | DONE
|  |  | SLIDER BLOCK | RT-88000-70103-013-1-DD-C | 1 |  |  | DONE
71850 | RT79-87710-PN-R004-R1 | Candu | End Shield Measurement Tool Sys | RT-87713-0001-1-GA-D | 10 | 2025-09-19 | 2025-09-19 | INS,DIR |  | 2025-07-01: Clean,Identify; 2025-08-18: INS,DIR; 2025-08-19: INS,DIR; 2025-08-20: INS,DIR; 2025-08-21: INS,DIR; 2025-08-22: INS,DIR
|  |  | Unistrut with Post | RT-87713-70002-1-DD-B | 10 |  |  | DONE |  | 2025-06-18: DEBURR
|  |  | U-SHAPE SLIDER | RT-87713-70010-1-DD-B | 1 |  |  | DONE
|  |  | UNISTRUT MODIFIED | RT-87713-70003-1-DD-B | 10 |  |  | DONE
|  |  | ROD | RT-87713-70005-1-DD-B | 10 |  |  | DONE
|  |  | SPACER | RT-87713-70006-1-DD-B | 1 |  |  | DONE
|  |  | BRACKET | RT-87713-70009-1-DD-B | 1 |  |  | DONE
|  |  | BASE DETAIL DESIGN | RT-87713-70010-1-DD-B | 10 |  |  | DONE
71851 | RT79-87550-PN-R001 | Candu | Bellows Cutting Tool (SFCR) | RT-87550-0100-01-GA-E | 2 | 2025-09-19
|  |  | SHIM | RT-87550-0192-01-DD-C | 4 |  |  | DONE
|  |  | TOOL BIT LONG (NORMAL CUT) | RT-87550-0144-01-DD-C | 1 |  |  | DEBURR | DEBURR
|  |  | TOOL BIT LONG (DEFECT CUT ) | RT-87550-0191-01-DD-C | 1
|  |  | TOOL BIT SHORT (NORMAL CUT) | RT-87550-0187-01-DD-C | 1
|  |  | TOOL BIT SHORT (DEEP CUT) | RT-87550-0188-01-DD-C | 1 |  |  | DEBBUR |  | 2025-07-04: DEBBUR
|  |  | TOOL BIT LONG (DEEP CUT) | RT-87550-0189-01-DD-C | 1 |  |  | DEBURR |  | 2025-06-23: DEBURR
|  |  | TOOL BIT SHORT (DEFECT CUT ) | RT-87550-0190-01-DD-C | 1 |  |  | Mill |  | 2025-07-22: Mill
|  |  | DRIVE SHAFT AND PIVOT POINT ASSEMBLY | RT-87550-0102-01-GA-E | 1 |  | ★Need fix | INS
|  |  | BRACKET | RT-87550-0103-01-DD-D | 2 |  |  | EDM | Receive or Stock | 2025-07-31: Turn; 2025-08-01: Mill; 2025-08-04: Mill; 2025-08-05: Bore,Drill&Tap; 2025-08-06: Bore,Drill&Tap; 2025-08-07: Deburr; 2025-08-08: INS; 2025-08-11: INS; 2025-09-03: EDM Profile EDM; 2025-09-04: EDM Profile EDM; 2025-09-05: EDM Profile EDM; 2025-09-08: EDM Profile EDM; 2025-09-09: EDM Profile EDM; 2025-09-10: EDM Profile EDM; 2025-09-11: EDM Profile EDM; 2025-09-12: Receive,INS; 2025-09-13: INS,DIR; 2025-09-16: INS,DIR
|  |  | SADDLE | RT-87550-0104-01-DD-D | 1 |  |  | DONE
|  |  | RETAINING FLANGE | RT-87550-0106-01-DD-C | 1 |  |  | DONE | Receive,INS
|  |  | MODIFIED UNIVERSAL JOINT | RT-87550-0115-01-DD-C | 1 |  |  | DONE | Receive,INS | 2025-07-25: TURN
|  |  | PINION SHAFT ASSEMBLY | RT-87550-0112-01-GA-D | 1 |  |  | DONE | Receive,INS
|  |  | PINION SHAFT | RT-87550-0332-01-DD-D | 1 |  | ★外注あり | DONE |  | 2025-07-02: Heat treat A&M; 2025-07-03: Heat treat A&M; 2025-07-04: Heat treat A&M; 2025-07-07: Heat treat A&M; 2025-07-08: Heat treat A&M; 2025-07-09: Heat treat A&M; 2025-07-10: Heat treat A&M; 2025-07-11: Heat treat A&M; 2025-07-14: Heat treat A&M; 2025-07-15: Heat treat A&M; 2025-07-16: Heat treat A&M; 2025-07-17: Heat treat A&M; 2025-07-18: Heat treat A&M; 2025-07-21: Heat treat A&M; 2025-07-22: Heat treat A&M; 2025-07-23: Heat treat A&M; 2025-07-24: Heat treat A&M; 2025-07-25: Heat treat A&M; 2025-07-28: Heat treat A&M; 2025-07-29: Heat treat A&M; 2025-07-30: Heat treat A&M; 2025-07-31: Receive,INS; 2025-08-01: Turn; 2025-08-04: Turn; 2025-08-05: Drill; 2025-08-06: Drill; 2025-08-07: Grind; 2025-08-08: Grind; 2025-08-11: INS; 2025-08-12: INS; 2025-08-13: Gear Cut True Gear; 2025-08-14: Gear Cut True Gear; 2025-08-15: Gear Cut True Gear; 2025-08-18: Gear Cut True Gear; 2025-08-19: Gear Cut True Gear; 2025-08-20: Gear Cut True Gear; 2025-08-21: Gear Cut True Gear; 2025-08-22: Receive,INS; 2025-08-25: INS; 2025-08-26: INS
|  |  | PINION SHAFT END | RT-87550-0301-01-DD-C | 1 |  |  | DONE
|  |  | SLEEVE | RT-87550-0110-01-DD-C | 1 |  |  | DONE |  | 2025-06-18: DEBURR
|  |  | BUSHING | RT-87550-0109-01-DD-C | 1 |  |  | DONE
|  |  | DRIVE SHAFT EXTENSION | RT-87550-0108-01-DD-C | 1 |  |  | DONE
|  |  | SHEAR PIN | RT-87550-0111-01-DD-C | 2 |  |  | DONE |  | 2025-07-21: TURN
|  |  | MODIFIED MITER GEAR 1.000 P.D. X 14 TEETH X 20 P.A. X 14 D.P. | RT-87550-0105-01-DD-C | 1 |  |  | DONE
|  |  | SPINDLE | RT-87550-0107-01-DD-C | 1 |  |  | DONE |  | 2025-07-23: TURN
|  |  | GEAR WRENCH TUBE | RT-87550-0114-01-DD-C | 1 |  |  | DONE |  | 2025-07-04: DEBURR
|  |  | MODIFIED PALM-GRIP HAND KNOB | RT-87550-0116-01-DD-C | 1 |  |  | DONE
|  |  | GEAR WRENCH SHAFT | RT-87550-0113-01-DD-C | 1 |  |  | DONE
|  |  | E/F FLANGE ASSEMBLY | RT-87550-0120-01-GA-E | 1 |  |  | Sub-parts are on order
|  |  | FLANGE WELDMENT | RT-87550-0121-01-GA-E | 1 |  |  | Deburr | Receive,Inspect | 2025-08-15: Deburr; 2025-08-26: INS,DIR; 2025-08-27: INS,DIR
|  |  | YOKE | RT-87550-0130-01-DD-C | 1 |  |  | DONE
|  |  | SHIM | RT-87550-0122-01-DD-C | 1 |  |  | DONE
|  |  | PROTECTIVE SLEEVE RING | RT-87550-0129-01-DD-C | 1 |  |  | CUT |  | 2025-07-16: CUT
|  |  | FEED SCREW | 08-31912-0446-01-DD-3 (RT-87550-0123-01-DD-C) | 1 |  |  | Parts machining by an external supplier M&M |  | 2025-07-18: Parts machining by an external supplier M&M
|  |  | CLAMP | RT-87550-0124-01-DD-C | 3 |  |  | DONE
|  |  | MODIFIED HAND KNOB | RT-87550-0125-01-DD-C | 5 |  |  | DONE
|  |  | THREADED ROD .375-16 UNC-3A X 3.0" LG | RT-87550-0127-01-DD-C | 2
|  |  | THREADED ROD .375-16 UNC-3A X 2.13" LG | RT-87550-0128-01-DD-C | 3 |  |  | DONE |  | 2025-07-21: TURN
|  |  | WASHER | RT-87550-0126-01-DD-C | 3 |  |  | DONE
|  |  | FEED SCREW & DRIVE ASSEMBLY | RT-87550-0312-01-GA-E | 1
|  |  | BRACKET | 08-31912-0456-01-DD-1 | 1
|  |  | SCREW STOP | RT-87550-0138-01-DD-C | 1
|  |  | SCALE PLATE | RT-87550-0139-01-DD-C | 1
|  |  | EXTENSION TUBE WELDMENT | RT-87550-0313-01-GA-C | 1 |  |  | DEBURR |  | 2025-06-27: DEBURR
|  |  | BRACKET | RT-87550-0136-01-DD-D | 2 |  |  | Face,Chamfers,Mill |  | 2025-07-18: Face,Chamfers,Mill
|  |  | FORK | RT-87550-0140-01-DD-C | 1 |  |  | DONE
|  |  | AIR MOTOR & PIPE FITTINGS ASSEMBLY | RT-87550-0186-01-GA-E | 1 |  |  | ASSY | ASSY
|  |  | UTILITY TOOL WELDMENT | RT-87550-0171-01-GA-D | 1 |  |  | Gather all items
|  |  | UTILITY TUBE | RT-87550-0172-01-DD-C | 1 |  |  | DEBURR |  | 2025-07-04: DEBURR
|  |  | SLIDE HANDLE | RT-87550-0173-01-DD-C | 1 |  |  | DONE
|  |  | STOP COLLAR | RT-87550-0174-01-DD-C | 2 |  |  | DONE
|  |  | FOOT | RT-87550-0175-01-DD-C | 1 |  |  | DONE
|  |  | SHELL INSTALLATION TOOL ASSEMBLY | RT-87550-0145-01-GA-E | 1 |  |  | Recive,INS | Recive,INS
|  |  | SQUARE TUBE WELDMENT | RT-87550-0146-01-GA-C | 1 |  |  | Deburr |  | 2025-07-29: Weld; 2025-08-06: Deburr; 2025-08-07: INS,DIR; 2025-08-08: INS,DIR
|  |  | CONNECTOR ROD/HOOK WELDMENT | RT-87550-0147-01-GA-D | 1 |  |  | Deburr |  | 2025-07-28: Deburr
|  |  | HANDLE | RT-87550-0148-01-DD-C | 1 |  |  | DONE
|  |  | MODIFIED HAND KNOB | RT-87550-0149-01-DD-C | 1
|  |  | HAND CRANK ASSEMBLY | RT-87550-0165-01-GA-C | 1 |  |  | Receive,INS | Receive,INS
|  |  | CRANK BODY WELDMENTCRANK BODY WELDMENT | RT-87550-0166-01-GA-C | 1 |  |  | DONE
|  |  | ADAPTORADAPTER | RT-87550-0167-01-DD-C | 1 |  |  | DONE
|  |  | CARRIER SHELL ASSEMBLY | RT-87550-0101-01-GA-E | 1 |  |  | Recive,INS | Recive,INS
|  |  | CARRIER SHELL SEGMENT TOP | RT-87550-0330-01-DD-E | 1 |  |  | Order material |  | 2025-07-17: Order material
|  |  | CARRIER SHELL SEGMENT BOTTOM | RT-87550-0117-01-DD-E | 1 |  |  | Split |  | 2025-07-17: Order material; 2025-08-26: Split; 2025-08-27: Deburr; 2025-08-28: INS
|  |  | CLAMPING PLATE | RT-87550-0118-01-DD-C | 1 |  |  | DONE
|  |  | ADUSTABLE BEARING SEGMENT | RT-87550-0119-01-DD-D | 4 |  |  | DEBURR | DEBURR
|  |  | WASHER-MODIFIED | RT-87550-0331-01-DD-C | 4 |  |  | DEBURR | DEBURR
|  |  | DOUBLE ACTING LOCK PIN ASSEMBLY | RT-87550-0181-01-GA-D | 1 |  |  | Recive,INS | Recive,INS
|  |  | DETENT PIN WELDMENT | RT-87550-0182-01-GA-C | 1 |  |  | Gather All items
|  |  | MODIFIED DETENT PIN | RT-87550-0328-01-DD-C | 1 |  |  | Sub-parts are on order
|  |  | PIN (1/4" DIA) | RT-87550-0329-01-DD-C | 1 |  |  | Turn |  | 2025-07-23: Turn; 2025-08-01: Grind; 2025-08-04: Deburr; 2025-08-05: INS; 2025-08-06: INS
|  |  | SHELL WRENCH (.093” A. F.) ASSEMBLY | RT-87550-0155-01-GA-C | 1 |  |  | Recive,INS | Recive,INS
|  |  | T-HANDLE(.093" A.F.) WELDMENT | RT-87550-0156-01-GA-C | 1 |  |  | TURN |  | 2025-07-24: TURN
|  |  | MODIFIED (.093" A.F.)BALL KEY | RT-87550-0157-01-DD-C | 1
|  |  | BEARING WRENCH (3/16" A/F) ASSEMBLY | RT-87550-0160-01-GA-C | 1
|  |  | T-HANDLE( 3/16" A.F.) WELDMENT | RT-87550-0161-01-GA-C | 2 |  |  | Silver Solder |  | 2025-07-24: TURN; 2025-08-20: Silver Solder; 2025-08-26: Deburr; 2025-08-27: INS; 2025-08-28: INS; 2025-08-29: Drill; 2025-09-01: Drill; 2025-09-02: Drill; 2025-09-03: Drill; 2025-09-04: Deburr; 2025-09-05: INS,DIR; 2025-09-08: INS,DIR
|  |  | MODIFIED BALL KEY (3/16") | RT-87550-0162-01-DD-C | 1 |  |  | DONE
|  |  | CATCH TRAY WELDMENT (SMALL) | RT-87550-0183-01-GA-D | 1 |  |  | Weld |  | 2025-08-22: Weld; 2025-08-28: Deburr; 2025-08-29: Weigh; 2025-09-01: L-Etch; 2025-09-02: L-Etch; 2025-09-03: INS,DIR; 2025-09-04: INS,DIR
|  |  | CATCH TRAY (SMALL) | RT-87550-0184-01-DD-C | 2 |  |  | Deburr |  | 2025-08-20: Deburr; 2025-08-21: INS,DIR; 2025-08-22: INS,DIR
|  |  | TUBE (SMALL) | RT-87550-0185-01-DD-C | 2 |  |  | DONE |  | 2025-07-17: Form; 2025-08-18: INS,DIR
|  |  | CATCH TRAY WELDMENT (LARGE) | RT-87550-0193-01-GA-D | 1 |  |  | Weld |  | 2025-08-22: Weld; 2025-08-25: Weld; 2025-08-26: Weld; 2025-08-27: Weld; 2025-08-28: Deburr; 2025-08-29: Weigh; 2025-09-01: L-Etch; 2025-09-02: L-Etch; 2025-09-03: INS,DIR; 2025-09-04: INS,DIR
|  |  | CATCH TRAY (LARGE) | RT-87550-0194-01-DD-D | 2 |  |  | DONE |  | 2025-08-20: Deburr; 2025-08-21: INS,DIR; 2025-08-22: INS,DIR
|  |  | TUBE (LARGE) | RT-87550-0195-01-DD-D | 1 |  |  | DONE |  | 2025-07-17: Form; 2025-08-11: Deburr; 2025-08-12: INS,DIR; 2025-08-13: INS,DIR
|  |  | STEP MEASURING TOOL | RT-87550-0320-01-GA-E | 1
|  |  | INNER TUBE | RT-87550-0327-01-DD-C | 1 |  |  | DONE |  | 2025-07-21: INS
|  |  | SUPPORT TUBE | RT-87550-0326-01-DD-C | 1 |  |  | DONE
|  |  | GUIDE BLOCK | RT-87550-0325-01-DD-C | 1 |  |  | DONE
|  |  | CLAMP SCREW | RT-87550-0324-01-DD-C | 1 |  |  | DONE
|  |  | WASHER | RT-87550-0323-01-DD-C | 1 |  |  | DONE
|  |  | CONNECTOR | RT-87550-0322-01-DD-C | 1 |  |  | DONE
|  |  | HANDLE - MODIFIED | RT-87550-0321-01-DD-C | 1 |  |  | DONE
71852 | RT79-87900-PN-R003 | Candu | C6- Bore Gauge | RT-87900-0400-1-GA-E | 3 | 2025-08-15 | waiting for the candu answer |  | Sub-parts are on order | 2025-10-24: Assembly; 2025-10-27: Doc
|  |  | PEEK GUIDE CONE | RT-87900-0401-1-DD-E | 1 |  |  | DONE
|  |  | CUSTOM PROBE TIP | RT-87900-0420-1-DD-C | 9 |  |  | Turn |  | 2025-10-22: Turn; 2025-10-23: Mill
|  |  | SPACER RESTRAIN | RT-87900-0407-1-DD-D | 1 |  |  | DONE |  | 2025-07-07: Receive,INS
|  |  | SCREW, CROSS DRILLED, HEX HD, CAP, 1-3/4" LG | RT-87900-0418-1-DD-C | 6 |  |  | DONE
|  |  | SHIELD PLUG | RT-87900-0402-1-DD-D | 1 |  |  | DONE
|  |  | SPACER BAR | RT-87900-0411-1-DD-C | 3 |  |  | DONE |  | 2025-07-17: INS
|  |  | SCREW, CROSS DRILLED, HEX HD, CAP, 1-1/2" LG | RT-87900-0418-1-DD-C | 6 |  |  | DONE
|  |  | HANDLE - WELDMENT | RT-87900-0424-1-DD-C | 1 |  |  | DONE
|  |  | PULLER SLEEVE | RT-87900-0403-1-DD-C | 2 |  |  | DONE
|  |  | INDICATOR BRACKET WELDMENT | RT-87900-0436-1-DD-C | 1 |  |  | DONE
|  |  | BUSHING | RT-87900-0408-1-DD-C | 1 |  | ★Need to fix waiting for a new drawing from Candu | Master Chrome |  | 2025-08-19: Master Chrome; 2025-08-20: Master Chrome; 2025-08-21: Master Chrome; 2025-08-22: Master Chrome; 2025-08-25: Master Chrome; 2025-08-26: Master Chrome; 2025-08-27: Master Chrome
|  |  | HANDLE BAR WELDMENT | RT-87900-0425-1-DD-C | 1 |  |  | DONE
|  |  | SPLIT CLAMP | RT-87900-0406-1-DD-C | 1 |  |  | DONE
|  |  | WHEEL SUPPORT SUB-ASSEMBLY | RT-87900-0426-1-GA-C | 6 |  |  | DONE | Receive or Stock
|  |  | WHEEL BASE PLATE | RT-87900-0427-1-DD-C |  |  |  | DONE
|  |  | WHEEL BRACKET | RT-87900-0428-1-DD-C |  |  |  | DONE
|  |  | WHEEL | RT-87900-0429-1-DD-C |  |  |  | DONE
|  |  | WHEEL BACKING PLATE | RT-87900-0430-1-DD-C |  |  |  | DONE
|  |  | MAGNET HOLDER SUB-ASSEMBLY | RT-87900-0432-1-GA-C | 2 |  |  | DONE | Receive or Stock
|  |  | Collar | RT-87900-0433-1-DD-C | 1 |  |  | DONE
|  |  | MKII BORE GAUGE SUB-ASSEMBLY | RT-87900-0443-1-GA-D | 1 |  |  | DONE
|  |  | MKII BORE GAUGE (VENDOR SUPPLIED) | RT-87900-0449-1-GA-D | 1 |  |  | DONE
|  |  | DIGIMATIC INDICATOR PROTECTIVE COVER ASSEMBLY | RT-87900-0447-1-GA-C | 3 |  |  | DONE | Receive or Stock
|  |  | DIGIMATIC INDICATOR PROTECTIVE COVER BASE | RT-87900-0452-1-DD-C | 1 |  |  | DONE
|  |  | DIGIMATIC INDICATOR PROTECTIVE COVER CLAMP | RT-87900-0453-1-DD-B | 1 |  |  | DONE
|  |  | POSITION GAUGE SUB-ASSEMBLY | RT-87900-0451-1-GA-D | 3 |  |  | DONE | Receive or Stock
|  |  | POSITION GAUGE | RT-87900-0409-1-DD-C | 1 |  |  | DONE |  | 2025-07-04: Fit,Tack,Weld
|  |  | FLASH PIN INDICATOR | RT-87900-0450-1-DD-C | 1 |  |  | DONE
71853 | RT79-87900-PN-R003 | Candu | C6 Bore Gauge- Narrow Landing | RT-87900-0500-01-GA-E | 2 | 2025-08-15 | waiting for the candu answer | ASSY | Sub-parts are on order | 2025-10-24: Assembly; 2025-10-27: Doc
|  |  | PEEK GUIDE CONE (NARROW) | RT-87900-0501-01-DD-E | 1 |  |  | DONE |  | 2025-07-18: DEBURR
|  |  | CUSTOM PROBE TIP | RT-87900-0420-1-DD-C | 6 |  |  | Turn |  | 2025-10-22: Turn; 2025-10-23: Mill
|  |  | SPACER RESTRAIN | RT-87900-0407-1-DD-D | 1 |  |  | DONE
|  |  | SCREW, CROSS DRILLED, HEX HD, CAP, 1-3/4" LG | RT-87900-0418-1-DD-C | 6 |  |  | DONE
|  |  | SHIELD PLUG | RT-87900-0402-1-DD-D | 1 |  |  | DONE
|  |  | SPACER BAR | RT-87900-0411-1-DD-C | 3 |  |  | DONE |  | 2025-07-17: INS
|  |  | SCREW, CROSS DRILLED, HEX HD, CAP, 1-1/2" LG | RT-87900-0418-1-DD-C | 6 |  |  | DONE
|  |  | HANDLE - WELDMENT | RT-87900-0424-1-DD-C | 1 |  |  | DONE
|  |  | PULLER SLEEVE | RT-87900-0403-1-DD-C | 2 |  |  | DONE
|  |  | INDICATOR BRACKET WELDMENT | RT-87900-0436-1-DD-C | 1 |  |  | DONE
|  |  | BUSHING | RT-87900-0408-1-DD-C | 1 |  |  | DONE
|  |  | PIPE SHAFT WELDMENT | RT-87900-0404-1-DD-D | 1 |  |  | DONE |  | 2025-07-24: INS
|  |  | HANDLE BAR WELDMENT | RT-87900-0425-1-DD-C | 1 |  |  | DONE
|  |  | SPLIT CLAMP | RT-87900-0406-1-DD-C | 1 |  |  | DONE
|  |  | WHEEL SUPPORT SUB-ASSEMBLY | RT-87900-0426-1-GA-C | 4 |  |  | DONE | Receive or Stock
|  |  | WHEEL BASE PLATE | RT-87900-0427-1-DD-C | 1 |  |  | DONE
|  |  | WHEEL BRACKET | RT-87900-0428-1-DD-C | 2 |  |  | DONE
|  |  | WHEEL | RT-87900-0429-1-DD-C | 2 |  |  | DONE
|  |  | WHEEL BACKING PLATE | RT-87900-0430-1-DD-C | 2 |  |  | DONE
|  |  | MAGNET HOLDER SUB-ASSEMBLY | RT-87900-0432-1-GA-C | 2 |  |  | DONE
|  |  | Collar | RT-87900-0433-1-DD-C | 1 |  |  | DONE
|  |  | MKII BORE GAUGE SUB-ASSEMBLY | RT-87900-0443-1-GA-D | 1 |  |  | DONE
|  |  | MKII BORE GAUGE (VENDOR SUPPLIED) | RT-87900-0449-1-GA-D | 1 |  |  | DONE
|  |  | DIGIMATIC INDICATOR PROTECTIVE COVER ASSEMBLY | RT-87900-0447-1-GA-C | 3 |  |  | DONE
|  |  | DIGIMATIC INDICATOR PROTECTIVE COVER BASE | RT-87900-0452-1-DD-C | 1 |  |  | DONE
|  |  | DIGIMATIC INDICATOR PROTECTIVE COVER CLAMP | RT-87900-0453-1-DD-B | 1 |  |  | DONE
|  |  | POSITION GAUGE SUB-ASSEMBLY | RT-87900-0451-1-GA-D | 3 |  |  | DONE
|  |  | POSITION GAUGE | RT-87900-0409-1-DD-C | 1 |  |  | DONE
|  |  | FLASH PIN INDICATOR | RT-87900-0450-1-DD-C | 1 |  |  | DONE
71859 | RT98-87920-PN-R007 | Candu | CTI Delivery Tool | RT-87920-74282-000-1-GA-E | 3 | 2025-07-11 | Awating Candu Release | DONE
|  |  | MAIN SHAFT | RT-87920-74282-001-1-DD-D | 1 |  |  | DONE
|  |  | HANDLE ADAPTER | RT-87920-74282-005-1-DD-B | 1 |  |  | DONE
|  |  | SHIELD 1 | RT-87920-74282-006-1-DD-D | 1 |  |  | DONE
|  |  | CENTER SHAFT | RT-87920-74282-007-1-DD-D | 1 |  |  | DONE
|  |  | ALIGNER | RT-87920-74282-010-1-DD-C | 2 |  |  | DONE
|  |  | END LOCATOR | RT-87920-74282-012-1-DD-B | 1 |  |  | DONE
|  |  | BUNG | RT-87920-74282-013-1-DD-B | 1 |  |  | DONE
|  |  | BUNG LOCKING NUT | RT-87920-74282-014-1-DD-B | 1 |  |  | DONE
|  |  | INNER SHIELD PLUG | RT-87920-74282-015-1-DD-B | 1 |  |  | DONE
|  |  | SHIELD 2 | RT-87920-74282-016-1-DD-D | 1 |  |  | DONE
|  |  | PLATE | RT-87920-7423-01-DD-C | 1 |  |  | DONE
|  |  | DIAL INDICATOR COVER | RT-87920-7424-01-DD-C | 2 |  |  | DONE
|  |  | JOINT ROD | RT-87920-7422-01-DD-C | 2 |  |  | DONE
|  |  | SHOULDER SCREW | RT-87920-7421-01-DD-C | 2 |  |  | DONE
71860 | RT98-87540-PN-R002 | Candu | Positioning Stud Rotation tool | RT-87540-0169-1-DD-2 | 3 | 2025-07-11 | Awating Candu release | DONE
71861 | RT98-87540-PN-R002 | Candu | Spacer Clip Installation Tool | RT-87540-0123-1-GA-1 | 3 | 2025-07-11 | Awating Candu release | DONE
|  |  | HANDLE WELDMENT | RT-87540-0124-01-DD-2 |  |  |  | DONE
|  |  | MODIFIED DETENT PIN | RT-87540-0125-01-DD-2 |  |  |  | DONE
|  |  | ADAPTOR | RT-87540-0126-01-DD-2 |  |  |  | DONE
|  |  | MODIFIED MAGNET, RIN | RT-87540-0143-01-DD-3 |  |  |  | DONE
71862 | RT98-87540-PN-R002 | Candu | Temporary Yoke Pin | RT-87540-0120-1-GA-2 | 3 | 2025-07-11 | Awating Candu release | DONE
|  |  | PIN | RT-87540-0121-01-DD-2 | 1 |  |  | DONE
|  |  | HANDLE | RT-87540-0122-01-DD-2 | 1 |  |  | DONE
|  |  | PIN, SLOTTED SPRING, .125 DIA X .625 LG | AISI 420/ # 240-008 | 1 |  |  | DONE
|  |  | PIN, SLOTTED SPRING, .125 DIA X 1.00 LG | AISI 420/ # TP-2002 | 1 |  |  | DONE
|  |  | TAG, BLANK METAL ENGRAVING, DIA 2" | PART No 1540T52 / 304 SS | 1 |  |  | DONE
|  |  | AIR CRAFT WIRE 1/16 DIA X 1 X 7 STRAND | PART No 3461T11 / 304 SS | 1 |  |  | DONE
|  |  | SWAGE SLEEVE, OVAL | PART No 3633T2 | 1 |  |  | DONE
71863 | RT98-87540-PN-R002 | Candu | Spring Pin Installation Spacer | RT-87540-0205-1-DD-2 | 3 | 2025-07-11 | Awating Candu release | DONE
71864 | RT98-87540-PN-R002 | Candu | Threaded Hole Insp. Tool ( Short) | RT-87540-0144-1-GA-2 | 7 | 2025-07-11 | Awating Candu release | DONE
|  |  | COUPLING, TOOL HOLDER | RT-87540-0146-01-DD-2 | 1 |  |  | DONE
|  |  | HANDLE ASSEMBLY (Short) | RT-87540-0145-01-GA-1 | 1 |  |  | DONE
|  |  | MODIFIED THREADED PLUG GAUGE SET 1.25-8 UN-2B | RT-87540-0147-01-GA-2 | 1 |  |  | DONE
71865 | RT98-87540-PN-R002 | Candu | Threaded Hole Repairing tool ( Short) | RT-87540-0186-1-GA-2 | 7 | 2025-07-11 | Awating Candu release | DONE
|  |  | HANDLE WELDMENT (Short) | RT-87540-0180-01-DD-2 | 1 |  |  | DONE
|  |  | BOTTOMING TAP 1 1/4-8 NS RH THREAD | H.S.S/ #2597A72 | 1 |  |  | DONE
|  |  | SCREW SOC HD SET CUP POINT 1/4-20 UNC-2A X 3/8" LG | S.S. 18-8/ #92311A535 | 2 |  |  | DONE
71866 | RT98-87540-PN-R002 | Candu | Spring Pin Insetion Tool | RT-87540-0137-1-GA-2 | 7 | 2025-07-11 | Awating Candu release | DONE
|  |  | SHAFT WELDMENT | RT-87540-0113-01-DD-2 | 1 |  |  | DONE
|  |  | SUPPORT BRACKET | RT-87540-0114-01-DD-2 | 1 |  |  | DONE
|  |  | SPRING PIN HOLDER | RT-87540-0140-01-DD-2 | 1 |  |  | DONE
|  |  | NUT JAM HEX 1/4-20UNC-2B, GRADE 5 | STEEL / #HN-49 | 1 |  |  | DONE
|  |  | SCREW CAP HEX HD. 1/4-20UNC-2A X 1.25 LG. | ASTM A307/ #B-46 | 1 |  |  | DONE
|  |  | PIN SLOTTED SPRING TENSION .0625 DIA X .375 LG. | CARBON STL./ #TP-48 | 1 |  |  | DONE
|  |  | O-RING, .239 I.D. x .07 WIDE, AS568A-010 | BUNA-N / #9555K11 | 1 |  |  | DONE
71867 | RT98-87540-PN-R002 | Candu | Spring Pin Holder | RT-87540-0140-1-DD-2 | 14 | 2025-07-11 | Awating Candu release | DONE
71868 | RT98-87540-PN-R002 | Candu | PA Spacer Clip Inst. Tool- Detent Pin Mod | RT-87540-0125-1-DD-2 | 14 | 2025-07-11 | Awating Candu release | DONE
71869 | RT98-87540-PN-R002 | Candu | Lattice Sleeve Rem. Tool HWT Mounted | RT-87600-0250-1-GA-E | 1 | 2025-07-11 | Awating Candu release | DONE
|  |  | BASE WELDMENT | RT-87600-0251-1-DD-E | 1 |  |  | DONE
|  |  | FLANGE BEAM WELDMENT | RT-87600-0252-1-DD-E | 1 |  |  | DONE
|  |  | SLEEVE BRACKET WELDMENT | RT-87600-0253-1-DD-D | 1 |  |  | DONE
|  |  | CYLINDER PUSH BRACKET WELDMENT | RT-87600-0254-1-DD-D | 1 |  |  | DONE
|  |  | CYLINDER MOUNTING BRACKET WELDMENT (RH) | RT-87600-0255-1-DD-D | 1 |  |  | DONE
|  |  | GUARD WELDMENT | RT-87600-0256-1-DD-D | 1 |  |  | DONE
|  |  | PIPE WELDMENT | RT-87600-0257-1-DD-C | 2 |  |  | DONE
|  |  | RING | RT-87600-0258-1-DD-C | 1 |  |  | DONE
|  |  | SPACER BLOCK | RT-87600-0259-1-DD-C | 2 |  |  | DONE
|  |  | STOP PLATE | RT-87600-0260-1-DD-C | 1 |  |  | DONE
|  |  | STOP PLATE 2 | RT-87600-0261-1-DD-C | 1 |  |  | DONE
|  |  | PUMP MOUNTING BRACKET | RT-87600-0262-1-DD-C | 1 |  |  | DONE
|  |  | SPACER PLATE | RT-87600-0263-1-DD-C | 1 |  |  | DONE
|  |  | CYLINDER NOSE | RT-87600-0264-1-DD-C | 1 |  |  | DONE
|  |  | TOOL STORAGE BRACKET | RT-87600-0265-1-DD-C | 2 |  |  | DONE
71870 | RT98-87540-PN-R002 | Candu | Yoke Pin Replacement Tool | RT-87540-0166-01-GA-E | 4 | 2025-07-11 | Awating Candu release | DONE
|  |  | END CONNECTOR FITTING | RT-87540-0138-01-DD-B | 1 |  |  | DONE
|  |  | SLIDE HAMMER | RT-87540-0139-01-DD-D | 1 |  |  | DONE
|  |  | SHAFT WELDMENT | RT-87540-0153-01-GA-C | 1 |  |  | DONE
|  |  | SHAFT | RT-87540-0130-01-DD-B | 1 |  |  | DONE
|  |  | ROUND STOPPER | RT-87540-0152-01-DD-B | 1 |  |  | DONE
|  |  | HANDLE | RT-87540-0141-01-DD-B | 1 |  |  | DONE
|  |  | YOKE PIN TOOL WELDMENT | RT-87540-0156-01-GA-C | 1 |  |  | DONE
|  |  | TUBING WELDMENT | RT-87540-0129-01-DD-C | 1 |  |  | DONE
|  |  | CONNECTOR | RT-87540-0155-01-DD-B | 1 |  |  | DONE
|  |  | ROUND PLATE | RT-87540-0154-01-DD-B | 2 |  |  | DONE
71873 | RT79-87550-PN-R001 | Candu | To Capture cost for Spare parts | Spare parts | Lot | 2025-09-19 |  | HT
71879 | RT98-88010-PN-R001 | Candu | Helium Leak Test Tool | RT-88000-70066-000-1-GA-D | 1 | 2025-07-16 | Awating Candu release | DONE
|  |  | SEAL RING (31910-814-1) | 12918-0066-0001 (RT-88000-70066-001-1-DD-B) |  |  |  | DONE
|  |  | SPACER (31910-823-1) | 12918-0066-0002 (RT-88000-70066-002-1-DD-D) |  |  |  | DONE
|  |  | SPACER (31910-819-1) | 12918-0066-0021(RT-88000-70066-021-1-DD-B) | 1 |  |  | DONE
|  |  | TUBE (31910-823-1) | 12918-0066-0022 (RT-88000-70066-022-1-DD-B) | 1 |  |  | DONE
|  |  | INNER TUBE ASSY | 12918-6610-0000 (RT-88000-76610-000-1-GA-D) |  |  |  | DONE
|  |  | GUIDE RING (31910-811-1) | 12918-6610-0001 (RT-88000-76610-001-1-DD-B) | 1 |  |  | DONE
|  |  | PLATE PT.1 (31910-809-1) | 12918-6610-0002 (RT-88000-76610-002-1-DD-B) | 1 |  |  | DONE
|  |  | INNER PIPE (31910-808-1) | 12918-6610-0003 (RT-88000-76610-003-1-DD-B) | 1 |  |  | DONE
|  |  | SHAFT END (31910-816-1) | 12918-6610-0004 (RT-88000-76610-004-1-DD-B) | 1 |  |  | DONE
|  |  | PIPE & PLATES | 12918-6610-0007 (RT-88000-76610-007-1-DD-D) | 1 |  |  | DONE
|  |  | PLATE PT.1 (31910-809-1) | 12918-6610-0002 (RT-88000-76610-002-1-DD-B) | 1 |  |  | DONE
|  |  | INNER PIPE (31910-808-1) | 12918-6610-0003 (RT-88000-76610-003-1-DD-B) | 1 |  |  | DONE
|  |  | OUTER TUBE ASSY | 12918-6620-0000 (RT-88000-76620-000-1-GA-D) |  |  |  | DONE
|  |  | PLATE PT.2 (31910-809-1) | 12918-6620-0001 (RT-88000-76620-001-1-DD-B) | 1 |  |  | DONE
|  |  | GUIDE RING (31910-811-1) | 12918-6620-0002 (RT-88000-76620-002-1-DD-B) | 1 |  |  | DONE
|  |  | GUIDE RING (31910-848-1) | 12918-6620-0003 (RT-88000-76620-003-1-DD-B) | 1 |  |  | DONE
|  |  | PLATE (31910-815-1) | 12918-6620-0004 (RT-88000-76620-004-1-DD-B) | 1 |  |  | DONE
|  |  | OUTER PIPE (31910-817-1) | 12918-6620-0005 (RT-88000-76620-005-1-DD-B) | 1 |  |  | DONE
|  |  | OUTER HOUSING END (31910-812-1) | 12918-6620-0006 (RT-88000-76620-006-1-DD-B) | 1 |  |  | DONE
|  |  | PIPE & PLATES | 12918-6620-0009 (RT-88000-76620-009-1-DD-D/RT-88000-76620-009-2-DD-D) | 1 |  |  | DONE
|  |  | TYGON TUBE (31910-807-1) | 12918-0066-0008 (RT-88000-70066-008-1-DD-B) |  |  |  | DONE
|  |  | CENTERING DISC (31910-854-1) | 12918-0066-0010 (RT-88000-70066-010-1-DD-B) |  |  |  | DONE
|  |  | TUBE (31910-807-1) | 12918-0066-0011 (RT-88000-70066-011-1-DD-B) |  |  |  | DONE
|  |  | SPACER (31910-819-1) | 12918-0066-0021 (RT-88000-70066-021-1-DD-B) |  |  |  | DONE
|  |  | TUBE (31910-823-1) | 12918-0066-0022 (RT-88000-70066-022-1-DD-B) |  |  |  | DONE
71880 | RT98-88010-PN-R001 | Candu | Liner Tube Protective Sleeve | RT-88000-70146-000-1-GA-E | 7 | 2025-07-16 | Awating Candu release | DONE
|  |  | Protective Sleeve (31910-52-1) | RT-88000-70146-002-1-DD-D | 1 |  |  | DONE
71881 | RT98-88010-PN-R001 | Candu | Helium Spray Tool | RT-88000-70069-000-1-GA-D | 2 | 2025-07-16 | Awating Candu release | DONE
|  |  | TUBING (31910-672-1) | 12918-0069-0004(RT-88000-70069-004-1-DD-B) | 1 |  |  | DONE
|  |  | RING (31910-672-1) | 12918-0069-0001 (RT-88000-70069-001-1-DD-B) | 1 |  |  | DONE
|  |  | SPIGOT (31910-672-1) | 12918-0069-0002 (RT-88000-70069-002-1-DD-B/RT-88000-70069-002-2-DD-B) | 1 |  |  | DONE
|  |  | SPIGOT (31910-672-1) | 12918-0069-0002 (RT-88000-70069-002-1-DD-B/RT-88000-70069-002-2-DD-B) | 1 |  |  | DONE
|  |  | TUBING (31910-672-1) ★only RT-88000-70069-002-1-DD-B | 12918-0069-0004 (RT-88000-70069-004-1-DD-B) | 1 |  |  | DONE
71882 | RT98-88010-PN-R001 | Candu | E/F Protective Sleeve | RT-88000-70038-000-1-GA-D | 17 | 2025-07-16 | Awating Candu release | DONE
|  |  | SLEEVE TUBE (98-31910-21-1) | 12918-0038-0001 (RT-88000-70038-001-1-DD-B) | 1 |  |  | DONE
|  |  | SLEEVE GUIDE (98-31910-21-1) | 12918-0038-0002 (RT-88000-70038-002-1-DD-B) | 1 |  |  | DONE
|  |  | SLEEVE GUIDE (98-31910-21-1) | 12918-0038-0003 (RT-88000-70038-003-1-DD-B) | 1 |  |  | DONE
|  |  | SPRING (98-31910-21-1) | 12918-0038-0100 (RT-88000-70038-100-1-DD-B) | 1 |  |  | DONE
|  |  | BLOCK (98-31910-21-1) | 12918-0038-0101 (RT-88000-70038-101-1-DD-B) | 1 |  |  | DONE
|  |  | RETAINING LATCH (98-31910-21-1) | 12918-0038-0004 (RT-88000-70038-004-1-DD-B) | 1 |  |  | DONE
|  |  | SPRING (98-31910-21-1) | 12918-0038-0100 (RT-88000-70038-100-1-DD-B) | 1 |  |  | DONE
|  |  | BLOCK (98-31910-21-1) | 12918-0038-0101 (RT-88000-70038-101-1-DD-B) | 1 |  |  | DONE
71883 | RT98-88010-PN-R001 | Candu | Spring Loaded Centre Punch | 80-01-00001-PRT- (Purchase) | 4 | 2025-07-16 | Awating Candu release | DONE
71884 | RT98-88010-PN-R001 | Candu | Vacuum Hose for Helium Leak Test | RT-88000-70068-000-1-GA-D | 2 | 2025-07-16 | Awating Candu release | DONE
|  |  | VACUUM LINE ADAPTER (31910-47-1) | 12918-0068-0005 (RT-88000-70068-005-1-DD-B) |  |  |  | DONE
|  |  | ELBOW (31910-47-1) | 12918-0068-0007 (RT-88000-70068-007-1-DD-B) |  |  |  | DONE
71885 | RT98-88010-PN-R001 | Candu | Air Motor Socket | RT-0055-000-PRT ( Purchase) | 5 | 2025-07-16 | Awating Candu release | DONE
71886 | RT98-88010-PN-R001 | Candu | Calibrated Measuring Tape | RT-88010-0005-01-GA-E | 2 | 2025-08-08 | Awating Candu release | DONE |  | 2025-07-28: Setup; 2025-07-29: Setup; 2025-07-30: Laser-Etching; 2025-07-31: Laser-Etching; 2025-08-01: Clean; 2025-08-04: INS,DIR; 2025-08-05: INS,DIR; 2025-08-06: Pack; 2025-08-07: Pack
|  |  | CALIBRATED TAPE HOLDER | RT-88010-0008-01-DD-C |  |  |  | DONE
|  |  | PLATE | RT-88010-0006-01-DD-C |  |  |  | DONE
|  |  | PULLEY SHAFT | RT-88010-0007-01-DD-C |  |  |  | DONE
|  |  | PULLEY BRACKET | RT-88010-0013-01-GA-C |  |  |  | DONE
|  |  | PULLEY BRACKET | RT-88010-0014-01-GA-C |  |  |  | DONE
|  |  | PULLEY BRACKET | RT-88010-0015-01-GA-C |  |  |  | DONE
|  |  | PULLEY BRACKET | RT-88010-0016-01-GA-C |  |  |  | DONE
71888 | RT98-88010-PN-R001 | Candu | Seal Face Protective Sleeve | RT-88000-70047-000-1-GA-D | 6 | 2025-07-16 | Awating Candu release | DONE
|  |  | SLEEVE TUBE | RT-88000-70047-001-1-DD-B | 1 |  |  | DONE
|  |  | SLEEVE GUIDE 1 | RT-88000-70047-002-1-DD-B | 1 |  |  | DONE
|  |  | SLEEVE GUIDE 2 | RT-88000-70047-003-1-DD-B | 1 |  |  | DONE
|  |  | RETAINING LATCH | RT-88000-70047-004-1-DD-B | 1 |  |  | DONE
71999 | RT79-87540-PN-R001-R.1 | Candu | Yoke Pin Replacement Tool | - | 4 | 2025-09-19 | Awating Candu release | DONE
72023 | RT98-87550-PN-R004 | Candu | Bellows Cutting Tool (SFCR) | RT-87550-0100-01-GA-E | 2 | 2025-09-19 |  | Sub-parts are on order
|  |  | Drive Shelf and Pivot Point ASSY | RT-87550-0102-01-GA-E | 1 |  |  | Receive,INS | Receive,INS
|  |  | BRACKET | RT-87550-0103-01-DD-D | 2 |  |  | EDM | Receive or Stock | 2025-07-31: Turn; 2025-08-01: Mill; 2025-08-04: Mill; 2025-08-05: Bore,Drill&Tap; 2025-08-06: Bore,Drill&Tap; 2025-08-07: Deburr; 2025-08-08: INS; 2025-08-11: INS; 2025-09-03: EDM Profile EDM; 2025-09-04: EDM Profile EDM; 2025-09-05: EDM Profile EDM; 2025-09-08: EDM Profile EDM; 2025-09-09: EDM Profile EDM; 2025-09-10: EDM Profile EDM; 2025-09-11: EDM Profile EDM; 2025-09-12: Receive,INS; 2025-09-13: INS,DIR; 2025-09-16: INS,DIR
|  |  | SADDLE | RT-87550-0104-01-DD-D | 1 |  |  | DONE
|  |  | RETAINING FLANGE | RT-87550-0106-01-DD-C | 1
|  |  | MODIFIED UNIVERSAL JOINT | RT-87550-0115-01-DD-C | 1 |  |  | TURN |  | 2025-07-25: TURN
|  |  | PINION SHAFT ASSEMBLY | RT-87550-0112-01-GA-D | 1 |  |  | Receive,INS
|  |  | PINION SHAFT | RT-87550-0332-01-DD-D | 1 |  | ★外注あり | Heat treat A&M |  | 2025-07-02: Heat treat A&M; 2025-07-03: Heat treat A&M; 2025-07-04: Heat treat A&M; 2025-07-07: Heat treat A&M; 2025-07-08: Heat treat A&M; 2025-07-09: Heat treat A&M; 2025-07-10: Heat treat A&M; 2025-07-11: Heat treat A&M; 2025-07-14: Heat treat A&M; 2025-07-15: Heat treat A&M; 2025-07-16: Heat treat A&M; 2025-07-17: Heat treat A&M; 2025-07-18: Heat treat A&M; 2025-07-21: Heat treat A&M; 2025-07-22: Heat treat A&M; 2025-07-23: Heat treat A&M; 2025-07-24: Heat treat A&M; 2025-07-25: Heat treat A&M; 2025-07-28: Heat treat A&M; 2025-07-29: Heat treat A&M; 2025-07-30: Heat treat A&M; 2025-07-31: Receive,INS; 2025-08-01: Turn; 2025-08-04: Turn; 2025-08-05: Drill; 2025-08-06: Drill; 2025-08-07: Grind; 2025-08-08: Grind; 2025-08-11: INS; 2025-08-12: INS; 2025-08-13: Gear Cut True Gear; 2025-08-14: Gear Cut True Gear; 2025-08-15: Gear Cut True Gear; 2025-08-18: Gear Cut True Gear; 2025-08-19: Gear Cut True Gear; 2025-08-20: Gear Cut True Gear; 2025-08-21: Gear Cut True Gear; 2025-08-22: Receive,INS; 2025-08-25: INS; 2025-08-26: INS
|  |  | PINION SHAFT END | RT-87550-0301-01-DD-C | 1
|  |  | SLEEVE | RT-87550-0110-01-DD-C | 1 |  |  | ★Need to fix
|  |  | BUSHING | RT-87550-0109-01-DD-C | 1 |  |  | DONE
|  |  | DRIVE SHAFT EXTENSION | RT-87550-0108-01-DD-C | 1
|  |  | SHEAR PIN | RT-87550-0111-01-DD-C | 2 |  |  | TURN |  | 2025-07-21: TURN
|  |  | MODIFIED MITER GEAR 1.000 P.D. X 14 TEETH X 20 P.A. X 14 D.P. | RT-87550-0105-01-DD-C | 1 |  |  | DONE
|  |  | SPINDLE | RT-87550-0107-01-DD-C | 1
|  |  | GEAR WRENCH TUBE | RT-87550-0114-01-DD-C | 1
|  |  | MODIFIED PALM-GRIP HAND KNOB | RT-87550-0116-01-DD-C | 1 |  |  | DONE
|  |  | GEAR WRENCH SHAFT | RT-87550-0113-01-DD-C | 1
|  |  | Flange ASSY | RT-87550-0120-01-GA-E | 1 |  |  | Sub parts order
|  |  | FLANGE WELDMENT | RT-87550-0121-01-GA-E | 1 |  |  | Deburr |  | 2025-08-15: Deburr; 2025-08-26: INS,DIR; 2025-08-27: INS,DIR
|  |  | YOKE | RT-87550-0130-01-DD-C | 1 |  |  | DONE
|  |  | SHIM | RT-87550-0122-01-DD-C | 1 |  |  | DONE
|  |  | PROTECTIVE SLEEVE RING | RT-87550-0129-01-DD-C | 1
|  |  | FEED SCREW | 08-31912-0446-01-DD-3 | 1
|  |  | CLAMP | RT-87550-0124-01-DD-C | 3
|  |  | MODIFIED HAND KNOB | RT-87550-0125-01-DD-C | 5
|  |  | THREADED ROD .375-16 UNC-3A X 3.0" LG | RT-87550-0127-01-DD-C | 2
|  |  | THREADED ROD .375-16 UNC-3A X 2.13" LG | RT-87550-0128-01-DD-C | 3
|  |  | WASHER | RT-87550-0126-01-DD-C | 3 |  |  | DONE
|  |  | Feed Screw & Drive ASSY | RT-87550-0312-01-GA-E | 1 |  |  | Receive,INS | Receive,INS
|  |  | BRACKET | 08-31912-0456-01-DD-1 | 1
|  |  | SCREW STOP | RT-87550-0138-01-DD-C | 1 |  |  | DONE
|  |  | SCALE PLATE | RT-87550-0139-01-DD-C | 1
|  |  | EXTENSION TUBE WELDMENT | RT-87550-0313-01-GA-C | 1
|  |  | FORK | RT-87550-0140-01-DD-C | 1 |  |  | DONE
|  |  | SHIM | RT-87550-0192-01-DD-C | 4 |  |  | DONE
|  |  | AIR MOTOR & PIPE FITTINGS ASSEMBLY | RT-87550-0186-01-GA-E | 1 |  |  | ASSY
|  |  | UTILITY TOOL WELDMENT | RT-87550-0171-01-GA-D | 1 |  |  | Gather all items
|  |  | UTILITY TUBE | RT-87550-0172-01-DD-C | 1
|  |  | SLIDE HANDLE | RT-87550-0173-01-DD-C | 1
|  |  | STOP COLLAR | RT-87550-0174-01-DD-C | 2 |  |  | DONE
|  |  | FOOT | RT-87550-0175-01-DD-C | 1 |  |  | DONE
|  |  | SHELL INSTALLATION TOOL ASSEMBLY | RT-87550-0145-01-GA-E | 1 |  |  | Receive,INS
|  |  | SQUARE TUBE WELDMENT | RT-87550-0146-01-GA-C | 1 |  |  | Deburr |  | 2025-08-06: Deburr; 2025-08-07: INS,DIR; 2025-08-08: INS,DIR
|  |  | CONNECTOR ROD/HOOK WELDMENT | RT-87550-0147-01-GA-D | 1 |  |  | Deburr |  | 2025-06-27: Deburr
|  |  | HANDLE | RT-87550-0148-01-DD-C | 1 |  |  | DONE
|  |  | MODIFIED HAND KNOB | RT-87550-0149-01-DD-C | 1 |  |  | DONE
|  |  | HAND CRANK ASSEMBLY | RT-87550-0165-01-GA-C | 1 |  |  | Receive,INS | Receive,INS
|  |  | CRANK BODY WELDMENTCRANK BODY WELDMENT | RT-87550-0166-01-GA-C | 1 |  |  | DONE
|  |  | ADAPTORADAPTER | RT-87550-0167-01-DD-C | 1 |  |  | DONE
|  |  | CARRIER SHELL ASSEMBLY | RT-87550-0101-01-GA-E | 1 |  |  | Receive,INS
|  |  | CARRIER SHELL SEGMENT TOP | RT-87550-0330-01-DD-E | 1
|  |  | CARRIER SHELL SEGMENT BOTTOM | RT-87550-0117-01-DD-E | 1 |  |  | Split |  | 2025-08-26: Split; 2025-08-27: Deburr; 2025-08-28: INS; 2025-08-29: ASSY; 2025-09-01: ASSY; 2025-09-02: Drill; 2025-09-03: Drill; 2025-09-04: Turn; 2025-09-05: Turn; 2025-09-08: Mill; 2025-09-09: Mill; 2025-09-10: Deburr; 2025-09-11: INS; 2025-09-12: INS; 2025-09-13: Gear Cut; 2025-09-16: Gear Cut; 2025-09-17: Gear Cut; 2025-09-18: Gear Cut; 2025-09-19: Gear Cut; 2025-09-22: Gear Cut; 2025-09-23: Gear Cut; 2025-09-24: Receive,INS; 2025-09-25: INS; 2025-09-26: INS; 2025-09-29: EDM; 2025-09-30: EDM; 2025-10-01: EDM; 2025-10-02: EDM; 2025-10-03: EDM; 2025-10-06: EDM; 2025-10-07: EDM; 2025-10-08: Receive,INS; 2025-10-09: INS,DIR; 2025-10-10: INS,DIR
|  |  | CLAMPING PLATE | RT-87550-0118-01-DD-C | 1 |  |  | DONE
|  |  | ADUSTABLE BEARING SEGMENT | RT-87550-0119-01-DD-D | 4
|  |  | WASHER-MODIFIED | RT-87550-0331-01-DD-C | 4
|  |  | TOOL BIT LONG (NORMAL CUT) | RT-87550-0144-01-DD-C | 1
|  |  | TOOL BIT LONG (DEFECT CUT ) | RT-87550-0191-01-DD-C | 1 |  |  | DEBURR |  | 2025-06-23: DEBURR
|  |  | TOOL BIT SHORT (NORMAL CUT) | RT-87550-0187-01-DD-C | 1
|  |  | TOOL BIT SHORT (DEEP CUT) | RT-87550-0188-01-DD-C | 1
|  |  | TOOL BIT LONG (DEEP CUT) | RT-87550-0189-01-DD-C | 1
|  |  | TOOL BIT SHORT (DEFECT CUT ) | RT-87550-0190-01-DD-C | 1 |  |  | Mill |  | 2025-07-22: Mill
|  |  | DOUBLE ACTING LOCK PIN ASSEMBLY | RT-87550-0181-01-GA-D | 1 |  |  | Receive,INS
|  |  | DETENT PIN WELDMENT | RT-87550-0182-01-GA-C | 1 |  |  | Gather All items
|  |  | MODIFIED DETENT PIN | RT-87550-0328-01-DD-C | 1
|  |  | PIN (1/4" DIA) | RT-87550-0329-01-DD-C | 1 |  |  | TURN |  | 2025-07-23: TURN; 2025-08-01: Grind; 2025-08-04: Deburr; 2025-08-05: INS; 2025-08-06: INS
|  |  | SHELL WRENCH (.093” A. F.) ASSEMBLY | RT-87550-0155-01-GA-C | 1 |  |  | Receive,INS
|  |  | T-HANDLE(.093" A.F.) WELDMENT | RT-87550-0156-01-GA-C | 1 |  |  | TURN |  | 2025-07-24: TURN
|  |  | MODIFIED (.093" A.F.)BALL KEY | RT-87550-0157-01-DD-C | 1
|  |  | BEARING WRENCH (3/16" A/F) ASSEMBLY | RT-87550-0160-01-GA-C | 1 |  |  | Receive,INS | Receive,INS
|  |  | T-HANDLE( 3/16" A.F.) WELDMENT | RT-87550-0161-01-GA-C | 1 |  |  | Silver Solder |  | 2025-07-24: TURN; 2025-08-20: Silver Solder; 2025-08-26: Deburr; 2025-08-27: INS; 2025-08-28: INS; 2025-08-29: Drill; 2025-09-01: Drill; 2025-09-02: Drill; 2025-09-03: Drill; 2025-09-04: Deburr; 2025-09-05: INS,DIR; 2025-09-08: INS,DIR
|  |  | MODIFIED BALL KEY (3/16") | RT-87550-0162-01-DD-C | 1
|  |  | CATCH TRAY WELDMENT (SMALL) | RT-87550-0183-01-GA-D | 1 |  |  | Weld |  | 2025-08-22: Weld; 2025-08-28: Deburr; 2025-08-29: Weigh; 2025-09-01: L-Etch; 2025-09-02: L-Etch; 2025-09-03: INS,DIR; 2025-09-04: INS,DIR
|  |  | CATCH TRAY (SMALL) | RT-87550-0184-01-DD-C | 2 |  |  | Deburr |  | 2025-08-20: Deburr; 2025-08-21: INS,DIR; 2025-08-22: INS,DIR
|  |  | TUBE (SMALL) | RT-87550-0185-01-DD-C | 2 |  |  | DONE |  | 2025-07-17: Form
|  |  | CATCH TRAY WELDMENT (LARGE) | RT-87550-0193-01-GA-D | 1 |  |  | Weld |  | 2025-08-22: Weld; 2025-08-25: Weld; 2025-08-26: Weld; 2025-08-27: Weld; 2025-08-28: Deburr; 2025-08-29: Weigh; 2025-09-01: Weigh; 2025-09-02: L-Etch; 2025-09-03: L-Etch; 2025-09-04: INS,DIR; 2025-09-05: INS,DIR
|  |  | CATCH TRAY (LARGE) | RT-87550-0194-01-DD-D | 2 |  |  | DONE |  | 2025-08-20: Deburr; 2025-08-21: INS,DIR; 2025-08-22: INS,DIR
|  |  | TUBE (LARGE) | RT-87550-0195-01-DD-D | 1 |  |  | DONE |  | 2025-08-11: Deburr; 2025-08-12: INS,DIR; 2025-08-13: INS,DIR
|  |  | STEP MEASURING TOOL | RT-87550-0320-01-GA-E | 1 |  |  | Receive,INS | Receive,INS
|  |  | INNER TUBE | RT-87550-0327-01-DD-C | 1 |  |  | DONE
|  |  | SUPPORT TUBE | RT-87550-0326-01-DD-C | 1 |  |  | DONE
|  |  | GUIDE BLOCK | RT-87550-0325-01-DD-C | 1 |  |  | DONE
|  |  | CLAMP SCREW | RT-87550-0324-01-DD-C | 1 |  |  | DONE
|  |  | WASHER | RT-87550-0323-01-DD-C | 1 |  |  | DONE
|  |  | CONNECTOR | RT-87550-0322-01-DD-C | 1 |  |  | DONE
|  |  | HANDLE - MODIFIED | RT-87550-0321-01-DD-C | 1 |  |  | DONE
72024 | RT98-87550-PN-R004-R.1 | Candu | To Capture cost for Spare parts | Spare parts | Lot | 2025-09-19
72028 | NPO # | DJ Ind. | Auger | NPN | 1 | 2025-02-21
72045 | RT98-87920-PN-R011 | Candu | Leak Test Vacuum Grease Clean'g tool | RT-87920-0353-01-GA-C | 3 | 2025-07-31 | 2025-08-20 | INS |  | 2025-07-14: Tack,Weld; 2025-08-15: INS; 2025-08-18: Pack; 2025-08-19: Pack
|  |  | BODY WELDMENT | RT-87920-0356-01-GA-D |  |  |  | DONE
|  |  | HANDLE | RT38-87920-70627-1-DD-C |  |  |  | DONE
|  |  | VACUUM GREASE CLEANING TOOL MKII HEAD ASSEMBLY | RT-87920-0355-01-GA-C | 3 |  |  | DONE |  | 2025-07-10: Assembly
|  |  | CLAMPING ROD | RT38-16400-007_000-0000-001-01 |  |  |  | DONE
|  |  | NUT | RT38-16400-007_000-0000-002-01 |  |  |  | DONE
|  |  | CLAMPING DISK | RT38-16400-007_000-0000-003-01 |  |  |  | DONE
|  |  | CLAMPING LINK | RT38-16400-007_000-0000-004-01 |  |  |  | DONE
|  |  | SMALL HEAD ASSEMBLY | RT38-16400-007_000-1000-000-01-GA-C |  |  |  | DONE
|  |  | LARGE HEAD ASSEMBLY | RT38-16400-007_000-2000-000-01 |  |  |  | DONE
72046 | RT98-87920-PN-R011 | Candu | CTI Cleaning Tool | RT-87920-0357-01-GA-C | 4 | 2025-07-31 | 2025-08-20 | DONE |  | 2025-07-14: Tack,Weld; 2025-08-15: INS; 2025-08-18: Pack; 2025-08-19: Pack
|  |  | SWAB HEAD ASSEMBLY | RT38-16300-024_000-0000-000-01-GA-C | 1 |  |  | DONE |  | 2025-07-09: Assembly
|  |  | CLAMPING ROD | RT38-16300-024_000-0000-001-01-DD-C | 1 |  |  | DONE
|  |  | NUT | RT38-16300-024_000-0000-002-01-DD-C | 1 |  |  | DONE
|  |  | HANDLE | RT-87920-70627-1-DD-C | 2 |  |  | DONE
|  |  | CLAMPING LINK | RT38-16300-024_000-0000-003-01-DD | 1 |  |  | DONE
|  |  | SWAB HEAD | RT38-16300-024_000-1000-000-01-GA-C | 1 |  |  | DONE
|  |  | BODY WELDMENT | RT-87920-0356-01-GA-D | 1 |  |  | DONE
72047 | RT98-87920-PN-R011 | Candu | CTI Cleaning Tool - Head | RT38-16300-024-000-0000-000-01-GA-C | 8 | 2025-07-31 | 2025-08-20 | DONE
|  |  | CLAMPING ROD | RT38-16300-024_000-0000-001-01-DD-C | 1 |  |  | DONE
|  |  | NUT | RT38-16300-024_000-0000-002-01-DD-C | 1 |  |  | DONE
|  |  | CLAMPING LINK | RT38-16300-024_000-0000-003-01-DD | 1 |  |  | DONE
|  |  | SWAB HEAD | RT38-16300-024_000-1000-000-01-GA-C | 1 |  |  | DONE
72048 | RT98-87920-PN-R011 | Candu | Vacuum Grease Cleaning Tool | RT-87920-0355-01-GA-C | 4 | 2025-07-31 | 2025-08-20 | DONE |  | 2025-07-10: Assembly
|  |  | CLAMPING ROD | RT38-16400-007_000-0000-001-01 |  |  |  | DONE
|  |  | NUT | RT38-16400-007_000-0000-002-01 |  |  |  | DONE
|  |  | CLAMPING DISK | RT38-16400-007_000-0000-003-01 |  |  |  | DONE
|  |  | CLAMPING LINK | RT38-16400-007_000-0000-004-01 |  |  |  | DONE
|  |  | SMALL HEAD ASSEMBLY | RT38-16400-007_000-1000-000-01-GA-C |  |  |  | DONE
|  |  | LARGE HEAD ASSEMBLY | RT38-16400-007_000-2000-000-01 |  |  |  | DONE
72057 | 87982- Rev.4 | ATS-Corp | CTSB Central Shaft stationary | MCR-15300-001-161000-01-GA-D | 1 | 2025-04-25 | ★外注あり(済) | Receive,INS | Order material | 2025-07-04: Receive,INS; 2025-08-06: Receive,INS; 2025-08-07: Nickel plate; 2025-08-08: Nickel plate; 2025-08-11: Nickel plate; 2025-08-12: Nickel plate; 2025-08-13: Nickel plate; 2025-08-14: Nickel plate; 2025-08-15: Nickel plate; 2025-08-18: Nickel plate; 2025-08-19: Receive,INS; 2025-08-26: INS,DIR; 2025-08-27: INS,DIR; 2025-08-28: Pack
72058 |  |  |  | MCR-15300-001-163002-01-DD-C |  |  |  | DONE
72061 | 280099239 | Kinectrics | Sliding Bar 02 | NPD0059-DET-5407 | 1 | 2025-04-04 |  | DONE
72066 | 280099239 | Kinectrics | Parts for Bellows Weldment | NPD0059-WLD-6309-C,D | 1 | 2025-04-04 | ★Dimention Change | DONE |  | 2025-08-28: Turn; 2025-08-29: Mill; 2025-09-01: Mill; 2025-09-02: Deburr; 2025-09-03: INS,DIR; 2025-09-04: INS,DIR; 2025-09-05: Pack
72066 | 280099239 | Kinectrics | Parts for Bellows Weldment | NPD0059-WLD-6309-A | 1 | 2025-04-04 |  | DONE |  | 2025-07-14: Mill
72066 | 280099239 | Kinectrics | Parts for Bellows Weldment | NPD0059-WLD-6309-B | 1 | 2025-04-04 |  | DONE |  | 2025-07-04: DEBURR
72073 | 280099239 | Kinectrics | H-Beam | NPD0059-DET-6304 | 2 | 2025-04-04 |  | DONE
|  |  |  | NPD0059-DET-6322 |  |  |  | DONE
|  |  |  | NPD0059-DET-5506 |  |  |  | DONE
|  |  |  | NET0059-DET-5507 |  |  |  | DONE
|  |  |  | NET0059-DET-5220 |  |  |  | DONE
72083 | RT79-88030-PN-R001 | Candu | Garter Spring Detection Tool | RT-88030-0300-01-GA-0 | 3 | 2025-08-27 | ★already received | INS | Receive,INS | 2025-08-11: Gather All items; 2025-08-12: ASSY; 2025-08-13: ASSY; 2025-08-14: ASSY; 2025-08-15: Clean; 2025-08-18: INS,DIR; 2025-08-19: INS,DIR; 2025-08-20: Receive; 2025-08-21: Pack; 2025-08-22: Pack; 2025-08-25: Ship; 2025-10-22: INS; 2025-10-23: INS; 2025-10-24: INS; 2025-10-27: INS; 2025-10-28: INS; 2025-10-29: DIR; 2025-10-30: DIR; 2025-10-31: DIR; 2025-11-03: DIR; 2025-11-04: DIR
|  |  | SHIELD PLUG | RT-88030-0302-01-DD-2 | 6 |  |  | DONE |  | 2025-07-23: Turn
|  |  | CENTERING RING-THRU CUT | RT38-17300-008_000-0000-009-01-DD-C | 24 |  |  | DONE |  | 2025-07-22: TURN; 2025-07-31: Mill
|  |  | CENTERING RING-NO THRU CUT | RT38-17300-008_000-0000-007-01-DD-C | 5 |  |  | DONE |  | 2025-07-22: TURN
|  |  | SHIELD PLUG-THRU CUT | RT38-17300-008_000-0000-010-01-DD-C | 9 |  |  | DONE |  | 2025-07-23: Turn; 2025-08-14: Mill; 2025-08-15: Mill; 2025-08-18: Mill; 2025-08-19: Deburr; 2025-08-20: INS; 2025-08-21: Split; 2025-08-22: Split; 2025-08-25: Tap; 2025-08-26: Tap; 2025-08-27: Deburr; 2025-08-28: INS,DIR; 2025-08-29: INS,DIR
|  |  | PIPE WELDMENT 3 | RT-88030-0314-01-DD-C | 1 |  |  | DONE |  | 2025-07-15: TURN
|  |  | HEAD ADAPTER | RT-88030-0315-01-DD-C | 1 |  |  | DONE
|  |  | PIPE WELDMENT 2 | RT-88030-0307-01-DD-C | 3 |  |  | DONE |  | 2025-08-07: Deburr; 2025-08-26: INS,DIR; 2025-08-27: INS,DIR
|  |  | OUTBOARD PIECE | RT38-17300-008_000-0000-008-01-DD-C | 1 |  |  | DONE
|  |  | INBOARD PIECE | 21RT-88030-0401-001-DD-2 | 1 |  |  | DONE
|  |  | STAND OFF | RT-88030-0035-1-DD-2 | 2 |  |  | DONE
|  |  | PROBE VERIFICATION PIPE | 21RT-88030-0408-001-DD-2 | 1 |  |  | DONE |  | 2025-07-08: Turn; 2025-08-01: Deburr; 2025-08-04: Deburr; 2025-08-05: INS,DIR; 2025-08-06: INS,DIR
|  |  | PIPE WELDMENT 1 | RT-88030-0306-01-DD-C | 3 |  |  | DONE |  | 2025-07-15: TURN
|  |  | COILFORMER BODY | RT38-17300-008_000-0000-002-01-DD-C | 1 | 2025-07-21 |  | DONE
|  |  | BALL PIN ASSEMBLY | RT-88030-0120-01-GA-2 | 1 |  |  | DONE
|  |  | MACHINED BALL PIN | RT-88030-0121-01-DD-2 | 1 |  |  | DONE
|  |  | BALL | RT-88030-0122-01-DD-2 | 1 |  |  | DONE
|  |  | WASHER | RT-88030-0123-01-DD-2 | 1 |  |  | DONE
|  |  | SPRING | RT-88030-0124-01-DD-2 | 1 |  |  | DONE
|  |  | TELEMENTARY DIAGRAM | RT-88030-7601-01-ED-B | 3 | 2025-07-21 |  | Sub-parts are on order
|  |  | TELEMENTARY DIAGRAM | RT-88030-7601-02-BD-C | 3 | 2025-07-21 |  | Sub-parts are on order
|  |  | TELEMENTARY DIAGRAM | RT-88030-7601-03-ED-C | 3 | 2025-07-21 |  | Sub-parts are on order
|  |  | TELEMENTARY DIAGRAM | RT-88030-7601-04-ED-C | 3 | 2025-07-21 |  | Sub-parts are on order
|  |  | TELEMENTARY DIAGRAM | RT-88030-7601-05-ED-C | 3 | 2025-07-21 |  | Sub-parts are on order
|  |  | TELEMENTARY DIAGRAM | RT-88030-7601-05-BM-C | 3 | 2025-07-21 |  | Sub-parts are on order
|  |  | SLIDER BLOCK | RT-88030-0125-01-DD-2 | 1 |  |  | DONE
72084 | RT79-88030-PN-R001 | Candu | Single Spacer Drop off Tool | RT-88030-0063-01-GA-E | 4 | 2025-08-27 |  | Assembly |  | 2025-07-02: Fit,Tack,Weld; 2025-08-20: Gather All items; 2025-08-21: ASSY; 2025-08-22: ASSY; 2025-08-25: Paint; 2025-08-26: Paint; 2025-08-27: Deburr; 2025-08-28: L-etch; 2025-08-29: L-etch; 2025-09-01: INS; 2025-09-02: INS; 2025-09-03: Pack; 2025-09-04: Pack; 2025-09-05: Ship; 2025-09-23: Drill Deburr; 2025-09-24: Deburr; 2025-09-25: L-Etch; 2025-09-26: L-Etch; 2025-09-29: INS,DIR; 2025-09-30: INS,DIR; 2025-10-01: INS,DIR; 2025-10-02: INS,DIR; 2025-10-03: INS,DIR; 2025-10-06: INS,DIR; 2025-10-07: INS,DIR; 2025-10-08: INS,DIR; 2025-10-22: Assembly; 2025-10-23: Assembly; 2025-10-24: Assembly; 2025-10-27: INS; 2025-10-28: INS; 2025-10-29: DIR; 2025-10-30: DIR; 2025-10-31: DIR; 2025-11-03: DIR; 2025-11-04: DIR
|  |  | Stop pin | RT38-17300-002_000-0000-003-01-DD-B | 10 |  |  | DONE
|  |  | CABLE WELDMENT | RT-88030-0062-01-DD-C | 4 |  |  | DONE |  | 2025-06-19: Receive or Stock
|  |  | SPACER HOLDER ASSEMBLY | RT-88030-0064-01-GA-E | 1 |  |  | DONE | Receive,INS
|  |  | CAM SLEEVE | RT-88030-0076-01-DD-D | 1 |  |  | DONE
|  |  | CAM PIN | RT-88030-0075-01-DD-C | 3 |  |  | DONE
|  |  | SPACER HOLDER ASSEMBLY | RT-88030-0064-02-GA-E | 10 |  | ★外注あり 8/20返却済 | Mill |  | 2025-07-01: DEBURR; 2025-07-30: Polyurethane Prothane; 2025-07-31: Polyurethane Prothane; 2025-08-01: Polyurethane Prothane; 2025-08-04: Polyurethane Prothane; 2025-08-05: Polyurethane Prothane; 2025-08-06: Polyurethane Prothane; 2025-08-07: Polyurethane Prothane; 2025-08-08: Polyurethane Prothane; 2025-08-11: Polyurethane Prothane; 2025-08-12: Polyurethane Prothane; 2025-08-13: Polyurethane Prothane; 2025-08-14: Polyurethane Prothane; 2025-08-15: Polyurethane Prothane; 2025-08-18: Polyurethane Prothane; 2025-08-19: Polyurethane Prothane; 2025-08-20: Polyurethane Prothane; 2025-08-21: Reseive,INS; 2025-08-22: INS; 2025-08-25: INS; 2025-08-26: Turn; 2025-08-27: Turn; 2025-08-28: Drill; 2025-08-29: Drill; 2025-09-01: Deburr; 2025-09-02: INS,DIR; 2025-09-03: INS,DIR
|  |  | Shell Pre Machining | RT-88030-0066-01-DD-E | 10 |  |  | DEBURR |  | 2025-07-01: DEBURR
|  |  | CABLE ACTUATOR ASSEMBLY | RT-88030-0059-01-GA-E | 4 |  |  | DONE | Receive,INS
|  |  | MODIFIED SCREW | RT-88030-0069-01-DD-C | 1 |  |  | DONE
|  |  | PLUNGER | RT-88030-0068-01-DD-C | 1 |  |  | DONE
|  |  | HAND KNOB | RT-88030-0067-01-DD-C | 1 |  |  | DONE
|  |  | SPRING CAP | RT-88030-0070-01-DD-C | 1 |  |  | DONE
|  |  | PULL ROD | RT-88030-0071-01-DD-C | 1 |  |  | DONE
|  |  | CABLE ACTUATOR WELDMENT | RT-88030-0060-01-DD-E | 1 |  |  | DONE
|  |  | TUBE WELDMENT DETAIL | RT-88030-0061-01-DD-E | 10 |  |  | DONE
|  |  | Single Spacer Drop off Tool-Tubing | RT-88030-0073-01-DD-C | 4 |  |  | DONE
|  |  | Single Spacer Drop off Tool-Tubing | RT-88030-0072-01-DD-C | 4 |  |  | DONE
72085 | RT98-88030-PN-R001 | Candu | Garter Spring Detection Tool | RT-88030-0300-01-GA-0 | 3 | 2025-08-27 | ★already received | Sub parts are ordered
|  |  | SHIELD PLUG | RT-88030-0302-01-DD-2 | 6 |  |  | ★remake |  | 2025-06-23: Turn; 2025-07-23: TURN
|  |  | CENTERING RING-THRU CUT | RT38-17300-008_000-0000-009-01-DD-C | 24 |  |  | Mill |  | 2025-07-31: Mill
|  |  | CENTERING RING-NO THRU CUT | RT38-17300-008_000-0000-007-01-DD-C | 5 |  |  | DONE
|  |  | SHIELD PLUG-THRU CUT | RT38-17300-008_000-0000-010-01-DD-C | 9 |  |  | Mill |  | 2025-07-23: Turn; 2025-08-14: Mill; 2025-08-15: Mill; 2025-08-18: Mill; 2025-08-19: Deburr; 2025-08-20: INS; 2025-08-21: Split; 2025-08-22: Split; 2025-08-25: Tap; 2025-08-26: Tap; 2025-08-27: Deburr; 2025-08-28: INS,DIR; 2025-08-29: INS,DIR
|  |  | PIPE WELDMENT 3 | RT-88030-0314-01-DD-C | 1 |  |  | DONE
|  |  | HEAD ADAPTER | RT-88030-0315-01-DD-C | 1 |  |  | DONE
|  |  | PIPE WELDMENT 2 | RT-88030-0307-01-DD-C | 1 |  |  | Deburr |  | 2025-07-15: TURN; 2025-08-07: Deburr; 2025-08-26: INS,DIR; 2025-08-27: INS,DIR
|  |  | OUTBOARD PIECE | RT38-17300-008_000-0000-008-01-DD-C | 1 |  |  | DONE
|  |  | INBOARD PIECE | 21RT-88030-0401-001-DD-2 | 1 |  |  | DONE
|  |  | STAND OFF | RT-88030-0035-1-DD-2 | 2 |  |  | DONE
|  |  | PROBE VERIFICATION PIPE | 21RT-88030-0408-001-DD-2 | 1 |  |  | Turn |  | 2025-07-08: Turn
|  |  | PIPE WELDMENT 1 | RT-88030-0306-01-DD-C | 3 |  |  | DONE
|  |  | COILFORMER BODY | RT38-17300-008_000-0000-002-01-DD-C | 1 | 2025-07-21 |  | DONE
|  |  | BALL PIN ASSEMBLY | RT-88030-0120-01-GA-2 | 1 |  |  | DONE
|  |  | MACHINED BALL PIN | RT-88030-0121-01-DD-2 | 1 |  |  | DONE
|  |  | BALL | RT-88030-0122-01-DD-2 | 1 |  |  | DONE
|  |  | WASHER | RT-88030-0123-01-DD-2 | 1 |  |  | DONE
|  |  | SPRING | RT-88030-0124-01-DD-2 | 1 |  |  | DONE
|  |  | TELEMENTARY DIAGRAM | RT-88030-7601-01-ED-B | 3 | 2025-07-21 | Ask Gus when receive | Sub-parts are on order
|  |  | TELEMENTARY DIAGRAM | RT-88030-7601-02-BD-C | 3 | 2025-07-21 | Ask Gus when receive | Sub-parts are on order
|  |  | TELEMENTARY DIAGRAM | RT-88030-7601-03-ED-C | 3 | 2025-07-21 | Ask Gus when receive | Sub-parts are on order
|  |  | TELEMENTARY DIAGRAM | RT-88030-7601-04-ED-C | 3 | 2025-07-21 | Ask Gus when receive | Sub-parts are on order
|  |  | TELEMENTARY DIAGRAM | RT-88030-7601-05-ED-C | 3 | 2025-07-21 | Ask Gus when receive | Sub-parts are on order
|  |  | TELEMENTARY DIAGRAM | RT-88030-7601-05-BM-C | 3 | 2025-07-21 | Ask Gus when receive | Sub-parts are on order
|  |  | SLIDER BLOCK | RT-88030-0125-01-DD-2 | 1 |  |  | DONE
72086 | RT98-88030-PN-R001 | Candu | Single Spacer Drop off Tool | RT-88030-0063-01-GA-E | 6 | 2025-08-27 |  | Fit,Tack,Weld |  | 2025-07-02: Fit,Tack,Weld; 2025-08-20: Gather All items; 2025-08-21: ASSY; 2025-08-22: ASSY; 2025-08-25: Paint; 2025-08-26: Paint; 2025-08-27: Deburr; 2025-08-28: L-etch; 2025-08-29: L-etch; 2025-09-01: INS; 2025-09-02: INS; 2025-09-03: Pack; 2025-09-04: Pack; 2025-09-05: Ship
|  |  | SPACER HOLDER ASSEMBLY | RT-88030-0064-01-GA-E | 1 |  |  | DONE | Receive,INS
|  |  | CAM SLEEVE | RT-88030-0076-01-DD-D | 3 |  |  | DONE
|  |  | CAM PIN | RT-88030-0075-01-DD-C | 1 |  |  | DONE
|  |  | SPACER HOLDER ASSEMBLY | RT-88030-0064-02-GA-E |  |  | ★外注あり 8/20返却済 | INS |  | 2025-07-30: Polyurethane Prothane; 2025-07-31: Polyurethane Prothane; 2025-08-01: Polyurethane Prothane; 2025-08-04: Polyurethane Prothane; 2025-08-05: Polyurethane Prothane; 2025-08-06: Polyurethane Prothane; 2025-08-07: Polyurethane Prothane; 2025-08-08: Polyurethane Prothane; 2025-08-11: Polyurethane Prothane; 2025-08-12: Polyurethane Prothane; 2025-08-13: Polyurethane Prothane; 2025-08-14: Polyurethane Prothane; 2025-08-15: Polyurethane Prothane; 2025-08-18: Polyurethane Prothane; 2025-08-19: Polyurethane Prothane; 2025-08-20: Polyurethane Prothane; 2025-08-21: Reseive,INS; 2025-08-22: INS; 2025-08-25: INS; 2025-08-26: Turn; 2025-08-27: Turn; 2025-08-28: Drill; 2025-08-29: Drill; 2025-09-01: Deburr; 2025-09-02: INS,DIR; 2025-09-03: INS,DIR
|  |  | CABLE ACTUATOR ASSEMBLY | RT-88030-0059-01-GA-E | 6 |  |  | DONE | Receive,INS
|  |  | MODIFIED SCREW | RT-88030-0069-01-DD-C | 1 |  |  | DONE
|  |  | PLUNGER | RT-88030-0068-01-DD-C | 1 |  |  | DONE
|  |  | HAND KNOB | RT-88030-0067-01-DD-C | 1 |  |  | DONE
|  |  | SPRING CAP | RT-88030-0070-01-DD-C | 1 |  |  | DONE
|  |  | PULL ROD | RT-88030-0071-01-DD-C | 1 |  |  | DONE
|  |  | CABLE ACTUATOR WELDMENT | RT-88030-0060-01-DD-E | 1 |  |  | DONE
|  |  | Stop pin | RT38-17300-002_000-0000-003-01-DD-B | 10 |  |  | DONE
|  |  | TUBE WELDMENT DETAIL | RT-88030-0061-01-DD-E
|  |  | Single Spacer Drop off Tool-Tubing | RT-88030-0073-01-DD-C | 6 |  |  | DONE
|  |  | Single Spacer Drop off Tool-Tubing | RT-88030-0072-01-DD-C | 6 |  |  | DONE
|  |  | CABLE WELDMENT | RT-88030-0062-01-DD-C | 6 |  |  | DONE |  | 2025-06-19: Receive or Stock
|  |  | PROTECT SLEEVE | RT-88030-0065-01-DD-B | 6 |  |  | DONE |  | 2025-07-01: CUT
72098 | 19509 | Hybrid | 4-Piston Inj Blk -r/w- WO#25-6945- Gateway | NMP6-3B-Asy- R/W | 1 | 2025-03-24 |  | DONE
72113 | NPO | Metonic | Misc WJ Cutting | Misc | 1 | 2025-02-25 | ★Ask Gus
72129 | PD-20694 | Woodbridge | MZ2x2-D Inj- S7 Nozzles Tested | MZ2X2-D-N-S7N | 3+3 | 2025-03-14 | ★Ask Gus
72139 | RT79-88230-PN-R012 | Candu | Large Template , MK TP-1A | RT-88230-0245-01-GA-E | 1 | 2025-11-24
|  |  | TEMPLATE FRAME MK F-1 | RT-88230-0230-01-GA-E | 1
|  |  | DECK PLATE MK. P-1A | RT-88230-0235-01-DD-D | 1
|  |  | DECK PLATE MK. P-1B | RT-88230-0234-01-DD-D | 1
|  |  | LOCATING BOSS MK. B-1 (3 1/2" DIA FEEDER) | RT-88230-0240-01-DD-C | 21
|  |  | LOCATING BOSS MK. B-2 (3" DIA FEEDER) | RT-88230-0241-01-DD-C | 4
|  |  | LOCATING BOSS MK. B-3 (2 1/2" DIA FEEDER) | RT-88230-0242-01-DD-C | 63
|  |  | LOCATING BOSS MK. B-4 (2" DIA FEEDER) | RT-88230-0243-01-DD-C | 49
|  |  | LOCATING BOSS MK. B-5 (1 1/2" DIA FEEDER) | RT-88230-0244-01-DD-C | 11
72139 | RT79-88230-PN-R012 | Candu | Tap Drill Jig |  | 1 |  |  | Laser Etch |  | 2025-07-11: Laser Etch
72140 | RT79-88230-PN-R012 | Candu | Large Template , MK TP-1C | RT-88230-0246-01-GA-E | 1 | 2025-11-24
|  |  | TEMPLATE FRAME MK F-1 | RT-88230-0230-01-GA-E | 1
|  |  | DECK PLATE MK. P-1A | RT-88230-0235-01-DD-D | 1
|  |  | DECK PLATE MK. P-1B | RT-88230-0234-01-DD-D | 1
|  |  | LOCATING BOSS MK. B-1 (3 1/2" DIA FEEDER) | RT-88230-0240-01-DD-C | 21
|  |  | LOCATING BOSS MK. B-2 (3" DIA FEEDER) | RT-88230-0241-01-DD-C | 4
|  |  | LOCATING BOSS MK. B-3 (2 1/2" DIA FEEDER) | RT-88230-0242-01-DD-C | 63
|  |  | LOCATING BOSS MK. B-4 (2" DIA FEEDER) | RT-88230-0243-01-DD-C | 49
|  |  | LOCATING BOSS MK. B-5 (1 1/2" DIA FEEDER) | RT-88230-0244-01-DD-C | 11
72141 | RT79-88230-PN-R012 | Candu | Large Template , MK TP-2A | RT-88230-0247-01-GA-E | 1 | 2025-11-24
|  |  | TEMPLATE FRAME MK F-2 | RT-88230-0231-01-GA-E | 1 |  |  | Deburr | Deburr
|  |  | DECK PLATE MK. P-2A | RT-88230-0236-01-DD-D | 1 |  |  | Material
|  |  | DECK PLATE MK. P-2B | RT-88230-0237-01-DD-D | 1 |  |  | waterjet | waterjet
|  |  | LOCATING BOSS MK. B-1 (3 1/2" DIA FEEDER) | RT-88230-0240-01-DD-C | 21
|  |  | LOCATING BOSS MK. B-2 (3" DIA FEEDER) | RT-88230-0241-01-DD-C | 4
|  |  | LOCATING BOSS MK. B-3 (2 1/2" DIA FEEDER) | RT-88230-0242-01-DD-C | 67
|  |  | LOCATING BOSS MK. B-4 (2" DIA FEEDER | RT-88230-0243-01-DD-C | 46
|  |  | LOCATING BOSS MK. B-5 (1 1/2" DIA FEEDER) | RT-88230-0244-01-DD-C | 10
72142 | RT79-88230-PN-R012 | Candu | Large Template , MK TP-2C | RT-88230-0248-01-GA-E | 1 | 2025-11-24
|  |  | TEMPLATE FRAME MK F-2 | RT-88230-0231-01-GA-E | 1 |  |  | Deburr | Deburr
|  |  | DECK PLATE MK. P-2A | RT-88230-0236-01-DD-D | 1
|  |  | DECK PLATE MK. P-2B | RT-88230-0237-01-DD-D | 1
|  |  | LOCATING BOSS MK. B-1 (3 1/2" DIA FEEDER) | RT-88230-0240-01-DD-C | 21
|  |  | LOCATING BOSS MK. B-2 (3" DIA FEEDER) | RT-88230-0241-01-DD-C | 4
|  |  | LOCATING BOSS MK. B-3 (2 1/2" DIA FEEDER) | RT-88230-0242-01-DD-C | 67
|  |  | LOCATING BOSS MK. B-4 (2" DIA FEEDER) | RT-88230-0243-01-DD-C | 46
|  |  | LOCATING BOSS MK. B-5 (1 1/2" DIA FEEDER) | RT-88230-0244-01-DD-C | 10
72143 | RT79-88230-PN-R012 | Candu | Small Template , MK TP-3A | RT-88230-0249-01-GA-D | 1 | 2025-11-24
|  |  | TEMPLATE FRAME MK F-3A | RT-88230-0232-01-GA-E | 1 |  |  | waterjet | waterjet
|  |  | DECK PLATE MK.P-3A | RT-88230-0238-01-DD-D | 1 |  |  | waterjet | waterjet
|  |  | LOCATING BOSS MK. B-1 (3 1/2" DIA FEEDER) | RT-88230-0240-01-DD-C | 5
|  |  | LOCATING BOSS MK. B-2 (3" DIA FEEDER) | RT-88230-0241-01-DD-C | 5
|  |  | LOCATING BOSS MK. B-3 (2 1/2" DIA FEEDER) | RT-88230-0242-01-DD-C | 15
|  |  | LOCATING BOSS MK. B-4 (2" DIA FEEDER) | RT-88230-0243-01-DD-C | 12
|  |  | LOCATING BOSS MK. B-5 (1 1/2" DIA FEEDER) | RT-88230-0244-01-DD-C | 5
72144 | RT79-88230-PN-R012 | Candu | Small Template , MK TP-3C | RT-88230-0250-01-GA-D | 1 | 2025-11-24
|  |  | TEMPLATE FRAME MK F-3C | RT-88230-0276-01-GA-E | 1
|  |  | DECK PLATE MK.P-3C | RT-88230-0277-01-DD-D | 1
|  |  | LOCATING BOSS MK. B-1 (3 1/2" DIA FEEDER) | RT-88230-0240-01-DD-C | 5
|  |  | LOCATING BOSS MK. B-2 (3" DIA FEEDER) | RT-88230-0241-01-DD-C | 5
|  |  | LOCATING BOSS MK. B-3 (2 1/2" DIA FEEDER) | RT-88230-0242-01-DD-C | 15
|  |  | LOCATING BOSS MK. B-4 (2" DIA FEEDER) | RT-88230-0243-01-DD-C | 12
|  |  | LOCATING BOSS MK. B-5 (1 1/2" DIA FEEDER) | RT-88230-0244-01-DD-C | 5
72145 | RT79-88230-PN-R012 | Candu | Small Template , MK TP-4A | RT-88230-0251-01-GA-D | 1 | 2025-11-24
|  |  | TEMPLATE FRAME MK F-4A | RT-88230-0278-01-GA-E | 1
|  |  | DECK PLATE MK. P-4A | RT-88230-0279-01-DD-D | 1 |  |  | waterjet | waterjet
|  |  | LOCATING BOSS MK. B-1 (3 1/2" DIA FEEDER) | RT-88230-0240-01-DD-C | 7
|  |  | LOCATING BOSS MK. B-2 (3" DIA FEEDER) | RT-88230-0241-01-DD-C | 5
|  |  | LOCATING BOSS MK. B-3 (2 1/2" DIA FEEDER) | RT-88230-0242-01-DD-C | 13
|  |  | LOCATING BOSS MK. B-4 (2" DIA FEEDER) | RT-88230-0243-01-DD-C | 10
|  |  | LOCATING BOSS MK. B-5 (1 1/2" DIA FEEDER) | RT-88230-0244-01-DD-C | 7
72146 | RT79-88230-PN-R012 | Candu | Small Template , MK TP-4C | RT-88230-0252-01-GA-D | 1 | 2025-11-24
|  |  | TEMPLATE FRAME MK F-4C | RT-88230-0233-01-GA-E | 1
|  |  | DECK PLATE MK. P-4C | RT-88230-0239-01-DD-D | 1 |  |  | waterjet | waterjet
|  |  | LOCATING BOSS MK. B-1 (3 1/2" DIA FEEDER) | RT-88230-0240-01-DD-C | 7
|  |  | LOCATING BOSS MK. B-2 (3" DIA FEEDER) | RT-88230-0241-01-DD-C | 5
|  |  | LOCATING BOSS MK. B-3 (2 1/2" DIA FEEDER) | RT-88230-0242-01-DD-C | 13
|  |  | LOCATING BOSS MK. B-4 (2" DIA FEEDER) | RT-88230-0243-01-DD-C | 10
|  |  | LOCATING BOSS MK. B-5 (1 1/2" DIA FEEDER) | RT-88230-0244-01-DD-C | 7
72147 | RT79-88230-PN-R012 | Candu | Upper Feeder Template Assy | RT-88230-0200-01-GA-E | 2 | 2025-10-17
|  |  | TOP SUPPORT ASSEMBLY AND DETAILS | RT-88230-0202-01-GA-E | 1
|  |  | SUPPORT CHANNEL ASSY MK. SC-3 | RT-88230-0261-01-GA-D | 1
|  |  | CHANNEL ASSY MK-SC-1A-CENTER | RT-88230-0264-01-GA-D | 1
|  |  | CHANNEL ASSY MK-SC-1B-CENTER | RT-88230-0265-01-GA-D | 1 |  |  | Fit,Tack,Weld | Fit,Tack,Weld
|  |  | CHANNEL ASSY MK-SC-3A-LEFT | RT-88230-0268-01-GA-D | 1
|  |  | CHANNEL ASSY MK-SC-1A-RIGHT | RT-88230-0267-01-GA-D | 1 |  |  | Fit, Tack, Weld | Fit, Tack, Weld
|  |  | SUPPORT CHANNEL ASSY MK. SC-4 | RT-88230-0263-01-GA-D | 1
|  |  | CHANNEL ASSY MK-SC-4A-LEFT | RT-88230-0269-01-GA-D | 1 |  |  | Fit,Tack,Weld |  | 2025-06-20: Fit,Tack,Weld
|  |  | CHANNEL ASSY MK-SC-4B-CENTER | RT-88230-0270-01-GA-D | 1 |  |  | Fit,Tack,Weld | Fit,Tack,Weld
|  |  | CHANNEL ASSY MK-SC-4A-CENTER | RT-88230-0271-01-GA-D | 1
|  |  | CHANNEL ASSY MK-SC-4A-RIGHT | RT-88230-0272-01-GA-D | 1
|  |  | CHANNEL ASSY MK-SC-2A-RIGHT | RT-88230-0273-01-GA-D | 1 |  |  | Fit,Tack,Weld |  | 2025-06-18: Fit,Tack,Weld
|  |  | CARRIER BEAM ASSY. MK. CB-3 | RT-88230-0256-01-GA-D | 24 |  |  | Weld | CUT | 2025-08-01: Weld
|  |  | CARRIER BEAM ASSY. MK. CB-2 | RT-88230-0256-01-GA-D | 24 |  |  | CUT | CUT
|  |  | CARRIER BEAM ASSY MK. CB-1 | RT-88230-0255-01-GA-D | 4 |  |  | Deburr |  | 2025-06-23: Deburr
|  |  | TIE ROD ANCHOR TP-2A/TP-1C | RT-88230-0203-01-GA-E
|  |  | TIE ROD ASSEMBLY MK. TR-5 | RT-88230-0206-01-GA-D
|  |  | ROD EXTENSION | RT-88230-0216-01-GA-D | 4 |  |  | Face/Turn/Drill/Tap | Face/Turn/Drill/Tap
|  |  | ANCHOR CORNER ASSEMBLY A FACE | RT-88230-0210-01-GA-D
|  |  | ANCHOR CORNER A FACE | RT-88230-0217-01-GA-D
|  |  | ANCHOR CORNER A FACE | RT-88230-0218-01-GA-D
|  |  | TIE ROD ASSEMBLY MK. TR-3 | RT-88230-0209-01-GA-D
|  |  | ANCHOR SHORT CORNER ASSY. A FACE | RT-88230-0215-01-GA-D
|  |  | ANCHOR CORNER A FACE | RT-88230-0226-01-GA-D
|  |  | ANCHOR CORNER A FACE | RT-88230-0227-01-GA-D
|  |  | TIE ROD ASSEMBLY MK. TR-2 | RT-88230-0207-01-GA-D
|  |  | ROD EXTENSION - SHORT | RT-88230-0219-01-GA-D | 4 |  |  | TURN |  | 2025-07-02: TURN
|  |  | ANCHOR ANGLE ASSEMBLY A FACE | RT-88230-0211-01-GA-D
|  |  | ANCHOR ANGLE A FACE | RT-88230-0220-01-GA-D
|  |  | ANCHOR ANGLE A FACE | RT-88230-0221-01-GA-D
|  |  | TIE ROD ASSEMBLY MK. TR-4 | RT-88230-0208-01-GA-D
|  |  | TIE ROD ANCHOR ASSEMBLY SAB | RT-88230-0214-01-GA-D
|  |  | TIE ROD ANCHOR SAB | RT-88230-0223-01-DD-D
|  |  | TIE ROD ANCHOR SCB | RT-88230-0224-01-DD-D
|  |  | TIE ROD ANCHOR SHORT A/C | RT-88230-0203-01-GA-E
|  |  | TIE ROD ASSEMBLY MK. TR-5 | RT-88230-0206-01-GA-D
|  |  | ROD EXTENSION | RT-88230-0216-01-GA-D | 4 |  |  | Face/Turn/Drill/Tap | Face/Turn/Drill/Tap
|  |  | ANCHOR CORNER ASSEMBLY A FACE | RT-88230-0210-01-GA-D
|  |  | ANCHOR CORNER A FACE | RT-88230-0217-01-GA-D
|  |  | ANCHOR CORNER A FACE | RT-88230-0218-01-GA-D
|  |  | TIE ROD ASSEMBLY MK. TR-3 | RT-88230-0209-01-GA-D
|  |  | ANCHOR SHORT CORNER ASSY. A FACE | RT-88230-0215-01-GA-D
|  |  | ANCHOR CORNER A FACE | RT-88230-0226-01-GA-D
|  |  | ANCHOR CORNER A FACE | RT-88230-0227-01-GA-D
|  |  | TIE ROD ASSEMBLY MK. TR-2 | RT-88230-0207-01-GA-D
|  |  | ROD EXTENSION - SHORT | RT-88230-0219-01-GA-D
|  |  | ANCHOR ANGLE ASSEMBLY A FACE | RT-88230-0211-01-GA-D
|  |  | ANCHOR ANGLE A FACE | RT-88230-0220-01-GA-D
|  |  | ANCHOR ANGLE A FACE | RT-88230-0221-01-GA-D
|  |  | TIE ROD ASSEMBLY MK. TR-4 | RT-88230-0208-01-GA-D
|  |  | TIE ROD ANCHOR ASSEMBLY SAB | RT-88230-0214-01-GA-D
|  |  | TIE ROD ANCHOR SAB | RT-88230-0223-01-DD-D
|  |  | TIE ROD ANCHOR SCB | RT-88230-0224-01-DD-D
|  |  | TIE ROD ANCHOR TP-1A/TP-2 | RT-88230-0203-01-GA-E
|  |  | TIE ROD ASSEMBLY MK. TR-5 | RT-88230-0206-01-GA-D
|  |  | ROD EXTENSION | RT-88230-0216-01-GA-D | 4 |  |  | Face/Turn/Drill/Tap | Face/Turn/Drill/Tap
|  |  | ANCHOR CORNER ASSEMBLY A FACE | RT-88230-0210-01-GA-D
|  |  | ANCHOR CORNER A FACE | RT-88230-0217-01-GA-D |  |  |  | Chamfer | Chamfer
|  |  | ANCHOR CORNER A FACE | RT-88230-0218-01-GA-D |  |  |  | Chamfer | Chamfer
|  |  | TIE ROD ASSEMBLY MK. TR-3 | RT-88230-0209-01-GA-D
|  |  | ANCHOR SHORT CORNER ASSY. A FACE | RT-88230-0215-01-GA-D
|  |  | ANCHOR CORNER A FACE | RT-88230-0226-01-GA-D
|  |  | ANCHOR CORNER A FACE | RT-88230-0227-01-GA-D
|  |  | TIE ROD ASSEMBLY MK. TR-2 | RT-88230-0207-01-GA-D
|  |  | ROD EXTENSION - SHORT | RT-88230-0219-01-GA-D
|  |  | ANCHOR ANGLE ASSEMBLY A FACE | RT-88230-0211-01-GA-D
|  |  | ANCHOR ANGLE A FACE | RT-88230-0220-01-GA-D
|  |  | ANCHOR ANGLE A FACE | RT-88230-0221-01-GA-D
|  |  | TIE ROD ASSEMBLY MK. TR-4 | RT-88230-0208-01-GA-D
|  |  | TIE ROD ANCHOR ASSEMBLY SAB | RT-88230-0214-01-GA-D
|  |  | TIE ROD ANCHOR SAB | RT-88230-0223-01-DD-D
|  |  | TIE ROD ANCHOR SCB | RT-88230-0224-01-DD-D
|  |  | TIE ROD ANCHOR SAB/SCB | RT-88230-0203-01-GA-E
|  |  | TIE ROD ASSEMBLY MK. TR-5 | RT-88230-0206-01-GA-D
|  |  | ROD EXTENSION | RT-88230-0216-01-GA-D | 4 |  |  | Face/Turn/Drill/Tap | Face/Turn/Drill/Tap
|  |  | ANCHOR CORNER ASSEMBLY A FACE | RT-88230-0210-01-GA-D
|  |  | ANCHOR CORNER A FACE | RT-88230-0217-01-GA-D
|  |  | ANCHOR CORNER A FACE | RT-88230-0218-01-GA-D
|  |  | TIE ROD ASSEMBLY MK. TR-3 | RT-88230-0209-01-GA-D
|  |  | ANCHOR SHORT CORNER ASSY. A FACE | RT-88230-0215-01-GA-D
|  |  | ANCHOR CORNER A FACE | RT-88230-0226-01-GA-D | 2 |  |  | Fit,Tack,Weld | Fit,Tack,Weld
|  |  | ANCHOR CORNER A FACE | RT-88230-0227-01-GA-D | 2 |  |  | Fit,Tack,Weld | Fit,Tack,Weld
|  |  | TIE ROD ASSEMBLY MK. TR-2 | RT-88230-0207-01-GA-D
|  |  | ROD EXTENSION - SHORT | RT-88230-0219-01-GA-D
|  |  | ANCHOR ANGLE ASSEMBLY A FACE | RT-88230-0211-01-GA-D
|  |  | ANCHOR ANGLE A FACE | RT-88230-0220-01-GA-D
|  |  | ANCHOR ANGLE A FACE | RT-88230-0221-01-GA-D
|  |  | TIE ROD ASSEMBLY MK. TR-4 | RT-88230-0208-01-GA-D
|  |  | TIE ROD ANCHOR ASSEMBLY SAB | RT-88230-0214-01-GA-D
|  |  | TIE ROD ANCHOR SAB | RT-88230-0223-01-DD-D | 2 |  |  | DEBURR | DEBURR
|  |  | TIE ROD ANCHOR SCB | RT-88230-0224-01-DD-D
|  |  | SUPPORT BRACKET ASSY. MK. SB-1 | RT-88230-0253-01-GA-C | 20 |  |  | Deburr | Deburr
|  |  | SUPPORT BRACKET ASSY. MK. SB-2 | RT-88230-0254-01-GA-C
|  |  | LATERAL TIE ARRANGEMENT ASSEMBLY (FACE) MK. TA-4 | RT-88230-0212-01-GA-E
|  |  | TIE ANGLE ASSEMBLY MK TA-5 | RT-88230-0212-01-GA-E
|  |  | TIE ANGLE ASSEMBLY MK TA-4 | RT-88230-0212-01-GA-E
|  |  | LATERAL TIE ARRANGEMENT ASSEMBLY (FACE) MK. TA-5 | RT-88230-0212-01-GA-E
|  |  | TIE ANGLE ASSEMBLY MK TA-5 | RT-88230-0212-01-GA-E
|  |  | TIE ANGLE ASSEMBLY MK TA-4 | RT-88230-0212-01-GA-E
|  |  | LATERAL TIE ARRANGEMENT ASSEMBLY (FACE) MK. TA-1 | RT-88230-0213-01-GA-E
|  |  | TIE ANGLE ASSEMBLY MK TA-1 | RT-88230-0213-01-GA-E
|  |  | TIE ANGLE ASSEMBLY MK TA-3 | RT-88230-0213-01-GA-E
|  |  | TIE ANGLE ASSEMBLY MK TA-2 | RT-88230-0213-01-GA-E
|  |  | TIE ANGLE ASSEMBLY MK TA-3 | RT-88230-0213-01-GA-E
|  |  | LATERAL TIE ARRANGEMENT ASSEMBLY (FACE) MK. TA-2 | RT-88230-0213-01-GA-E
|  |  | TIE ANGLE ASSEMBLY MK TA-1 | RT-88230-0213-01-GA-E
|  |  | TIE ANGLE ASSEMBLY MK TA-3 | RT-88230-0213-01-GA-E
|  |  | TIE ANGLE ASSEMBLY MK TA-2 | RT-88230-0213-01-GA-E
|  |  | TIE ANGLE ASSEMBLY MK TA-3 | RT-88230-0213-01-GA-E
|  |  | LATERAL BRACKET | RT-88230-0274-01-DD-C |  |  |  | DEBURR | DEBURR
|  |  | LATERAL BRACKET | RT-88230-0275-01-DD-C
72180 | 280099616 | Kinectrics | Fastener Plate | NPD0059-DET-6306 | 4 | 2025-05-29
72181 | 280099616 | Kinectrics | Mast Flange | NPD0059-DET-6307 | 2 | 2025-03-24 |  | DONE
72183 | 280099616 | Kinectrics | Flange Connector ( Mcmaster F/I) | NPD0059-DET-6313- F/I | 1 | 2025-03-24
72190 | 280099616 | Kinectrics | Floating Thermocouple Mount Collet | NPD0059-DET-6328 | 3 | 2025-03-24
72200 | 280099616 | Kinectrics | Plate 1-Lower Ins.ulator Plate- Fixed | NPD0059-DET-8017 | 2 | 2025-05-29
72203 | 280099616 | Kinectrics | Plate 1- Upper Insulator Plate- Floating | NPD0059-DET-8019 | 2 | 2025-05-29
72205 | 280099616 | Kinectrics | Plate 1- Lower Insulator Plate- Floating | NPD0059-DET-8022 | 2 | 2025-05-29
72207 | 280099616 | Kinectrics | Plate 1- Upper Insulator Plate- Fixed | NPD0059-DET-8013 | 2 | 2025-05-29
72226 | 4500933778 | Westinghouse | Lead Screw | NTR-MU01-T3-164 | 2 | 2025-06-24 | 7/23 : Receive 7/30 : Ship | DONE | Grind
72234 | RT98-88230-PN-R010 | Candu | Large Template , MK TP-1A | RT-88230-0245-01-GA-E | 1 | 2025-11-24
|  |  | TEMPLATE FRAME MK F-1 | RT-88230-0230-01-GA-E | 1 |  |  | Deburr | Deburr
|  |  | DECK PLATE MK. P-1A | RT-88230-0235-01-DD-D | 1 |  |  | Material
|  |  | DECK PLATE MK. P-1B | RT-88230-0234-01-DD-D | 1 |  |  | waterjet | waterjet
|  |  | LOCATING BOSS MK. B-1 (3 1/2" DIA FEEDER) | RT-88230-0240-01-DD-C | 21
|  |  | LOCATING BOSS MK. B-2 (3" DIA FEEDER) | RT-88230-0241-01-DD-C | 4
|  |  | LOCATING BOSS MK. B-3 (2 1/2" DIA FEEDER) | RT-88230-0242-01-DD-C | 63
|  |  | LOCATING BOSS MK. B-4 (2" DIA FEEDER) | RT-88230-0243-01-DD-C | 49
|  |  | LOCATING BOSS MK. B-5 (1 1/2" DIA FEEDER) | RT-88230-0244-01-DD-C | 11
72235 | RT98-88230-PN-R010 | Candu | Large Template , MK TP-1C | RT-88230-0246-01-GA-E | 1 | 2025-11-24
|  |  | TEMPLATE FRAME MK F-1 | RT-88230-0230-01-GA-E | 1 |  |  | Deburr | Deburr
|  |  | DECK PLATE MK. P-1A | RT-88230-0235-01-DD-D | 1
|  |  | DECK PLATE MK. P-1B | RT-88230-0234-01-DD-D | 1
|  |  | LOCATING BOSS MK. B-1 (3 1/2" DIA FEEDER) | RT-88230-0240-01-DD-C | 21
|  |  | LOCATING BOSS MK. B-2 (3" DIA FEEDER) | RT-88230-0241-01-DD-C | 4
|  |  | LOCATING BOSS MK. B-3 (2 1/2" DIA FEEDER) | RT-88230-0242-01-DD-C | 63
|  |  | LOCATING BOSS MK. B-4 (2" DIA FEEDER) | RT-88230-0243-01-DD-C | 49
|  |  | LOCATING BOSS MK. B-5 (1 1/2" DIA FEEDER) | RT-88230-0244-01-DD-C | 11
72236 | RT98-88230-PN-R010 | Candu | Large Template , MK TP-2A | RT-88230-0247-01-GA-E | 1 | 2025-11-24
|  |  | TEMPLATE FRAME MK F-2 | RT-88230-0231-01-GA-E | 1
|  |  | DECK PLATE MK. P-2A | RT-88230-0236-01-DD-D | 1
|  |  | DECK PLATE MK. P-2B | RT-88230-0237-01-DD-D | 1
|  |  | LOCATING BOSS MK. B-1 (3 1/2" DIA FEEDER) | RT-88230-0240-01-DD-C | 21
|  |  | LOCATING BOSS MK. B-2 (3" DIA FEEDER) | RT-88230-0241-01-DD-C | 4
|  |  | LOCATING BOSS MK. B-3 (2 1/2" DIA FEEDER) | RT-88230-0242-01-DD-C | 67
|  |  | LOCATING BOSS MK. B-4 (2" DIA FEEDER | RT-88230-0243-01-DD-C | 46
|  |  | LOCATING BOSS MK. B-5 (1 1/2" DIA FEEDER) | RT-88230-0244-01-DD-C | 10
72237 | RT98-88230-PN-R010 | Candu | Large Template , MK TP-2C | RT-88230-0248-01-GA-E | 1 | 2025-11-24
|  |  | TEMPLATE FRAME MK F-2 | RT-88230-0231-01-GA-E | 1
|  |  | DECK PLATE MK. P-2A | RT-88230-0236-01-DD-D | 1
|  |  | DECK PLATE MK. P-2B | RT-88230-0237-01-DD-D | 1
|  |  | LOCATING BOSS MK. B-1 (3 1/2" DIA FEEDER) | RT-88230-0240-01-DD-C | 21
|  |  | LOCATING BOSS MK. B-2 (3" DIA FEEDER) | RT-88230-0241-01-DD-C | 4
|  |  | LOCATING BOSS MK. B-3 (2 1/2" DIA FEEDER) | RT-88230-0242-01-DD-C | 67
|  |  | LOCATING BOSS MK. B-4 (2" DIA FEEDER) | RT-88230-0243-01-DD-C | 46
|  |  | LOCATING BOSS MK. B-5 (1 1/2" DIA FEEDER) | RT-88230-0244-01-DD-C | 10
72238 | RT98-88230-PN-R010 | Candu | Small Template , MK TP-3A | RT-88230-0249-01-GA-D | 1 | 2025-11-24
|  |  | TEMPLATE FRAME MK F-3A | RT-88230-0232-01-GA-E | 1 |  |  | waterjet | waterjet
|  |  | DECK PLATE MK.P-3A | RT-88230-0238-01-DD-D | 1 |  |  | waterjet | waterjet
|  |  | LOCATING BOSS MK. B-1 (3 1/2" DIA FEEDER) | RT-88230-0240-01-DD-C | 5
|  |  | LOCATING BOSS MK. B-2 (3" DIA FEEDER) | RT-88230-0241-01-DD-C | 5
|  |  | LOCATING BOSS MK. B-3 (2 1/2" DIA FEEDER) | RT-88230-0242-01-DD-C | 15
|  |  | LOCATING BOSS MK. B-4 (2" DIA FEEDER) | RT-88230-0243-01-DD-C | 12
|  |  | LOCATING BOSS MK. B-5 (1 1/2" DIA FEEDER) | RT-88230-0244-01-DD-C | 5
72239 | RT98-88230-PN-R010 | Candu | Small Template , MK TP-3C | RT-88230-0250-01-GA-D | 1 | 2025-11-24
|  |  | TEMPLATE FRAME MK F-3C | RT-88230-0276-01-GA-E | 1
|  |  | DECK PLATE MK.P-3C | RT-88230-0277-01-DD-D | 1 |  |  | waterjet | waterjet
|  |  | LOCATING BOSS MK. B-1 (3 1/2" DIA FEEDER) | RT-88230-0240-01-DD-C | 5
|  |  | LOCATING BOSS MK. B-2 (3" DIA FEEDER) | RT-88230-0241-01-DD-C | 5
|  |  | LOCATING BOSS MK. B-3 (2 1/2" DIA FEEDER) | RT-88230-0242-01-DD-C | 15
|  |  | LOCATING BOSS MK. B-4 (2" DIA FEEDER) | RT-88230-0243-01-DD-C | 12
|  |  | LOCATING BOSS MK. B-5 (1 1/2" DIA FEEDER) | RT-88230-0244-01-DD-C | 5
72240 | RT98-88230-PN-R010 | Candu | Small Template , MK TP-4A | RT-88230-0251-01-GA-D | 1 | 2025-11-24
|  |  | TEMPLATE FRAME MK F-4A | RT-88230-0278-01-GA-E | 1
|  |  | DECK PLATE MK. P-4A | RT-88230-0279-01-DD-D | 1
|  |  | LOCATING BOSS MK. B-1 (3 1/2" DIA FEEDER) | RT-88230-0240-01-DD-C | 7
|  |  | LOCATING BOSS MK. B-2 (3" DIA FEEDER) | RT-88230-0241-01-DD-C | 5
|  |  | LOCATING BOSS MK. B-3 (2 1/2" DIA FEEDER) | RT-88230-0242-01-DD-C | 13
|  |  | LOCATING BOSS MK. B-4 (2" DIA FEEDER) | RT-88230-0243-01-DD-C | 10
|  |  | LOCATING BOSS MK. B-5 (1 1/2" DIA FEEDER) | RT-88230-0244-01-DD-C | 7
72241 | RT98-88230-PN-R010 | Candu | Small Template , MK TP-4C | RT-88230-0252-01-GA-D | 1 | 2025-11-24
|  |  | TEMPLATE FRAME MK F-4C | RT-88230-0233-01-GA-E | 1
|  |  | DECK PLATE MK. P-4C | RT-88230-0239-01-DD-D | 1
|  |  | LOCATING BOSS MK. B-1 (3 1/2" DIA FEEDER) | RT-88230-0240-01-DD-C | 7
|  |  | LOCATING BOSS MK. B-2 (3" DIA FEEDER) | RT-88230-0241-01-DD-C | 5
|  |  | LOCATING BOSS MK. B-2 (3" DIA FEEDER) | RT-88230-0242-01-DD-C | 13
|  |  | LOCATING BOSS MK. B-4 (2" DIA FEEDER) | RT-88230-0243-01-DD-C | 10
|  |  | LOCATING BOSS MK. B-5 (1 1/2" DIA FEEDER) | RT-88230-0244-01-DD-C | 7
72242 | RT98-88230-PN-R010 | Candu | Upper Feeder Template Assy | RT-88230-0200-01-GA-E | 2 | 2025-11-24
|  |  | TOP SUPPORT ASSEMBLY AND DETAILS | RT-88230-0202-01-GA-E | 1
|  |  | SUPPORT CHANNEL ASSY MK. SC-3 | RT-88230-0261-01-GA-D | 1
|  |  | CHANNEL ASSY MK-SC-1A-CENTER | RT-88230-0264-01-GA-D | 1 |  |  | Material
|  |  | CHANNEL ASSY MK-SC-1B-CENTER | RT-88230-0265-01-GA-D | 1 |  |  | DONE
|  |  | CHANNEL ASSY MK-SC-3A-LEFT | RT-88230-0268-01-GA-D | 1 |  |  | Fit,Tack,Weld |  | 2025-06-18: Fit,Tack,Weld
|  |  | CHANNEL ASSY MK-SC-1A-RIGHT | RT-88230-0267-01-GA-D | 1 |  |  | Fit,Tack,Weld | Fit,Tack,Weld
|  |  | SUPPORT CHANNEL ASSY MK. SC-4 | RT-88230-0263-01-GA-D | 1
|  |  | CHANNEL ASSY MK-SC-4A-LEFT | RT-88230-0269-01-GA-D | 1
|  |  | CHANNEL ASSY MK-SC-4B-CENTER | RT-88230-0270-01-GA-D | 1
|  |  | CHANNEL ASSY MK-SC-4A-CENTER | RT-88230-0271-01-GA-D | 1 |  |  | Material
|  |  | CHANNEL ASSY MK-SC-4A-RIGHT | RT-88230-0272-01-GA-D | 1
|  |  | CARRIER BEAM ASSY. MK. CB-3 | RT-88230-0256-01-GA-D | 8 |  |  | Cut
|  |  | CARRIER BEAM ASSY. MK. CB-2 | RT-88230-0256-01-GA-D | 8 |  |  | Weld |  | 2025-08-01: Weld
|  |  | CARRIER BEAM ASSY MK. CB-1 | RT-88230-0255-01-GA-D | 4 |  |  | Deburr |  | 2025-06-23: Deburr
|  |  | TIE ROD ANCHOR TP-2A/TP-1C | RT-88230-0203-01-GA-E
|  |  | TIE ROD ASSEMBLY MK. TR-5 | RT-88230-0206-01-GA-D
|  |  | ROD EXTENSION | RT-88230-0216-01-GA-D
|  |  | ANCHOR CORNER ASSEMBLY A FACE | RT-88230-0210-01-GA-D
|  |  | ANCHOR CORNER A FACE | RT-88230-0217-01-GA-D
|  |  | ANCHOR CORNER A FACE | RT-88230-0218-01-GA-D
|  |  | TIE ROD ASSEMBLY MK. TR-3 | RT-88230-0209-01-GA-D
|  |  | ANCHOR SHORT CORNER ASSY. A FACE | RT-88230-0215-01-GA-D
|  |  | ANCHOR CORNER A FACE | RT-88230-0226-01-GA-D
|  |  | ANCHOR CORNER A FACE | RT-88230-0227-01-GA-D
|  |  | TIE ROD ASSEMBLY MK. TR-2 | RT-88230-0207-01-GA-D
|  |  | ROD EXTENSION - SHORT | RT-88230-0219-01-GA-D
|  |  | ANCHOR ANGLE ASSEMBLY A FACE | RT-88230-0211-01-GA-D
|  |  | ANCHOR ANGLE A FACE | RT-88230-0220-01-GA-D
|  |  | ANCHOR ANGLE A FACE | RT-88230-0221-01-GA-D
|  |  | TIE ROD ASSEMBLY MK. TR-4 | RT-88230-0208-01-GA-D
|  |  | TIE ROD ANCHOR ASSEMBLY SAB | RT-88230-0214-01-GA-D
|  |  | TIE ROD ANCHOR SAB | RT-88230-0223-01-DD-D
|  |  | TIE ROD ANCHOR SCB | RT-88230-0224-01-DD-D | 2 |  |  | DEBURR | DEBURR
|  |  | TIE ROD ANCHOR SHORT A/C | RT-88230-0203-01-GA-E
|  |  | TIE ROD ASSEMBLY MK. TR-5 | RT-88230-0206-01-GA-D
|  |  | ROD EXTENSION | RT-88230-0216-01-GA-D
|  |  | ANCHOR CORNER ASSEMBLY A FACE | RT-88230-0210-01-GA-D
|  |  | ANCHOR CORNER A FACE | RT-88230-0217-01-GA-D
|  |  | ANCHOR CORNER A FACE | RT-88230-0218-01-GA-D
|  |  | TIE ROD ASSEMBLY MK. TR-3 | RT-88230-0209-01-GA-D
|  |  | ANCHOR SHORT CORNER ASSY. A FACE | RT-88230-0215-01-GA-D
|  |  | ANCHOR CORNER A FACE | RT-88230-0226-01-GA-D
|  |  | ANCHOR CORNER A FACE | RT-88230-0227-01-GA-D
|  |  | TIE ROD ASSEMBLY MK. TR-2 | RT-88230-0207-01-GA-D
|  |  | ROD EXTENSION - SHORT | RT-88230-0219-01-GA-D
|  |  | ANCHOR ANGLE ASSEMBLY A FACE | RT-88230-0211-01-GA-D
|  |  | ANCHOR ANGLE A FACE | RT-88230-0220-01-GA-D
|  |  | ANCHOR ANGLE A FACE | RT-88230-0221-01-GA-D
|  |  | TIE ROD ASSEMBLY MK. TR-4 | RT-88230-0208-01-GA-D
|  |  | TIE ROD ANCHOR ASSEMBLY SAB | RT-88230-0214-01-GA-D
|  |  | TIE ROD ANCHOR SAB | RT-88230-0223-01-DD-D
|  |  | TIE ROD ANCHOR SCB | RT-88230-0224-01-DD-D
|  |  | TIE ROD ANCHOR TP-1A/TP-2 | RT-88230-0203-01-GA-E
|  |  | TIE ROD ASSEMBLY MK. TR-5 | RT-88230-0206-01-GA-D
|  |  | ROD EXTENSION | RT-88230-0216-01-GA-D
|  |  | ANCHOR CORNER ASSEMBLY A FACE | RT-88230-0210-01-GA-D
|  |  | ANCHOR CORNER A FACE | RT-88230-0217-01-GA-D
|  |  | ANCHOR CORNER A FACE | RT-88230-0218-01-GA-D
|  |  | TIE ROD ASSEMBLY MK. TR-3 | RT-88230-0209-01-GA-D
|  |  | ANCHOR SHORT CORNER ASSY. A FACE | RT-88230-0215-01-GA-D
|  |  | ANCHOR CORNER A FACE | RT-88230-0226-01-GA-D
|  |  | ANCHOR CORNER A FACE | RT-88230-0227-01-GA-D
|  |  | TIE ROD ASSEMBLY MK. TR-2 | RT-88230-0207-01-GA-D
|  |  | ROD EXTENSION - SHORT | RT-88230-0219-01-GA-D
|  |  | ANCHOR ANGLE ASSEMBLY A FACE | RT-88230-0211-01-GA-D
|  |  | ANCHOR ANGLE A FACE | RT-88230-0220-01-GA-D
|  |  | ANCHOR ANGLE A FACE | RT-88230-0221-01-GA-D
|  |  | TIE ROD ASSEMBLY MK. TR-4 | RT-88230-0208-01-GA-D
|  |  | TIE ROD ANCHOR ASSEMBLY SAB | RT-88230-0214-01-GA-D
|  |  | TIE ROD ANCHOR SAB | RT-88230-0223-01-DD-D
|  |  | TIE ROD ANCHOR SCB | RT-88230-0224-01-DD-D
|  |  | TIE ROD ANCHOR SAB/SCB | RT-88230-0203-01-GA-E
|  |  | TIE ROD ASSEMBLY MK. TR-5 | RT-88230-0206-01-GA-D
|  |  | ROD EXTENSION | RT-88230-0216-01-GA-D
|  |  | ANCHOR CORNER ASSEMBLY A FACE | RT-88230-0210-01-GA-D
|  |  | ANCHOR CORNER A FACE | RT-88230-0217-01-GA-D
|  |  | ANCHOR CORNER A FACE | RT-88230-0218-01-GA-D
|  |  | TIE ROD ASSEMBLY MK. TR-3 | RT-88230-0209-01-GA-D
|  |  | ANCHOR SHORT CORNER ASSY. A FACE | RT-88230-0215-01-GA-D
|  |  | ANCHOR CORNER A FACE | RT-88230-0226-01-GA-D
|  |  | ANCHOR CORNER A FACE | RT-88230-0227-01-GA-D
|  |  | TIE ROD ASSEMBLY MK. TR-2 | RT-88230-0207-01-GA-D
|  |  | ROD EXTENSION - SHORT | RT-88230-0219-01-GA-D
|  |  | ANCHOR ANGLE ASSEMBLY A FACE | RT-88230-0211-01-GA-D
|  |  | ANCHOR ANGLE A FACE | RT-88230-0220-01-GA-D
|  |  | ANCHOR ANGLE A FACE | RT-88230-0221-01-GA-D
|  |  | TIE ROD ASSEMBLY MK. TR-4 | RT-88230-0208-01-GA-D
|  |  | TIE ROD ANCHOR ASSEMBLY SAB | RT-88230-0214-01-GA-D
|  |  | TIE ROD ANCHOR SAB | RT-88230-0223-01-DD-D
|  |  | TIE ROD ANCHOR SCB | RT-88230-0224-01-DD-D
|  |  | SUPPORT BRACKET ASSY. MK. SB-1 | RT-88230-0253-01-GA-C | 20 |  |  | Deburr | Deburr
|  |  | SUPPORT BRACKET ASSY. MK. SB-2 | RT-88230-0254-01-GA-C
|  |  | LATERAL TIE ARRANGEMENT ASSEMBLY (FACE) MK. TA-4 | RT-88230-0212-01-GA-E
|  |  | TIE ANGLE ASSEMBLY MK TA-5 | RT-88230-0212-01-GA-E
|  |  | TIE ANGLE ASSEMBLY MK TA-4 | RT-88230-0212-01-GA-E
|  |  | LATERAL TIE ARRANGEMENT ASSEMBLY (FACE) MK. TA-5 | RT-88230-0212-01-GA-E
|  |  | TIE ANGLE ASSEMBLY MK TA-5 | RT-88230-0212-01-GA-E
|  |  | TIE ANGLE ASSEMBLY MK TA-4 | RT-88230-0212-01-GA-E
|  |  | LATERAL TIE ARRANGEMENT ASSEMBLY (FACE) MK. TA-1 | RT-88230-0213-01-GA-E
|  |  | TIE ANGLE ASSEMBLY MK TA-1 | RT-88230-0213-01-GA-E
|  |  | TIE ANGLE ASSEMBLY MK TA-3 | RT-88230-0213-01-GA-E
|  |  | TIE ANGLE ASSEMBLY MK TA-2 | RT-88230-0213-01-GA-E
|  |  | TIE ANGLE ASSEMBLY MK TA-3 | RT-88230-0213-01-GA-E
|  |  | LATERAL TIE ARRANGEMENT ASSEMBLY (FACE) MK. TA-2 | RT-88230-0213-01-GA-E
|  |  | TIE ANGLE ASSEMBLY MK TA-1 | RT-88230-0213-01-GA-E
|  |  | TIE ANGLE ASSEMBLY MK TA-3 | RT-88230-0213-01-GA-E
|  |  | TIE ANGLE ASSEMBLY MK TA-2 | RT-88230-0213-01-GA-E
|  |  | TIE ANGLE ASSEMBLY MK TA-3 | RT-88230-0213-01-GA-E
|  |  | LATERAL BRACKET | RT-88230-0274-01-DD-C
|  |  | LATERAL BRACKET | RT-88230-0275-01-DD-C |  |  |  | DEBURR | DEBURR
72264 | RT79-87876-PN-R004 | Candu | Debris Transfer Frame Adapter | RT-87876-0414-01-GA-E | 1 | 2025-08-15 | 2025-08-22 | DONE | Receive ,INS | 2025-07-24: ASSY; 2025-07-25: ASSY; 2025-07-28: ASSY; 2025-07-29: ASSY; 2025-07-30: Claen; 2025-07-31: INS,DIR; 2025-08-01: INS,DIR; 2025-08-04: Pack; 2025-08-05: Pack
|  |  | DEBRIS TRANSFER FRAME ADAPTER WELDMENT | RT-87876-0415-01-GA-E | 1 |  |  | DONE
72265 | RT79-87876-PN-R004 | Candu | Transfer Container Flask ( Tungsten) | RT-87876-0400-01-GA-D | 1 | 2025-08-15 |  | DONE | Receive ,INS | 2025-08-01: GatherAllitems; 2025-08-04: ASSY; 2025-08-05: ASSY; 2025-08-06: Clean INS,DIR; 2025-08-07: INS,DIR; 2025-08-08: INS,DIR; 2025-08-11: Pack; 2025-08-12: Pack; 2025-08-13: Ship
|  |  | DEBRIS COLLECTION LINER | RT-87876-0401-01-DD-C | 1 |  |  | DONE
|  |  | DEBRIS COLLECTION CAP | RT-87876-0402-01-DD-C | 1 |  |  | DONE
|  |  | DEBRIS COLLECTION TUNGSTEN LINER | RT-87876-0403-01-DD-C | 1 |  |  | DONE
|  |  | PRESSFIT SPIGOT | RT-87876-0404-01-DD-C | 1 |  |  | DONE
|  |  | OVERPACK CAN | RT-87876-0405-01-DD-D | 1 |  |  | INS | INS | 2025-07-28: Receive; 2025-07-29: Receive; 2025-07-30: INS,DIR; 2025-07-31: INS,DIR
|  |  | LOCKING PLATE (OVERPACK) | RT-87876-0406-01-DD-C | 1 |  |  | DONE
|  |  | DOOR | RT-87876-0407-01-DD-C | 1 |  |  | DONE
|  |  | COVER | RT-87876-0408-01-DD-C | 1 |  |  | DONE
|  |  | DOOR PLATE | RT-87876-0409-01-DD-C | 1 |  |  | DONE
|  |  | EXTENSION BLOCK | RT-87876-0410-01-DD-C | 1 |  |  | DONE
|  |  | TOP | RT-87876-0411-01-DD-C | 1 |  |  | DONE
|  |  | BODY | RT-87876-0412-01-DD-C | 1 |  |  | DONE
|  |  | LOCKING PLATE (FLASK) | RT-87876-0413-01-DD-C | 1 |  |  | DONE
72272 | 88308 | ATS-Corp | Tool Body | 700567102 | Body | 2025-05-13 |  | DONE |  | 2025-07-11: Parts machining by an external supplier CMC; 2025-07-14: Parts machining by an external supplier CMC; 2025-07-15: Parts machining by an external supplier CMC; 2025-07-16: Parts machining by an external supplier CMC; 2025-07-17: Parts machining by an external supplier CMC; 2025-07-18: Parts machining by an external supplier CMC; 2025-07-21: Parts machining by an external supplier CMC; 2025-07-22: L-Etch MCR-12110-001-000005
72276 | RT98-87530-PN-R004 | Candu | Plunger Position Gauge Assy Tool | RT-87530-0112-1-GA-0 | 5 | 2025-07-06 | Awating Candu Release | DONE
|  |  | PLUNGER POSITION GAUGE BASE | RT-87530-0113-1-DD-2 | 1 |  |  | DONE
|  |  | GAUGE HOLDER HANDLE - PLUNGER | RT-87530-0140-1-DD-1 | 1 |  |  | DONE
|  |  | CALIBRATION PLATE | RT-87530-0115-1-DD-2 | 1 |  |  | DONE
72277 | RT98-87530-PN-R004 | Candu | Stem Position Gauge assy Tool | RT-87530-0116-1-GA-0 | 5 | 2025-07-06 | Awating Candu Release | DONE
|  |  | STEM POSITION GAUGE BASE | RT-87530-0117-1-DD-2 | 1 |  |  | DONE
|  |  | GAUGE HOLDER HANDLE - STEM | RT-87530-0141-1-DD-1 | 1 |  |  | DONE
|  |  | CALIBRATION PLATE | RT-87530-0115-1-DD-2 | 1 |  |  | DONE
72278 | RT79-88030-PN-R001-R.1 | Candu | Eddy Current Spacer Detection Trough | RT-88030-0250-1-GA-D | 2 | 2025-08-27 | Awating updated scheduled from Eddyfi | Receive,INS | Receive,INS | 2025-10-22: Assembly; 2025-10-23: Assembly; 2025-10-24: INS; 2025-10-27: INS; 2025-10-28: INS; 2025-10-29: DIR; 2025-10-30: DIR; 2025-10-31: DIR; 2025-11-03: DIR; 2025-11-04: DIR
|  |  | ANGLE WELDMENT | RT-88030-0251-1-DD-C | 1 |  |  | DEBURR | DEBURR
|  |  | PAD | RT-88030-0252-1-DD-C | 2 |  |  | Waterjet | Waterjet
|  |  | MODIFIED PIPE STAND | RT-88030-0253-1-DD-D | 1 |  |  | Fit,Tack,weld | Fit,Tack,weld | 2025-08-04: Deburr; 2025-08-05: INS; 2025-08-06: INS
72279 | RT98-88030-PN-R001- R.1 | Candu | Eddy Current Spacer Detection Trough | RT-88030-0250-1-GA-D | 2 | 2025-08-27 | Awating updated scheduled from Eddyfi | Receive,INS |  | 2025-10-22: Assembly; 2025-10-23: Assembly; 2025-10-24: INS; 2025-10-27: INS; 2025-10-28: INS; 2025-10-29: DIR; 2025-10-30: DIR; 2025-10-31: DIR; 2025-11-03: DIR; 2025-11-04: DIR
|  |  | ANGLE WELDMENT | RT-88030-0251-1-DD-C | 1 |  |  | DEBURR | DEBURR
|  |  | PAD | RT-88030-0252-1-DD-C | 2 |  |  | Waterjet | Waterjet
|  |  | MODIFIED PIPE STAND | RT-88030-0253-1-DD-D | 1 |  |  | Fit,Tack,weld | Fit,Tack,weld | 2025-08-04: Deburr; 2025-08-05: INS; 2025-08-06: INS
72280 | RT98-87590-PN-R007 | Candu | Mockup LWTF Trolley | RT-87640-70300-000-1-GA-E | 1 | 2025-08-15 | 2025-09-08 | Doc |  | 2025-10-22: Doc; 2025-10-23: Doc; 2025-10-24: Doc
|  |  | LWTF MOCK-UP TROLLEY FRAME ASSY | RT-87640-70300-001-1-DD-E/RT-87640-70300-001-2-DD-E | 1 |  |  | DONE
|  |  | Square Tube 1 | RT-87640-70300-002-DD-B |  |  |  | DONE
|  |  | Center Beam | RT-87640-72150-001-1-DD-B |  |  |  | DONE
|  |  | Short Beam | RT-87640-72150-002-1-DD-B |  |  |  | DONE
|  |  | Wheel Gusset | RT-87640-72150-003-1-DD-B |  |  |  | DONE
|  |  | Access Door | RT-87640-72150-004-1-DD-B |  |  |  | DONE
|  |  | Trolley Frame | RT-87640-72150-005-1-DD-B |  |  |  | DONE
|  |  | W-Block spacer plate | RT-87640-72150-006-1-DD-B |  |  |  | DONE
|  |  | Sound Alarm Mounting Plate | RT-87640-72150-008-1-DD-B |  |  |  | DONE
|  |  | Long Beam | RT-87640-72150-009-1-DD-B |  |  |  | DONE
|  |  | Lifting Block | RT-87640-72150-010-1-DD-B |  |  |  | DONE
|  |  | Bumper Mount Type 1 | RT-87640-72150-012-1-DD-B |  |  |  | DONE
|  |  | LWTF Locating Pin | RT-87640-72150-013-1-DD-B |  |  |  | DONE
|  |  | SF Front Locator Plate | RT-87640-72150-016-1-DD-B |  |  |  | DONE
|  |  | SF Rear Locator Plate | RT-87640-72150-018-1-DD-B |  |  |  | DONE
|  |  | Asafety bumper | RT-87640-72150-019-1-DD-B |  |  |  | DONE
|  |  | LWTF Front Guide | RT-87640-72150-020-1-DD-B |  |  |  | DONE
|  |  | Coupling Shaft | RT-87640-72150-021-1-DD-B |  |  |  | DONE
|  |  | Coupling Y-Plate | RT-87640-72150-022-1-DD-B |  |  |  | DONE
|  |  | Coupling X-Plate | RT-87640-72150-023-1-DD-B |  |  |  | DONE
|  |  | Locate Plate-SWTF | RT-87640-72150-024-1-DD-B |  |  |  | DONE
|  |  | Shuttle Flask Pin | RT-87640-72150-025-1-DD-B |  |  |  | DONE
|  |  | SF Side Locator | RT-87640-72150-026-1-DD-B |  |  |  | DONE
|  |  | SF Back Locator | RT-87640-72150-027-1-DD-B |  |  |  | DONE
|  |  | LWTF FRONT PIN PLATE | RT-87640-72150-011-1-DD-D | 1 |  | ★Nickel | DONE
|  |  | LWTF REAR PIN PLATE | RT-87640-72150-014-1-DD-D | 1 |  | ★Nickel | DONE
|  |  | Front Shim | RT-87640-72150-028-1-DD-B | 2 |  |  | DONE
|  |  | LWTF Front Block | RT-87640-72150-030-1-DD-D | 1 |  | ★Nickel | DONE | DEBURR
|  |  | LWTF REAR SUPPORT PIN SHIM | RT-87640-72150-038-1-DD-B | 1 |  |  | DONE
|  |  | LWTF REAR SUPPORT SHIM | RT-87640-72150-039-1-DD-B | 1 |  |  | DONE
|  |  | LATCH MOUNT BRACKET C SIDE | RT-87640-70300-020-1-DD-D | 1 |  |  | DONE
|  |  | LATCH MOUNT BRACKET A SIDE | RT-87640-70300-021-1-DD-D | 1 |  |  | DONE
|  |  | JACK SCREW MOUNTING PLATE-C SIDE | RT-87640-72150-102-1-DD-B | 1 |  |  | DONE
|  |  | Arm A side | RT-87640-72150-093-1-DD-D | 1 |  |  | DONE
|  |  |  | RT-87640-72150-094-1-DD-B | 2 |  |  | DONE
|  |  | Torque-A side | RT-87640-72150-095-1-DD-D | 1 |  |  | DONE
|  |  | Arm C side | RT-87640-72150-100-1-DD-D | 1 |  |  | DONE
|  |  | Torque-C side | RT-87640-72150-101-1-DD-D | 1 |  |  | DONE
|  |  | Flag Spacer | RT-87640-72150-098-1-DD-B | 2 |  |  | DONE
|  |  | JACK SCREW MOUNTING PLATE-A SIDE | RT-87640-72150-096-1-DD-B | 1 |  |  | DONE
|  |  | Jack Screw Mount Block | RT-87640-72150-097-1-DD-B | 2 |  |  | DONE
|  |  | Flag | RT-87640-72150-099-1-DD-B | 2 |  |  | DONE
|  |  | LWTF Locating Pin | RT-87640-72150-013-1-DD-B | 2 |  |  | DONE
|  |  | ID Tag-A Side Latch | RT-87640-72150-103-1-DD-B | 1 |  |  | DONE
|  |  | ID Tag-C Side Latch | RT-87640-72150-104-1-DD-B | 1 |  |  | DONE
|  |  | ID Tag-Orientation LWTF | RT-87640-72150-082-1-DD-B | 6 |  |  | DONE
|  |  | ID Tag-Assembly 6 | RT-87640-72150-079-1-DD-B | 1 |  |  | DONE
|  |  | ID Tag-Assembly 5 | RT-87640-72150-078-1-DD-B | 1 |  |  | DONE
72284 | 88243- Rev.14 | ATS-Corp | Camera Holder | MCR-15300-003-107000-00-GA-E | 1 | 2025-05-16 | ★fixing | DONE |  | 2025-07-08: DEBURR
|  |  | Flange | MCR-15300-003-107000-02-DD-B | 1 |  |  | DONE
|  |  | Flange | MCR-15300-003-107002-02-DD-B | 1 |  |  | DONE | DEBURR
|  |  | Tab | MCR-15300-003-107005-02-DD-B | 2 |  |  | DONE
|  |  | Clamp Tab | MCR-15300-003-107003-01-DD-B | 2 |  |  | DONE
|  |  | Switch Tab | MCR-15300-003-107004-01-DD-B | 1 |  |  | DONE
|  |  | Support Tube | MCR-15300-003-107001-01-DD-B | 1 |  |  | DONE
72286 | 88243- Rev.14 | ATS-Corp | Middle Vacuum Tube Weldment | MCR-15300-003-102000-00-GA-C | 1 | 2025-05-27 |  | DONE
72290 | 88243- Rev.14 | ATS-Corp | Vacuum Tube With Flange | MCR-15300-003-110004-01-DD-C | 1 | 2025-05-16 |  | DONE
72295 | RT79-79113-PN-R001-R.1 | Candu | Beam LWTF Spreader Beam | 59RF-79113-9093-1-DD-B | 3 | 2025-07-16 |  | DONE |  | 2025-06-26: Clean; 2025-07-25: Paint; 2025-07-28: Clean INS; 2025-07-29: INS
72297 |  | Bombardier | BA Trench Cover | Sketch | 15 | 2025-04-28
72317 | 147-31972-PN-R072 | Candu | Drive & Index Motor Housing | 147-31972-0153-01-DD-B | 4 | 2025-08-14 |  | DONE |  | 2025-07-15: TURN; 2025-07-28: Mill; 2025-07-29: Mill; 2025-07-30: Mill; 2025-07-31: Mill; 2025-08-01: Deburr; 2025-08-04: INS,DIR; 2025-08-05: INS,DIR; 2025-08-06: Pack; 2025-08-07: Pack
72318 | 147-31972-PN-R072 | Candu | Motor Drive Coupler | 147-31972-0163-01-DD-C | 4 | 2025-08-14 | ★Gear Cut | Gear Cut |  | 2025-07-07: TURN; 2025-07-28: Mill; 2025-07-29: Mill; 2025-07-30: Deburr; 2025-07-31: INS,DIR; 2025-08-01: INS,DIR; 2025-08-04: Gearcut@truegear; 2025-08-05: Gearcut@truegear; 2025-08-06: Gearcut@truegear; 2025-08-07: Gearcut@truegear; 2025-08-08: Gearcut@truegear; 2025-08-11: Gearcut@truegear; 2025-08-12: Gearcut@truegear; 2025-08-13: Receive; 2025-08-14: INS,DIR; 2025-08-15: INS,DIR; 2025-08-18: Pack; 2025-08-19: Pack; 2025-09-02: Gear Cut; 2025-09-03: Gear Cut; 2025-09-04: Gear Cut; 2025-09-05: Gear Cut; 2025-09-08: Gear Cut; 2025-09-09: Gear Cut; 2025-09-10: Gear Cut; 2025-09-11: Gear Cut; 2025-09-12: Gear Cut; 2025-09-13: Gear Cut; 2025-09-16: Gear Cut; 2025-09-17: Gear Cut; 2025-09-18: Gear Cut; 2025-09-19: Receive,INS; 2025-09-22: INS,DIR; 2025-09-23: INS,DIR; 2025-09-24: INS,DIR; 2025-09-25: INS,DIR; 2025-09-26: INS,DIR; 2025-09-29: Pack; 2025-09-30: Ship
72319 | 147-31972-PN-R072 | Candu | Ball Joint Socket | 147-31972-0181-01-DD-C | 4 | 2025-08-14 | ★EDM | INS | CUT | 2025-07-25: Heat Treat M/C; 2025-07-28: Heat Treat M/C; 2025-07-29: Heat Treat M/C; 2025-07-30: Heat Treat M/C; 2025-07-31: Heat Treat M/C; 2025-08-01: Heat Treat M/C; 2025-08-04: Heat Treat M/C; 2025-08-08: Receive; 2025-08-11: TURN; 2025-08-12: TURN; 2025-08-13: Mill; 2025-08-14: Mill; 2025-08-25: Drill; 2025-08-26: Drill; 2025-08-27: Deburr; 2025-08-28: INS; 2025-08-29: INS; 2025-09-01: INS; 2025-09-02: INS; 2025-09-03: EDM; 2025-09-04: EDM; 2025-09-05: EDM; 2025-09-08: EDM; 2025-09-09: EDM; 2025-09-10: EDM; 2025-09-11: EDM; 2025-09-12: Receive,INS; 2025-09-13: INS,DIR; 2025-09-16: INS,DIR; 2025-09-17: INS,DIR; 2025-09-18: INS,DIR; 2025-09-19: INS,DIR; 2025-09-22: Pack; 2025-09-23: Ship
72320 | 147-31972-PN-R072 | Candu | Ball Joint Knuckle | 147-31972-0182-01-DD-C | 4 | 2025-08-14 |  | INS | CUT | 2025-08-22: Turn; 2025-08-25: Drill; 2025-08-26: Drill; 2025-08-27: Mill; 2025-08-28: INS,DIR; 2025-08-29: INS,DIR; 2025-09-01: INS,DIR; 2025-09-02: INS,DIR; 2025-09-03: Pack; 2025-09-04: Ship
72321 | 147-31972-PN-R072 | Candu | Push Tube Ball Joint Knuckle | 147-31972-0241-01-DD-C | 4 | 2025-08-14 |  | INS | CUT | 2025-08-22: Turn; 2025-08-25: Drill; 2025-08-26: Drill; 2025-08-27: Mill; 2025-08-28: INS,DIR; 2025-08-29: INS,DIR; 2025-09-01: INS,DIR; 2025-09-02: INS,DIR; 2025-09-03: Pack; 2025-09-04: Ship
72322 | 147-31972-PN-R072 | Candu | Ball Joint Socket | 147-31972-0242-01-DD-C | 4 | 2025-08-14 | ★EDM Change the material | INS |  | 2025-07-23: Heat Treat M/C; 2025-07-24: Heat Treat M/C; 2025-07-25: Heat Treat M/C; 2025-07-28: Heat Treat M/C; 2025-07-29: Heat Treat M/C; 2025-07-30: Heat Treat M/C; 2025-07-31: Heat Treat M/C; 2025-08-08: Receive; 2025-08-11: Turn; 2025-08-12: Turn; 2025-08-22: Mill; 2025-08-25: Mill; 2025-08-26: Mill; 2025-08-27: Mill; 2025-08-28: Deburr; 2025-08-29: INS; 2025-09-01: INS; 2025-09-02: INS; 2025-09-03: EDM; 2025-09-04: EDM; 2025-09-05: EDM; 2025-09-08: EDM; 2025-09-09: EDM; 2025-09-10: EDM; 2025-09-11: EDM; 2025-09-12: Receive,INS; 2025-09-13: INS,DIR; 2025-09-16: INS,DIR; 2025-09-17: INS,DIR; 2025-09-18: INS,DIR; 2025-09-19: INS,DIR; 2025-09-22: Pack; 2025-09-23: Ship
72324 | RT79-87250-PN-R004 | Candu | Carriage Mock-up HWT | RT-87250-0700-01-GA-E | 2 | 2025-08-29 |  | CONREX | Receive,INS | 2025-08-06: CONREX; 2025-08-07: CONREX; 2025-08-08: CONREX; 2025-08-11: CONREX; 2025-08-12: CONREX; 2025-08-13: CONREX; 2025-08-14: CONREX
|  |  | BOTTOM CARRIAGE WELDMENT | RT-87250-0701-01-GA-E | 1
|  |  | BEARING BLOCK MOUNTING ASSEMBLY | RT-87250-0703-01-GA-D | 2 |  | ★外注あり | Stress Reliese |  | 2025-07-10: Stress Reliese; 2025-07-11: Stress Reliese; 2025-07-14: Stress Reliese; 2025-07-15: Stress Reliese; 2025-07-16: Stress Reliese; 2025-07-17: Stress Reliese; 2025-07-18: Stress Reliese; 2025-07-21: Stress Reliese; 2025-07-22: Fit, Tack, Weld
|  |  | BEARING BLOCK MOUNTING PLATE | RT-87250-0702-01-DD-C | 1 |  | ★Black Oxide | INS | Deburr | 2025-08-28: INS; 2025-09-02: Black Oxide; 2025-09-03: Black Oxide; 2025-09-04: Black Oxide; 2025-09-05: Black Oxide; 2025-09-08: Black Oxide; 2025-09-09: Black Oxide; 2025-09-10: Black Oxide; 2025-09-11: Receive,INS; 2025-09-12: INS,DIR; 2025-09-13: INS,DIR
|  |  | THREADED BLOCK | RT-87250-0704-01-DD-B | 4 |  |  | DONE
72326 |  | DJ Ind. | Valve to repair Worn Areas & Chrome | Sample | 1 | 2025-05-02
72327 |  | DJ Ind. | Plunger Valve to Repair by Sleeve | Sample | 1 | 2025-05-02
72328 |  | DJ Ind. | Hand Pump hone after chrome | Sample | 1 | 2025-05-02
72330 | RT79-87550-PN-R001-R.1 | Candu | Shell Installation Tool Assy | RT-87550-0145-01-GA-E | 1 | 2025-09-19 | ★外注あり | oeder sub parts |  | 2025-08-26: Receive,INS; 2025-08-27: Gather all items; 2025-08-28: ASSY; 2025-08-29: ASSY; 2025-09-01: Clean; 2025-09-02: Clean; 2025-09-03: Weigh; 2025-09-04: Weigh; 2025-09-05: L-Etch; 2025-09-08: L-Etch; 2025-09-09: INS; 2025-09-10: INS; 2025-09-11: Doc; 2025-09-12: Doc; 2025-09-13: Pack; 2025-09-16: Pack; 2025-09-17: Ship
|  |  | SQUARE TUBE WELDMENT | RT-87550-0146-01-GA-C | 1 |  |  | Deburr |  | 2025-08-06: Deburr; 2025-08-07: INS,DIR; 2025-08-08: INS,DIR
|  |  | CONNECTOR ROD/HOOK WELDMENT | RT-87550-0147-01-DD-C | 1 |  |  | DONE
|  |  | HANDLE | RT-87550-0148-01-DD-C | 1 |  |  | DONE
|  |  | MODIFIED HAND KNOB | RT-87550-0149-01-DD-C | 1 |  |  | DONE
72331 | RT98-87550-PN-R004-R.1 | Candu | Shell Installatin Tool Assy | RT-87550-0145-01-GA-E | 1 | 2025-09-19 | ★外注あり | oeder sub parts
|  |  | SQUARE TUBE WELDMENT | RT-87550-0146-01-GA-C | 1 |  |  | Deburr |  | 2025-07-04: Deburr
|  |  | CONNECTOR ROD/HOOK WELDMENT | RT-87550-0147-01-DD-D | 1 |  |  | DONE
|  |  | HANDLE | RT-87550-0148-01-DD-C | 1 |  |  | DONE
|  |  | MODIFIED HAND KNOB | RT-87550-0149-01-DD-C | 1 |  |  | DONE
72349 | 88439- Rev.1 | ATS-Corp | Torsion Spring | NK38-DRAW-31935-10569-0001 | 21 | 2025-07-17 |  | DONE
72362 | RT79-87110-PN-R010 | Candu | Ring Rolled Joint Centering Ring | RT-87110-0174-01-DD-2 | 4 | 2025-07-11 |  | DONE
72364 | 280101251 | Kinectrics | Flange F/I Fit and Weld per Dwg | NPD0059-7-WLD-1407 | 1 | 2025-05-30
72365 | 88502- Rev.7 | ATS-Corp | North Sole Plate | 700589434 | 1 | 2025-09-01 |  | Ship |  | 2025-07-10: DEBURR
72366 | 88502- Rev.7 | ATS-Corp | South Sole Plate | 700589302 | 1 | 2025-09-01 | ★外注あり(済) | Ship |  | 2025-07-04: Fit,Tack,Weld; 2025-07-29: Mill; 2025-07-31: Deburr; 2025-08-01: INS; 2025-08-04: INS; 2025-08-05: MPI Perfection; 2025-08-06: MPI Perfection; 2025-08-07: MPI Perfection; 2025-08-08: MPI Perfection; 2025-08-11: MPI Perfection; 2025-08-12: MPI Perfection; 2025-08-13: MPI Perfection; 2025-08-14: Stress Relieve,Sand Blast Conrex; 2025-08-15: Stress Relieve,Sand Blast Conrex; 2025-08-18: Stress Relieve,Sand Blast Conrex; 2025-08-19: Stress Relieve,Sand Blast Conrex; 2025-08-20: Mill; 2025-08-21: Deburr; 2025-08-22: Deburr; 2025-08-25: Stamp; 2025-08-26: INS,DIR; 2025-08-27: INS,DIR; 2025-08-28: INS,DIR; 2025-08-29: INS,DIR; 2025-09-01: INS,DIR; 2025-09-02: Paint; 2025-09-03: Paint; 2025-09-04: Pack; 2025-09-05: Pack; 2025-09-08: Ship
72367 | RT98-87000-PN-R012 | Candu | Pitch Yaw Mounting Frame Tool | RT-87250-74016-000-1-GA-E | 4 | 2026-07-29
|  |  | Stop Block | RT-87250-74016-091-1-DD-B | 16 |  |  | DONE
|  |  | Chain Retainer Plate | RT-87250-74016-12-1-DD-B | 72 |  |  | DRILL |  | 2025-07-16: DRILL
|  |  | Yaw Push Pin Mount | RT-87250-74016-008-1-DD-D | 4 |  | ★外注あり | INS |  | 2025-07-10: DEBURR; 2025-07-25: INS; 2025-07-28: Nickelplate CMC; 2025-07-29: Nickelplate CMC; 2025-07-30: Nickelplate CMC; 2025-07-31: Nickelplate CMC; 2025-08-01: Nickelplate CMC; 2025-08-04: Nickelplate CMC; 2025-08-05: Nickelplate CMC; 2025-08-06: Receive,INS; 2025-08-07: INS,DIR; 2025-08-08: INS,DIR
|  |  | Idler Mount Sprocket Mount | RT-87250-74016-004-1-DD-D | 48 |  |  | Machine |  | 2025-07-11: CUT; 2025-07-30: Machine
|  |  | Chain Connection Link | RT-87250-74016-011-1-DD-D | 36 |  |  | Machine |  | 2025-07-23: Machine; 2025-07-24: Machine; 2025-07-25: Machine
|  |  | Roller Mount 2 | RT-87250-74016-089-1-DD-B | 4 |  |  | INS |  | 2025-07-11: INS
|  |  | Handle Drive Lock | RT-87250-74016-093-1-DD-B | 48 |  |  | Cut |  | 2025-07-14: Cut
|  |  | Cam Roller Mount | RT-87250-74016-006-1-DD-B | 8 |  | ★外注あり | CUT |  | 2025-07-10: CUT
72368 | RT98-87000-PN-R012 | Candu | Pitch Yaw Mounting Table | RT-87250-74010-000-1-GA-E | 4 | 2026-07-29
72373 | RT98-87590-PN-R006 | Candu | EFSF Removal Tool (RT-7591-000-PRT) | RT-87590-70000-000-1-GA-E | 3 | 2026-10-09
72380 | 280101422 | Kinectrics | BL Mockup Elbolet Interface Plate | K-402310-09-WLD-5300-004 | 1 | 2025-06-05 |  | DONE | Mill | 2025-08-19: Debur
72381 | 30-35385-PN-R007 | Candu | Cyl. Mtg Plate- F/I for Zinc Plating | NK30-DCN-35385-0022-001 | 1 | 2025-05-22 |  | DONE |  | 2025-07-14: Parts machining by an external supplier M&M; 2025-07-15: Parts machining by an external supplier M&M; 2025-07-16: Parts machining by an external supplier M&M; 2025-07-17: Parts machining by an external supplier M&M; 2025-07-18: Parts machining by an external supplier M&M; 2025-07-21: Parts machining by an external supplier M&M; 2025-07-22: Parts machining by an external supplier M&M; 2025-07-23: Receive; 2025-07-24: Pack; 2025-07-25: Pack
72381 | 30-35385-PN-R007 | Candu | Spacer Rod - F/I for Zinc Plating | NK30-DBN-35385-0023-001 | 4 | 2025-05-22 |  | DONE |  | 2025-07-14: Parts machining by an external supplier M&M; 2025-07-15: Parts machining by an external supplier M&M; 2025-07-16: Parts machining by an external supplier M&M; 2025-07-17: Parts machining by an external supplier M&M; 2025-07-18: Parts machining by an external supplier M&M; 2025-07-21: Parts machining by an external supplier M&M; 2025-07-22: Parts machining by an external supplier M&M; 2025-07-23: Receive; 2025-07-24: Pack; 2025-07-25: Pack
72381 | 30-35385-PN-R007 | Candu | Solid Ring- F/I for Zinc Plating | NK30-DBN-35385-0025-001 | 1 | 2025-05-22 |  | DONE |  | 2025-07-14: Parts machining by an external supplier M&M; 2025-07-15: Parts machining by an external supplier M&M; 2025-07-16: Parts machining by an external supplier M&M; 2025-07-17: Parts machining by an external supplier M&M; 2025-07-18: Parts machining by an external supplier M&M; 2025-07-21: Parts machining by an external supplier M&M; 2025-07-22: Parts machining by an external supplier M&M; 2025-07-23: Receive; 2025-07-24: Pack; 2025-07-25: Pack
72381 | 30-35385-PN-R007 | Candu | Cylinder Saddle - F/I for Zinc Plating | NK30-DBN-35385-0027-001 | 1 | 2025-05-22 |  | DONE |  | 2025-07-14: Parts machining by an external supplier M&M; 2025-07-15: Parts machining by an external supplier M&M; 2025-07-16: Parts machining by an external supplier M&M; 2025-07-17: Parts machining by an external supplier M&M; 2025-07-18: Parts machining by an external supplier M&M; 2025-07-21: Parts machining by an external supplier M&M; 2025-07-22: Parts machining by an external supplier M&M; 2025-07-23: Receive; 2025-07-24: Pack; 2025-07-25: Pack
72381 | 30-35385-PN-R007 | Candu | Split Ring- F/I for zinc Plating | NK30-DCN-35385-0028-001 | 1 | 2025-05-22 |  | DONE |  | 2025-07-14: Parts machining by an external supplier M&M; 2025-07-15: Parts machining by an external supplier M&M; 2025-07-16: Parts machining by an external supplier M&M; 2025-07-17: Parts machining by an external supplier M&M; 2025-07-18: Parts machining by an external supplier M&M; 2025-07-21: Parts machining by an external supplier M&M; 2025-07-22: Parts machining by an external supplier M&M; 2025-07-23: Receive; 2025-07-24: Pack; 2025-07-25: Pack
72386 | 4500938848 | Westinghouse | M10-1.5mm x 25mm Screw-Alloy 625 | EVR-MS01-T3-152E2 | 200 | 2025-07-17 |  | DONE
72388 | 211246771 | Buffalo | Z-Axis Carriage- F/I Casting | 742637 | 1 | 2025-06-15 | ★Check to Gus | Free Issue
72395 | RT79-87630-PN-R005 | Candu | VRS Manual Retrieval Tool | RT-87630-71254-1000-1-GA-D | 1 | 2025-08-27
|  |  | VRS Manual Retrieval Tool - Filter | RT-87630-71254-1000-1-GA-D-Item#1 004 | 4 |  |  | DONE
|  |  | IPEX .5 BUSHING | RT-87630-71254-1001-1-DD-D | 15 | ★Hard Anodize |  | Receive,INS |  | 2025-08-27: Hard Anodize; 2025-08-28: Receive,INS; 2025-08-29: INS,DIR; 2025-09-01: INS,DIR
|  |  | IPEX .75 BUSHING | RT-87630-71254-1002-1-DD-D | 15 | ★Hard Anodize |  | Receive,INS |  | 2025-08-27: Hard Anodize; 2025-08-28: Receive,INS; 2025-08-29: INS,DIR; 2025-09-01: INS,DIR
|  |  | IPEX 1.0 BUSHING | RT-87630-71254-1003-1-DD-D | 15 | ★Hard Anodize |  | Receive,INS |  | 2025-08-27: Hard Anodize; 2025-08-28: Receive,INS; 2025-08-29: INS,DIR; 2025-09-01: INS,DIR
|  |  | .5 SCREEN | RT-87630-71254-1004-1-DD-B |  |  | ★Ask Gus | 進捗なし 放置？
|  |  | .75 SCREEN | RT-87630-71254-1005-1-DD-B |  |  | ★Ask Gus | 進捗なし 放置？
|  |  | 1.0 SCREEN | RT-87630-71254-1006-1-DD-B |  |  | ★Ask Gus | 進捗なし 放置？
|  |  | MICRO FIBER CLOTH | RT-87630-71254-1007-1-DD-B
|  |  | FOAM DISC | RT-87630-71254-1008-1-DD-B
|  |  | POKER STICK | RT-87630-71254-1009-1-DD-D | 4 |  |  | Deburr |  | 2025-07-15: CUT; 2025-07-25: Deburr
|  |  | POKER STICK - TUBING | RT-87630-71254-1010
|  |  | POKER STICK - CAP | RT-87630-71254-1011
|  |  | FILTER DELIVERY TOOL | RT-87630-71254-1012-1-DD-D | 1 |  |  | Deburr |  | 2025-07-10: Cut; 2025-07-31: Turn; 2025-08-04: Weld; 2025-08-18: Deburr; 2025-08-19: INS; 2025-08-20: Paint; 2025-08-21: Paint; 2025-08-22: L-Etch; 2025-08-25: L-Etch
|  |  | FILTER DELIVERY TOOL FLANGE | RT-87630-71254-1020-1-DD-B | 2 |  |  | DONE |  | 2025-07-10: DEBURR; 2025-07-23: INS
|  |  | FILTER DELIVERY TOOL MID FLANGE | RT-87630-71254-1021-1-DD-B | 1 |  |  | DONE
|  |  | FILTER DELIVERY TOOL GUSSET | RT-87630-71254-1022-1-DD-B | 2 |  |  | DONE |  | 2025-07-09: Waterjet cut
|  |  | FILTER DELIVERY TOOL TROUGH | RT-87630-71254-1023-1-DD-B | 1 |  |  | DONE |  | 2025-06-19: DEBURR
|  |  | FILTER DELIVERY TOOL END PLATE | RT-87630-71254-1024-1-DD-B | 2 |  |  | DONE
|  |  | DELIVERY TOOL TUBE | RT-87630-71254-1030 |  |  |  | DONE
|  |  | TOOL BOX A TAG | RT-87630-71254-1013-1-DD-B |  |  |  | Mill |  | 2025-08-08: Mill; 2025-08-11: Deburr; 2025-08-12: INS,DIR; 2025-08-13: INS,DIR
|  |  | TOOL BOX B TAG | RT-87630-71254-1014-1-DD-B |  |  |  | Mill |  | 2025-08-06: Mill; 2025-08-07: Deburr; 2025-08-08: INS,DIR; 2025-08-11: INS,DIR
|  |  | REDUCER-VACUUM TUBE CONNECTION | RT-87630-71254-1015-1-DD-D
|  |  | 1 IN NIPPLE-REDUCER | RT-87630-71254-1026-1-DD-B | 1 |  |  | Cut |  | 2025-07-29: Cut; 2025-07-30: Turn; 2025-07-31: Turn; 2025-08-01: Deburr; 2025-08-04: INS,DIR; 2025-08-05: INS,DIR
|  |  | 1.5 IN NIPPLE-REDUCER | RT-87630-71254-1044-1-DD-B
|  |  | FOOT-REDUCER | RT-87630-71254-1045-1-DD-B | 1 |  |  | Cut
|  |  | NOZZLE DELIVERY TOOL | RT-87630-71254-1016-1-DD-B | 1 |  | ★外注あり | Fit,Tack,Weld |  | 2025-07-14: TURN; 2025-07-28: Fit,Tack,Weld; 2025-07-31: Deburr; 2025-08-01: INS,DIR; 2025-08-04: INS,DIR; 2025-08-05: Visual Examination Perfection; 2025-08-06: Visual Examination Perfection; 2025-08-07: Visual Examination Perfection; 2025-08-08: Visual Examination Perfection; 2025-08-11: Visual Examination Perfection; 2025-08-12: Visual Examination Perfection; 2025-08-13: Visual Examination Perfection; 2025-08-14: Paint; 2025-08-15: Paint; 2025-08-18: L-Etch; 2025-08-19: L-Etch
|  |  | NOZZLE WAND | RT-87630-71254-1017-1-DD-B | 1 |  |  | Receive |  | 2025-08-26: Cut; 2025-08-27: Turn; 2025-08-28: Turn; 2025-08-29: Drill; 2025-09-01: Drill; 2025-09-02: Deburr; 2025-09-03: INS,DIR; 2025-09-04: INS,DIR
|  |  | GARTER SPRING COLLECTION TRAY | RT-87630-71254-1018-1-DD-D | 1 |  |  | Deburr |  | 2025-07-10: Cut; 2025-07-31: Turn; 2025-08-18: Deburr; 2025-08-19: INS; 2025-08-20: Paint; 2025-08-21: Paint; 2025-08-22: L-Etch; 2025-08-25: L-Etch
|  |  | FILTER DELIVERY TOOL FLANGE | RT-87630-71254-1020-1-DD-B
|  |  | DELIVERY TOOL TUBE | RT-87630-71254-1030
|  |  | GARTER SPRING TRAY BOTTOM PLATE | RT-87630-71254-1031-1-DD-B
|  |  | GARTER SPRING TRAY SIDE WALL | RT-87630-71254-1032-1-DD-B | 1 |  |  | DEBURR |  | 2025-06-19: DEBURR
|  |  | GARTER SPRING TRAY GUSSET | RT-87630-71254-1033-1-DD-B | 2 |  |  | DONE
|  |  | CAMERA CLAMP ADAPTER | RT-87630-71254-1019-1-DD-B
|  |  | FILTER DELIVERY TOOL FLANGE | RT-87630-71254-1020-1-DD-B
|  |  | FILTER DELIVERY TOOL MID FLANGE | RT-87630-71254-1021-1-DD-B
|  |  | FILTER DELIVERY TOOL GUSSET | RT-87630-71254-1022-1-DD-B
|  |  | FILTER DELIVERY TOOL TROUGH | RT-87630-71254-1023-1-DD-B
|  |  | FILTER DELIVERY TOOL END PLATE | RT-87630-71254-1024-1-DD-B
|  |  | FLEX TUBE-FILTER TO REDUCER | RT-87630-71254-1025-1-DD-B
|  |  | 1 IN NIPPLE-REDUCER | RT-87630-71254-1026-1-DD-B
|  |  | VACUUM NOZZLE BLOCK | RT-87630-71254-1027-1-DD-B
|  |  | NOZZLE DELIVERY TOOL SCREW | RT-87630-71254-1028-1-DD-B | 1 |  |  | ★Need to fix アラート！ |  | 2025-07-14: TURN
|  |  | NOZZLE DELIVERY TOOL TUBE | RT-87630-71254-1029
|  |  | DELIVERY TOOL TUBE | RT-87630-71254-1030
|  |  | GARTER SPRING TRAY BOTTOM PLATE | RT-87630-71254-1031-1-DD-B | 1 |  |  | DEBURR |  | 2025-06-19: DEBURR
|  |  | GARTER SPRING TRAY SIDE WALL | RT-87630-71254-1032-1-DD-B
|  |  | GARTER SPRING TRAY GUSSET | RT-87630-71254-1033-1-DD-B
|  |  | VACUUM FILTER INLET NOZZLE ASSEMBLY | RT-87630-71254-1034-1-DD-B
|  |  | VACUUM FILTER INLET NOZZLE | RT-87630-71254-1036-1-DD-B | 4
|  |  | VACUUM FILTER INLET FLANGE | RT-87630-71254-1037-1-DD-B | 4
|  |  | FILTER HOUSING | RT-87630-71254-1035-1-DD-E
|  |  | FILTER HOUSING CANISTER | RT-87630-71254-1038-1-DD-D
|  |  | FILTER HOUSING TUBE | RT-87630-71254-1039-1-DD-D
|  |  | FILTER HOUSING PIPE CAP | RT-87630-71254-1040-1-DD-B
|  |  | VACUUM FILTER INLET NOZZLE | RT-87630-71254-1036-1-DD-B
|  |  | VACUUM FILTER INLET FLANGE | RT-87630-71254-1037-1-DD-B
|  |  | FILTER HOUSING CANISTER | RT-87630-71254-1038-1-DD-D
|  |  | FILTER HOUSING TUBE | RT-87630-71254-1039-1-DD-D
|  |  | FILTER HOUSING PIPE CAP | RT-87630-71254-1040-1-DD-B
|  |  | FLEX TUBE-NOZZLE TO FILTER | RT-87630-71254-1041-1-DD-B
|  |  | VACUUM NOZZLE 2 | RT-87630-71254-1042-1-DD-D |  |  |  | Gather all items
|  |  | VACUUM NOZZLE BLOCK | RT-87630-71254-1027-1-DD-B
|  |  | NOZZLE TUBE | RT-87630-71254-1043-1-DD-B |  |  |  | Cut |  | 2025-07-08: Cut; 2025-08-04: Turn; 2025-08-05: Turn; 2025-08-06: Form; 2025-08-07: Form; 2025-08-08: Trim/Mill; 2025-08-11: Trim/Mill; 2025-08-12: Deburr; 2025-08-13: INS,DIR; 2025-08-14: INS,DIR
|  |  | NOZZLE TUBE | RT-87630-71254-1043-1-DD-B |  |  |  | Cut |  | 2025-07-08: Cut
|  |  | 1.5 IN NIPPLE-REDUCER | RT-87630-71254-1044-1-DD-B
|  |  | FOOT-REDUCER | RT-87630-71254-1045-1-DD-B
|  |  | HANDLE-STICKY STICK | RT-87630-71254-1046-1-DD-B
|  |  | GUIDE HANDLE-NOZZLE WAND | RT-87630-71254-1047-1-DD-B
|  |  | ID TAG - INSP & RETRIEVAL TOOLS | RT-87630-71254-1048-1-DD-B | 20 |  |  | Mill |  | 2025-08-18: Mill; 2025-08-19: Mill; 2025-08-20: Deburr; 2025-08-21: INS,DIR; 2025-08-22: INS,DIR
72396 | 88485- Rev.5 | ATS-Corp | Anchor Plate | NK38-DRAW-31935-10445-0001 | 1 | 2025-07-25 |  | Ship
72397 | 88485- Rev.5 | ATS-Corp | Measurement Station Anchor Plt | NK38-DRAW-31935-10465-0001 | 1 | 2025-07-25 |  | Ship |  | 2025-07-01: DEBURR; 2025-07-31: INS,DIR; 2025-08-01: INS,DIR; 2025-08-04: Pack; 2025-08-05: Pack; 2025-08-06: Ship
72398 | 88485- Rev.5 | ATS-Corp | Center Rod -Anchor Plate | NK38-DRAW-31935-10491-0001 | 1 | 2025-07-25 |  | Ship | Receive Release
72399 | 88485- Rev.5 | ATS-Corp | RH Guide Strip | NK38-DRAW-31935-10523-0001 | 1 | 2025-07-25 |  | Ship
72400 | 88485- Rev.5 | ATS-Corp | Slide Bar | NK38-DRAW-31935-10524-0001 | 1 | 2025-07-25 |  | Ship |  | 2025-07-07: INS; 2025-07-22: INS; 2025-07-31: Pack; 2025-08-01: Pack; 2025-08-04: Ship
72401 | 88485- Rev.5 | ATS-Corp | Guide | NK38-DRAW-31935-10552-0001 | 1 | 2025-07-25 | 2025-09-26 | DEBURR |  | 2025-07-03: DEBURR; 2025-07-31: INS; 2025-08-01: INS; 2025-08-04: Straighten; 2025-08-05: Straighten; 2025-08-06: Mill; 2025-08-07: Mill; 2025-08-08: Deburr; 2025-08-11: INS; 2025-08-12: INS; 2025-08-13: Straighten; 2025-08-14: Mill,Drill; 2025-08-15: Mill,Drill; 2025-08-18: Deburr; 2025-08-19: Straighten; 2025-08-20: INS,DIR; 2025-08-21: INS,DIR; 2025-08-22: Pack; 2025-08-25: Pack; 2025-08-26: Ship; 2025-09-22: Mill; 2025-09-23: Mill; 2025-09-24: Deburr; 2025-09-25: INS; 2025-09-26: Mill; 2025-09-29: Mill; 2025-09-30: Deburr; 2025-10-01: INS; 2025-10-02: Mill; 2025-10-03: Mill; 2025-10-06: Drill; 2025-10-07: Drill; 2025-10-08: Deburr; 2025-10-09: INS,DIR; 2025-10-10: INS,DIR; 2025-10-13: INS,DIR; 2025-10-14: INS,DIR; 2025-10-15: INS,DIR; 2025-10-16: Doc; 2025-10-17: Doc; 2025-10-20: Ship
72402 | 88485- Rev.5 | ATS-Corp | LH Guide Strip | NK38-DRAW-31935-10572-0001 | 1 | 2025-07-25 |  | Ship
72406 | 8423365- Rev.1 | ATS-Corp | MF Heatsing Liner-F/I to Modify | 700628267-F/I | 1 | 2025-06-11 |  | Complete M/E |  | 2025-07-14: Complete M/E; 2025-07-31: Deburr; 2025-08-01: INS,DIR; 2025-08-04: INS,DIR; 2025-08-05: Pack; 2025-08-06: Pack; 2025-08-07: Ship
72407 | 79-35217-PN-R004 | Candu | Deloro 60 Ring Only | XX-35217-3-1-DD-D | 2 | 2025-09-19 | ★外注あり | Machine Kennametal ★back in Sep | Machine Kennametal
72422 | RT79-79112-PN-R002 | Candu | Small Waste Transfer Flask | RT-79112-0300-01-GA-E | 1 | 2026-01-26
|  |  | Small flask body ASSY | RT-79112-0302-01-GA-D | 1 |  |  |  |  | 2025-11-07: Receive,INS; 2025-11-10: Gather all items; 2025-11-11: ASSY; 2025-11-12: ASSY; 2025-11-13: ASSY; 2025-11-14: INS; 2025-11-17: INS; 2025-11-18: Pack; 2025-11-19: Ship
|  |  | Lower Drawer ASSY | 59RT-79112-0082-01-GA-D | 1
|  |  | Bottom Gate can't bar weldment | RT-79112-0336-01-GA-E | 1
|  |  | Upper drawer ASSY | RT-79112-0061-01-GA-D | 1
|  |  | Upper drawer STOP (Left) | RT-79112-0060-01-DD-B | 1
|  |  | Upper drawer STOP (Right) | RT-79112-0098-01-DD-B | 1
|  |  | Junction box ASSY | RT-79112-0350-01-GA-B | 1
|  |  | Proximity switch ASSY | 59RT-79112-0104-01-DD-B | 4
|  |  | Wire Cover (Left) | 59RT-79112-0108-01-DD-B | 1
|  |  | Rack/Pinion Block ASSY(Right) | 59RT-79112-0099-01-GA-D | 1
|  |  | Rack/Pinion Block ASSY(Left) | 59RT-79112-0099-01-GA-D | 1
|  |  | Small and Large Waste Transfer flask shielding flapper block weldment | RT-79112-051-01-DD-E | 1
|  |  | Wire Cover (Right) | 59RT-79112-0108-01-DD-B | 1
|  |  | Lower Drawer (Machined) | RT-79112-0083-01-DD-E | 1
|  |  | Lower Drawer (Weldment) | RT-79112-0084-01-DD-B | 1 |  | ★Lead Pouring Integrity Test
|  |  | Base Plate | 59RT-79112-0085-01-DD-B | 1
|  |  | Side Plate-1 | 59RT-79112-0086-01-DD-B | 1
|  |  | Drawer Cover | 59RT-79112-0087-01-DD-B | 1
|  |  | Top Bar | 59RT-79112-0088-01-DD-B | 1
|  |  | Block | 59RT-79112-0089-01-DD-B | 2
|  |  | Back Plate | 59RT-79112-0090-01-DD-B | 1
|  |  | Front Plate | 59RT-79112-0091-01-DD-B | 1
|  |  | Lock Bar | 59RT-79112-0092-01-DD-B | 1
|  |  | End Plate | 59RT-79112-0093-01-DD-B | 1
|  |  | Lead seal plug | 59RT-79112-0031-01-DD-B | 12
|  |  | Side Plate-2 | 59RT-79112-0086-01-DD-B | 1
|  |  | Bar 1.75"DIA. X 2"LG. | 59RT-79112-0094-01-DD-B | 2
|  |  | Flask Cover (Weldment) | RT-79112-0336-01-GA-E | 1 |  | ★Lead Pouring Integrity Test
|  |  | Top Plate | 59RT-79112-0037-01-DD-B | 1
|  |  | Cover Drum | 59RT-79112-0038-01-DD-B | 1
|  |  | Top Seal plate (Top&Bottoms components) ASSY | RT-79112-0342-01-GA-C | 1
|  |  | Cover bar (Left) | RT-79112-0177-01-DD-C | 1
|  |  | Cover bar (Right) | RT-79112-0043-01-DD-C | 1
|  |  | Rear Plate | 59RT-79112-0044-01-DD-B | 1
|  |  | Bearing Rail (Left) | 59RT-79112-0045-01-DD-B | 1
|  |  | Bearing Rail (Right) | 59RT-79112-0046-01-DD-B | 1
|  |  | Lead Seal Plug | 59RT-79112-0031-01-DD-B | 4
|  |  | Container Index Pin | 59RT-79112-0178-01-DD-B | 1
|  |  | Block left | 59RT-79112-0048-01-DD-B | 1
|  |  | Block right | 59RT-79112-0049-01-DD-B | 1
|  |  | Hard stop | 59RT-79112-0050-01-DD-B | 1
|  |  | Back Plate | 59RT-79112-0051-01-DD-B | 2
|  |  | Index pin container | 59RT-79112-0052-01-DD-B | 1
|  |  | Lock Plug | 59RT-79112-0053-01-DD-B | 1
|  |  | Container Locating Rod | 59RT-79112-0054-01-DD-B | 1
|  |  | Switch casting | 59RT-79112-0055-01-DD-B | 2
|  |  | Upper lifting lug | 59RT-79112-0056-01-DD-B | 2
|  |  | Hoist Lifting Lug | 59RT-79112-0057-01-DD-B | 2
|  |  | Guide pipe | 59RT-79112-0058-01-DD-B | 2
|  |  |  | 59RT-79112-0036-01-GA-E | 1
|  |  | Small Waste Transfer Flask-Cover Bar Left | 59RT-79112-0177-01-DD-C | 1
|  |  | Cover Bar Right | 59RT-79112-0043-01-DD-C | 1
|  |  |  | RT-79112-0336-01-GA-E | 1
|  |  | Top Seal Plate-Top Component 1 | RT-79112-0342-01-GA-C | 1
|  |  | Top Seal Plate | RT-79112-0340-01-DD-C | 1
|  |  |  | 59RT-79112-0042-01-GA-C | 1
|  |  | Bottom Component 2 | 59RT-79112-0041-01-DD-C | 1
|  |  |  | RT-79112-0303-01-DD-E | 1
|  |  | Small Waste Transfer Flask-Small Flask Body(Weldment) | RT-79112-0309-01-DD-B 59RT-79112-0009-02-DD-B | 1 |  | ★Lead Pouring Integrity Test
|  |  | Top Bar | 59RT-79112-0010-01-DD-B | 1
|  |  | Inner Drum | 59RT-79112-0011-01-DD-B | 1
|  |  | Base Plate | 59RT-79112-0012-01-DD-B | 1
|  |  | Internal Plate | 59RT-79112-0013-01-DD-B | 1
|  |  | Rail Plate | 59RT-79112-0014-01-DD-B | 2
|  |  | Rear Plate | 59RT-79112-0015-01-DD-B | 1
|  |  | Bottom bar | 59RT-79112-0016-01-DD-B | 1
|  |  | Side plate | 59RT-79112-0017-01-DD-B | 2
|  |  | Base cap separator | 59RT-79112-0018-01-DD-B | 1
|  |  | Left pipe | 59RT-79112-0019-01-DD-B | 1
|  |  | Side Angle Plate（Left） | 59RT-79112-0020-01-DD-B | 1
|  |  | Side Angle Plate（Right） | 59RT-79112-0020-01-DD-B | 1
|  |  | Rear Angle Plate（Left） | 59RT-79112-0021-01-DD-B | 1
|  |  | Rear Angle Plate（Right） | 59RT-79112-0021-01-DD-B | 1
|  |  | Top Angle Plate（Left） | 59RT-79112-0022-01-DD-B | 1
|  |  | Top Angle Plate（Right） | 59RT-79112-0022-01-DD-B | 1
|  |  | Enclosure pltate | 59RT-79112-0023-01-DD-B | 1
|  |  | Front plate | 59RT-79112-0024-01-DD-B | 2
|  |  | Flask Lifting Bracket | 59RT-79112-0025-01-DD-B | 2
|  |  | Flask Body | 59RT-79112-0026-01-DD-B | 1
|  |  | Lifting Bracket Gusset | 59RT-79112-0027-01-DD-B | 8
|  |  | Back Bar | 59RT-79112-0028-01-DD-B | 1
|  |  | Lower Lifting Lug | 59RT-79112-0029-01-DD-B | 4
|  |  | Block | 59RT-79112-0030-01-DD-B | 2
|  |  | Lead seal Plug | 59RT-79112-0031-01-DD-B | 8
|  |  | Junction box support | 59RT-79112-0032-01-DD-B | 2
|  |  | Switch casting | 59RT-79112-0033-01-DD-B | 2
|  |  | container guide pad | 59RT-79112-0034-01-DD-B | 4
|  |  | pipe(Right) | 59RT-79112-0035-01-DD-B | 1
|  |  |  | RT-79112-0061-01-GA-D | 1
|  |  | Upper Drawer (Machined) | RT-79112-0062-01-DD-D | 1
|  |  | Upper Drawer (Weldment) | RT-79112-0072-01-DD-B | 1 |  | ★Lead Pouring Integrity Test
|  |  | Back Plate | 59RT-79112-0063-01-DD-B | 1
|  |  | Side Plate | 59RT-79112-0063-01-DD-B | 2
|  |  | Base Plate | 59RT-79112-0064-01-DD-B | 1
|  |  | Front Plate | 59RT-79112-0065-01-DD-B | 1
|  |  | Lead Seal Plug | 59RT-79112-0066-01-DD-B | 6
|  |  | Cover Latch Plate | 59RT-79112-0031-01-DD-B | 1
|  |  | Upper Latch Bar | 59RT-79112-0067-01-DD-B | 1
|  |  | Base Block | 59RT-79112-0068-01-DD-B | 1
|  |  | Boss | 59RT-79112-0069-01-DD-B | 4
|  |  | Lead Shielding | 59RT-79112-0070-01-DD-B | 1
|  |  | Top Cover Plate | 59RT-79112-0071-01-DD-B | 1
72425 | 4590038355 | Safran (Messier) | Loading Block | DSK30906G01-113 | 1 | 2025-06-24 |  | DONE
72430 | 88808- Rev.4 | ATS-Corp | Table Shielding Plate ( 103420) | NK38-DRAW-31935-10359-0001 | 1 | 2025-07-30 | ★Need to contuct | Passivate to ASTM |  | 2025-07-15: Fit, Tac, Weld; 2025-08-04: Turn; 2025-08-05: INS; 2025-08-14: Passivate to ASTM; 2025-08-15: Passivate to ASTM; 2025-08-18: Passivate to ASTM; 2025-08-19: Passivate to ASTM; 2025-08-20: Passivate to ASTM
72431 | 88808- Rev.2 | ATS-Corp | Counter Balance W/ Lead Assy (100882) | NK38-DRAW-31935-10536-0001 | 1 | 2025-07-30 | 2025-09-26 | water jet |  | 2025-09-22: Deburr; 2025-09-23: INS; 2025-09-24: Visual Examination; 2025-09-25: Visual Examination; 2025-09-26: Visual Examination; 2025-09-29: L-Etch; 2025-09-30: INS; 2025-10-01: Passivate; 2025-10-02: Passivate; 2025-10-03: Passivate; 2025-10-06: Passivate; 2025-10-07: Passivate; 2025-10-08: Receive,INS; 2025-10-09: INS,DIR; 2025-10-10: INS,DIR; 2025-10-13: INS,DIR; 2025-10-14: Doc; 2025-10-15: Doc; 2025-10-16: Pack; 2025-10-17: Ship
72431 | 88808- Rev.0 | ATS-Corp | Counter Balance Weldment (103414) | NK38-DRAW-31935-10538-0001 | 1 | 2025-07-30 | 2025-09-26 | water jet
72438 | RT98-87250-PN-R007 | Candu | Installation Worktable | RT-87250-040-01-GA-E | 3 | 2026-10-16
|  |  | INSTALLATION WORKTABLE (RT-7257) | RT-87250-0401-01-GA-E | 1
|  |  | SCISSOR ASSEMBLY | 21RT-87250-9001-1-DD-D
|  |  | BASEFRAME ASSEMBLY | 21RT-87250-9018-1-GA-D
|  |  | PLATFORM ASSEMBLY | 21RT-87250-9077-1-GA-D
|  |  | Y INDICATOR SLIDE ASSEMBLY | 21RT-87250-9148-1-GA-B
|  |  | BELLOWS | 21RT-87250-9125-1-DD-B
|  |  | BELLOWS MOUNTING BAR SIDE | 21RT-87250-9162-1-DD-B
|  |  | BELLOWS MOUNTING BAR END | 21RT-87250-9163-1-DD-B
|  |  | YAW ANGLE INDICATOR SCRIBE PLATE | 21RT-87250-9164-1-DD-B
|  |  | YAW INDICATOR ARM | 21RT-87250-9165-1-DD-B
|  |  | YAW INDICATOR ARM (OPPOSITE HAND) | 21RT-87250-9165-1-DD-B
|  |  | SERIAL PLATE | 21RT-87250-9166-1-DD-B
|  |  | Y INDICATOR SLIDE ASSEMBLY | 21RT-87250-9148-1-GA-B
|  |  | IWT SUPPORT FRAME (RT-7612) | RT-87250-70000-5000-1-GA-B | 1
|  |  | PIN BRACKET | RT-87920-0008-001-DD-C | 2
72439 | RT98-87250-PN-R007 | Candu | Inst. Worktable Support Frame | RT-87250-70000-5000-1-GA-B | 3 | 2026-10-16
IWT SUPPORT
FRAME
72440 | RT98-87250-PN-R007 | Candu | CT Shield Sleeve- Short | RT-87920-0303-01-GA-D | 4 | 2026-10-16
72441 | RT98-87250-PN-R007 | Candu | Hook Assy For Extension Tool | RT-87920-0051-01-DD-C | 6 | 2026-10-16
72443 | 216-02123-PN-T101 | Candu | Round Stud | RT-87600-0403-1-DD-C | 1 | 2025-08-27 |  | DONE
72444 | 216-02123-PN-T102 | Candu | Tooling Guide Pin | RT-87250-74017-002-1-DD-B | 8 | 2025-08-27 |  | DONE
72445 | 216-02123-PN-T102 | Candu | Handle | RT-87250-74017-044-1-DD-B | 4 | 2025-08-27 |  | DONE
72446 | 216-02123-PN-T102 | Candu | Pivot Block 0.50 x 1.25 x 3.0 | RT-87250-74017-045-1-DD-B | 4 | 2025-08-27 |  | DONE
72451 | 216-02123-PN-T104 | Candu | Axial Vacuum Nozzle | RT-87876-0049-01-DD-D | 1 | 2025-08-27 |  | DONE |  | 2025-07-21: Receive or Stock; 2025-07-22: CUT; 2025-07-23: Form; 2025-07-24: Form; 2025-07-25: Deburr; 2025-07-28: INS; 2025-07-29: Gather All items; 2025-07-30: Fit,Tack,Weld; 2025-07-31: Fit,Tack,Weld; 2025-08-01: Deburr; 2025-08-04: INS; 2025-08-05: Drill; 2025-08-06: Drill; 2025-08-07: Deburr; 2025-08-08: INS; 2025-08-11: Install; 2025-08-12: L-Etch; 2025-08-13: INS,DIR; 2025-08-14: INS,DIR; 2025-08-15: Pack; 2025-08-18: Pack
|  |  | Axial Vacuum Nozzle-Flat Pattern | RT-87876-0049-02-DD-C | 1 |  |  | Done |  | 2025-07-01: Water jet; 2025-07-28: Deburr; 2025-07-29: Deburr; 2025-07-30: INS
|  |  | Axial Vacuum Nozzle-Cover | RT-87876-0039-01-DD-C | 2 |  |  | Done |  | 2025-07-01: Water jet; 2025-07-28: Form; 2025-07-29: Form; 2025-07-30: Trim; 2025-07-31: Trim; 2025-08-01: Deburr; 2025-08-04: INS
|  |  | Axial Vacuum Nozzle-Side Stopper | RT-87876-0038-01-DD-C | 2 |  |  | Done |  | 2025-07-01: Water jet; 2025-07-28: Deburr; 2025-07-29: Deburr; 2025-07-30: INS
72452 | 216-02123-PN-T104 | Candu | Sliding Pad- Item # 4 | 21RT-87920-0453-002-DD-0 | 2 | 2025-08-29 |  | DONE |  | 2025-06-25: Mill
72453 | 4590038422 | Safran (Messier) | Striker Plate | DSK30901G04-101 ( HOLD) | 3 | 2025-07-04 |  | DONE
72454 | 4590038422 | Safran (Messier) | Dome | DSK30901G04-103 ( HOLD) | 1 | 2025-07-04 |  | DONE
72455 | 8451261- Rev.1 | ATS-Corp | Post Bearing Spacer | 700540049 | 1+1 | 2025-07-25 |  | DONE |  | 2025-07-18: Parts machining by an external supplier M&M
72456 | 8451261- Rev.1 | ATS-Corp | Coupling Housing | 700573391 | 2 | 2025-08-06 | ★外注あり（済） | Turn |  | 2025-07-17: Fit,Tack,Weld; 2025-07-23: Receive,INS; 2025-07-25: Turn; 2025-08-04: Mill、Drll＆Tap; 2025-08-05: Mill、Drll＆Tap; 2025-08-06: Paint; 2025-08-07: Doc; 2025-08-08: Doc; 2025-08-11: Doc; 2025-08-12: Doc; 2025-08-13: Pack; 2025-08-14: Pack; 2025-08-15: Ship
72458 | 88028931- Rev.1 | ATS Test | Flowmeter Pipe Section | 700615075 | 1 | 2025-08-06 |  | Ship |  | 2025-07-10: DRILL
72459-1 72459-10 | RT98-88030-PN-R001- R.2 | Candu | Eddy Current Verification Bench | RT-88030-0310-1-GA-D | 2 | 2025-08-27 | Awating updated scheduled from Eddyfi | INS | Receive,INS | 2025-10-22: INS; 2025-10-23: INS; 2025-10-24: INS; 2025-10-27: INS; 2025-10-28: INS; 2025-10-29: DIR; 2025-10-30: DIR; 2025-10-31: DIR; 2025-11-03: DIR; 2025-11-04: DIR
|  |  | BASE PLATE | RT-88030-0311-1-DD-E | 1 |  |  | DONE |  | 2025-07-03: waterjet
|  |  | V-BLOCK | RT-88030-0311-1-DD-E | 1 |  |  | DONE |  | 2025-07-14: waterjet
|  |  | FRONT V-BLOCK | RT-88030-0311-1-DD-E | 1 |  |  | DONE |  | 2025-07-14: waterjet
|  |  | TRANSDUCER SUPPORT | RT-88030-0312-1-DD-D | 1 |  |  | DONE |  | 2025-07-07: waterjet
|  |  | GUSSET | RT-88030-0312-1-DD-D | 2 |  |  | DONE
|  |  | TAB WASHER | RT-88030-0312-1-DD-D | 6 |  |  | DEBURR |  | 2025-07-02: DEBURR
72460-1 72460-9 | RT98-88030-PN-R001- R.2 | Candu | Tool Encoder Bracket Assy | RT-88030-0021-01-GA-1 | 2 | 2025-08-27 | Awating updated scheduled from Eddyfi | Assembly |  | 2025-10-22: Assembly; 2025-10-23: INS; 2025-10-24: INS; 2025-10-27: INS; 2025-10-28: INS; 2025-10-29: DIR; 2025-10-30: DIR; 2025-10-31: DIR; 2025-11-03: DIR; 2025-11-04: DIR
|  |  | Tool Encoder Bracket Assy-Pin | RT-88030-0024-01-DD-2 | Pin |  |  | DONE
|  |  | Tool Encoder Bracket Assy-Gusset | RT-88030-0019-01-DD-2 | 4 |  |  | DONE
|  |  | Tool Encoder Bracket Assy-PinHolder | RT-88030-0020-01-DD-2 | 4 |  |  | DONE |  | 2025-07-11: TURN
|  |  | Tool Encoder Bracket Assy-Guide ASSY | RT-88030-0016-01-GA-1 | 2 |  |  | DONE |  | 2025-08-21: Weld; 2025-08-22: Deburr; 2025-08-25: INS; 2025-08-26: Face Datum; 2025-08-27: Face Datum; 2025-08-28: Deburr; 2025-08-29: INS,DIR; 2025-09-01: INS,DIR
|  |  | Tool Encoder Bracket Assy-Guide ASSY | RT-88030-0018-01-GA-2 | 2 |  |  | DONE
|  |  | Tool Encoder Bracket Assy-Wire Wheel | RT-88030-0023-01-DD-2 | 2 |  |  | DONE
|  |  | Tool Encoder Bracket Assy-Top Plate | RT-88030-0017-01-DD-2 | 2 |  |  | DONE |  | 2025-07-11: Waterjet; 2025-08-01: Mill; 2025-08-04: Mill; 2025-08-05: Deburr; 2025-08-06: INS,DIR; 2025-08-07: INS,DIR
|  |  | Tool Encoder Bracket Assy-wheel Bracket | RT-88030-0022-01-DD-2 | 2 |  | ★外注あり(済) | DONE |  | 2025-07-09: Waterjet; 2025-08-19: Canada Tools & Molding; 2025-08-20: Canada Tools & Molding; 2025-08-21: Receive,INS; 2025-08-22: Mill; 2025-08-25: Mill; 2025-08-26: Mill; 2025-08-27: Mill; 2025-08-28: Deburr; 2025-08-29: INS,DIR; 2025-09-01: INS,DIR
72461 | 216-02123-PN-T105 | Candu | Tag- Load Test | RT-88000-70164-107-1-DD-B | 2 | 2025-09-03 |  | DONE
72462 | 216-02123-PN-T105 | Candu | Counterweight assy | RT-88000-70164-035-1-GA-C | 1 | 2025-09-03 |  | DONE |  | 2025-06-17: Receive,INS; 2025-08-26: INS,DIR; 2025-08-27: INS,DIR; 2025-08-28: Pack; 2025-08-29: Ship
|  |  | PLATE 1 | RT-88000-70164-036-1-DD-B | 1 |  |  | DONE
|  |  | PLATE 2 | RT-88000-70164-037-1-DD-B | 2 |  |  | DONE |  | 2025-07-04: DEBURR
|  |  | RETAINING BLOCK | RT-88000-70164-038-1-DD-B | 4 |  |  | DONE
|  |  | PAD | RT-88000-70164-039-1-DD-B | 2 |  |  | DONE
72463 | 216-02123-PN-T105 | Candu | PT Support Assy | RT-88000-70164-030-1-GA-D | 1 | 2025-09-03 |  | DONE |  | 2025-06-17: Receive,INS
|  |  | CLAMP | RT-88000-70164-031-1-DD-C | 1 |  |  | DONE |  | 2025-07-04: DEBURR
|  |  | ARM | RT-88000-70164-032-1-DD-C | 2 |  |  | DONE
|  |  | WHEEL | RT-88000-70164-033-1-DD-C | 2 |  |  | DONE
72464 | 216-02123-PN-T105 | Candu | Tag C of G | RT-88000-70164-106-1-DD-B | 2 | 2025-09-03 |  | DONE |  | 2025-08-05: Mill
72465 | 216-02123-PN-T105 | Candu | Tag C of G without end fitting | RT-88000-70164-105-1-DD-B | 2 | 2025-09-03 |  | DONE |  | 2025-08-06: Mill
72466 | 216-02123-PN-T105 | Candu | Tag | RT-88000-70164-104-1-DD-E | 2 | 2025-09-03 |  | DONE
72467 | 216-02123-PN-T105 | Candu | Sleeve Block | RT-88000-70164-025-1-DD-D | 2 | 2025-08-29 |  | DONE
72468 | 216-02123-PN-T105 | Candu | Spacer | RT-88000-70164-020-1-DD-B | 1 | 2025-08-29 |  | DONE
72469 | 216-02123-PN-T105 | Candu | Stiffener 1 | RT-88000-70164-018-1-DD-D | 1 | 2025-09-30 |  | Dimention is out so making another one Big machine stuck |  | 2025-08-25: Cut; 2025-08-26: Mill,Drill; 2025-08-27: Mill,Drill; 2025-08-28: Drill; 2025-08-29: Drill; 2025-09-01: Deburr; 2025-09-02: INS,DIR; 2025-09-03: INS,DIR; 2025-09-04: Pack; 2025-09-05: Ship
72470 | 216-02123-PN-T105 | Candu | Block 12 | RT-88000-70164-012-1-DD-D | 2 | 2025-08-29 |  | DONE
72471 | 216-02123-PN-T105 | Candu | Stiffener 2 | RT-88000-70164-019-1-DD-D | 1 | 2025-09-30 |  | Dimention is out so making another one Big machine stuck |  | 2025-08-25: Cut; 2025-08-26: Mill,Drill; 2025-08-27: Mill,Drill; 2025-08-28: Drill; 2025-08-29: Drill; 2025-09-01: Deburr; 2025-09-02: INS,DIR; 2025-09-03: INS,DIR; 2025-09-04: Pack; 2025-09-05: Ship
72472 | 211248489 | Buffalo | Motor Adapter Plate | 3677249 | 1 | 2025-07-11 |  | DONE
72473 | 211248489 | Bombardier | Small Buttons ( Busihng) For H/T | Samples- F/I | 15 | 2025-06-20 |  | DONE
72475 | 4074 | EHV Power | "L" Type Angle- 102 x 76 x 6.4ft- l=908mm | 230819-EBA230-02 | 6 | 2025-07-11
72475 | 4074 | EHV Power | "L" Type Angle- 51 x 51 6f.4 ft- l=876mm | 230819-EBA230-02 | 12 | 2025-07-11
72475 | 4074 | EHV Power | "L" Type Angle- 102 x 76 x 6.4ft- l=102mm | 230819-EBA230-02 | 66 | 2025-07-11 |  | DONE
72475 | 4074 | EHV Power | "L" Type Angle- 64 x 64 x 6.4ft- l=914mm | 230819-EBA230-02 | 16 | 2025-07-11 |  | DONE
72475 | 4074 | EHV Power | "L" Type Angle- 64 x 64 x 6.4ft- l=800mm | 230819-EBA230-02 | 16 | 2025-07-11 |  | DONE
72475 | 4074 | EHV Power | Hardware-HH bolts, Nuts, Washers -galv | 230819-EBA230-02 | lot | 2025-07-11
72477 | 4500012296-0 | ABI Ltd | Drive Roller | 4212B011 | 1 | 2025-07-07 |  | DONE
72477 | 4500012296-0 | ABI Ltd | Drive Roller-Drive Pulley Tube | 5210C114 | 1 | 2025-07-07 |  | DONE
72478 | 88706-Rev.7 | ATS-Corp | Probe Support Base Weldment | NK38-DRAW-31935-10461-0001 | 1 | 2025-08-28 | 2025-09-26 | DIR |  | 2025-07-17: INS; 2025-09-03: Passivate to ASTM Electro Kleen; 2025-09-04: Passivate to ASTM Electro Kleen; 2025-09-05: Passivate to ASTM Electro Kleen; 2025-09-08: Passivate to ASTM Electro Kleen; 2025-09-09: Passivate to ASTM Electro Kleen; 2025-09-10: Passivate to ASTM Electro Kleen; 2025-09-11: Passivate to ASTM Electro Kleen; 2025-09-12: Receive,INS; 2025-09-13: INS,DIR; 2025-09-16: DIR; 2025-09-17: DIR Doc; 2025-09-18: Doc; 2025-09-19: Ship
72479 | 88706-Rev.7 | ATS-Corp | Frame Weldment | NK38-DRAW-31935-10462-0001 | 1 | 2025-08-28 | 2025-09-26 | Fixing |  | 2025-07-28: Mill,Drill; 2025-07-29: Mill; 2025-07-30: Waterjet; 2025-07-31: Waterjet; 2025-08-01: Mill; 2025-08-04: Mill; 2025-08-05: Mill; 2025-08-06: Mill; 2025-08-07: Mill; 2025-08-08: Mill; 2025-08-11: Deburr; 2025-08-12: INS; 2025-08-13: INS; 2025-08-14: Gather All items; 2025-08-15: Fit,Tack,Weld; 2025-08-18: Fit,Tack,Weld; 2025-08-19: Deburr; 2025-08-20: INS; 2025-08-21: INS; 2025-08-22: Visual Examination Perfection; 2025-08-25: Visual Examination Perfection; 2025-08-26: Visual Examination Perfection; 2025-08-27: Visual Examination Perfection; 2025-08-28: Visual Examination Perfection; 2025-08-29: Visual Examination Perfection; 2025-09-01: Visual Examination Perfection; 2025-09-02: Passivate to ASTM Electro-Kleen; 2025-09-03: Passivate to ASTM Electro-Kleen; 2025-09-04: Passivate to ASTM Electro-Kleen; 2025-09-05: Passivate to ASTM Electro-Kleen; 2025-09-08: Passivate to ASTM Electro-Kleen; 2025-09-09: Passivate to ASTM Electro-Kleen; 2025-09-10: Passivate to ASTM Electro-Kleen; 2025-09-11: Receive,INS; 2025-09-12: INS,DIR; 2025-09-13: INS,DIR; 2025-09-17: Fixing; 2025-09-18: Fixing; 2025-09-19: Fixing; 2025-09-22: Passivate to ASTM Electro Kleen; 2025-09-23: Passivate to ASTM Electro Kleen; 2025-09-24: Passivate to ASTM Electro Kleen; 2025-09-25: Passivate to ASTM Electro Kleen; 2025-09-26: Passivate to ASTM Electro Kleen; 2025-09-29: Passivate to ASTM Electro Kleen; 2025-09-30: Passivate to ASTM Electro Kleen; 2025-10-01: Receive,INS; 2025-10-02: INS,DIR; 2025-10-03: INS,DIR; 2025-10-06: INS,DIR; 2025-10-07: INS,DIR; 2025-10-08: Pack; 2025-10-09: Pack; 2025-10-10: Ship
72480 | 88706-Rev.7 | ATS-Corp | Probe Weldment | NK38-DRAW-31935-10464-0001 | 1 | 2025-08-28 | 2025-09-26 | INS,DIR |  | 2025-07-25: Prep; 2025-07-28: Fit; 2025-07-29: Fit; 2025-07-30: Straighten; 2025-07-31: Visual Examination Perfection; 2025-08-01: Visual Examination Perfection; 2025-08-04: Visual Examination Perfection; 2025-08-05: Visual Examination Perfection; 2025-08-06: Visual Examination Perfection; 2025-08-07: Visual Examination Perfection; 2025-08-08: Visual Examination Perfection; 2025-08-11: Face Flange; 2025-08-12: Face Flange; 2025-08-29: Deburr; 2025-09-01: INS; 2025-09-02: INS; 2025-09-03: Weigh; 2025-09-04: L-Etch; 2025-09-05: L-Etch; 2025-09-08: INS; 2025-09-09: INS; 2025-09-10: Passivate to ASTM Electro Kleen; 2025-09-11: Passivate to ASTM Electro Kleen; 2025-09-12: Passivate to ASTM Electro Kleen; 2025-09-13: Passivate to ASTM Electro Kleen; 2025-09-17: Passivate to ASTM Electro Kleen; 2025-09-18: Receive,INS; 2025-09-19: INS,DIR; 2025-09-22: INS,DIR; 2025-09-23: INS,DIR; 2025-09-24: INS,DIR; 2025-09-25: Pack; 2025-09-26: Ship
72481 | 88706-Rev.7 | ATS-Corp | Bundle Support Base Weldment | NK38-DRAW-31935-10466-0001 | 1 | 2025-08-28 | 2025-09-26 | DIR |  | 2025-06-24: Receive or Stock; 2025-07-24: Prep; 2025-07-25: Fit; 2025-07-28: Fit; 2025-07-29: Deburr; 2025-07-30: INS; 2025-07-31: INS; 2025-08-01: Straighten; 2025-08-04: Visual Examination Perfection; 2025-08-05: Visual Examination Perfection; 2025-08-06: Visual Examination Perfection; 2025-08-07: Visual Examination Perfection; 2025-08-08: Visual Examination Perfection; 2025-08-11: Visual Examination Perfection; 2025-08-12: Visual Examination Perfection; 2025-08-13: Face Flange; 2025-08-14: Face Flange; 2025-08-15: Deburr; 2025-08-18: INS; 2025-08-19: INS; 2025-08-20: Install; 2025-09-03: Passivate to ASTM Electro Kleen; 2025-09-04: Passivate to ASTM Electro Kleen; 2025-09-05: Passivate to ASTM Electro Kleen; 2025-09-08: Passivate to ASTM Electro Kleen; 2025-09-09: Passivate to ASTM Electro Kleen; 2025-09-10: Passivate to ASTM Electro Kleen; 2025-09-11: Passivate to ASTM Electro Kleen; 2025-09-12: Receive,INS; 2025-09-13: INS,DIR; 2025-09-16: DIR; 2025-09-17: DIR Doc; 2025-09-18: Doc; 2025-09-19: Ship
72482 | 88706-Rev.7 | ATS-Corp | Probe Guard Weldment | NK38-DRAW-31935-10469-0001 | 1 | 2025-08-28 | 2025-09-26 | Fixing |  | 2025-07-17: CUT; 2025-07-24: Fit; 2025-07-31: Straighten; 2025-08-01: Visual Examination Perfection; 2025-08-04: Visual Examination Perfection; 2025-08-05: Visual Examination Perfection; 2025-08-06: Visual Examination Perfection; 2025-08-07: Visual Examination Perfection; 2025-08-08: Visual Examination Perfection; 2025-08-11: Visual Examination Perfection; 2025-08-12: Mill; 2025-08-13: Mill; 2025-08-14: Deburr; 2025-08-15: INS,DIR; 2025-08-18: INS,DIR; 2025-08-19: Weigh; 2025-08-20: L-Etch; 2025-08-21: L-Etch; 2025-08-22: INS Marking; 2025-08-25: INS Marking; 2025-08-26: Pack; 2025-08-27: Pack; 2025-08-28: Ship; 2025-09-16: Fixing; 2025-09-17: Fixing; 2025-09-18: Fixing; 2025-09-19: Fixing; 2025-09-22: Fixing; 2025-09-23: INS; 2025-09-24: L-Etch; 2025-09-25: DIR; 2025-09-26: DIR; 2025-09-29: DIR; 2025-09-30: DIR; 2025-10-01: DIR Doc; 2025-10-02: Doc; 2025-10-03: Ship
72483 | 88706-Rev.7 | ATS-Corp | Probe Holder Extension | NK38-DRAW-31935-10472-0001 | 1 | 2025-08-28 | 2025-09-26 | INS |  | 2025-07-21: Cut; 2025-08-01: Prep; 2025-08-04: Prep; 2025-08-05: Fit,Tack,Weld; 2025-08-06: Fit,Tack,Weld; 2025-08-07: Deburr; 2025-08-08: INS; 2025-08-11: INS; 2025-08-12: Straighten; 2025-08-13: Visual Examination Perfection; 2025-08-14: Visual Examination Perfection; 2025-08-15: Visual Examination Perfection; 2025-08-18: Visual Examination Perfection; 2025-08-19: Visual Examination Perfection; 2025-08-20: Visual Examination Perfection; 2025-08-21: Visual Examination Perfection; 2025-08-22: Face End,Bore; 2025-08-25: Face End,Bore; 2025-08-26: Deburr; 2025-08-27: INS; 2025-08-28: INS; 2025-08-29: Passivate to ASTM Electro Kleen; 2025-09-01: Passivate to ASTM Electro Kleen; 2025-09-02: Passivate to ASTM Electro Kleen; 2025-09-03: Passivate to ASTM Electro Kleen; 2025-09-04: Passivate to ASTM Electro Kleen; 2025-09-05: Passivate to ASTM Electro Kleen; 2025-09-08: Passivate to ASTM Electro Kleen; 2025-09-09: Receive,INS; 2025-09-10: INS,DIR; 2025-09-11: INS,DIR; 2025-09-12: Pack; 2025-09-13: Pack; 2025-09-17: Passivate to ASTM Electro Kleen; 2025-09-18: Receive,INS; 2025-09-19: INS,DIR; 2025-09-22: INS,DIR; 2025-09-23: INS,DIR; 2025-09-24: INS,DIR; 2025-09-25: Pack; 2025-09-26: Ship
72484 | 88706-Rev.7 | ATS-Corp | Upper Frame Weldment | NK38-DRAW-31935-10489-0001 | 1 | 2025-08-28 | 2025-09-26 | Deburr |  | 2025-07-21: Cut; 2025-07-31: Straighten; 2025-08-01: Visual Examination Perfection; 2025-08-04: Visual Examination Perfection; 2025-08-05: Visual Examination Perfection; 2025-08-06: Visual Examination Perfection; 2025-08-07: Visual Examination Perfection; 2025-08-08: Visual Examination Perfection; 2025-08-11: Deburr; 2025-08-12: INS; 2025-08-13: INS; 2025-08-14: Weigh; 2025-08-15: L-Etch; 2025-08-18: L-Etch; 2025-08-19: INS Marking; 2025-08-20: Passivate Electro-Kleen; 2025-08-21: Passivate Electro-Kleen; 2025-08-22: Passivate Electro-Kleen; 2025-08-25: Passivate Electro-Kleen; 2025-08-26: Passivate Electro-Kleen; 2025-08-27: Passivate Electro-Kleen; 2025-08-28: Passivate Electro-Kleen; 2025-08-29: Receive,INS; 2025-09-01: Pack; 2025-09-02: Pack; 2025-09-03: Ship; 2025-09-17: Passivate to ASTM Electro Kleen; 2025-09-18: Receive,INS; 2025-09-19: INS,DIR; 2025-09-22: INS,DIR; 2025-09-23: INS,DIR; 2025-09-24: INS,DIR; 2025-09-25: Pack; 2025-09-26: Ship
72485 | 88706-Rev.7 | ATS-Corp | Bottom Frame Weldment | NK38-DRAW-31935-10490-0001 | 1 | 2025-08-28 | 2025-09-26 | INS |  | 2025-07-22: Cut; 2025-07-31: Prep; 2025-08-01: Prep; 2025-08-06: Fit,Tack,Weld; 2025-08-07: Fit,Tack,Weld; 2025-08-08: Deburr; 2025-08-11: INS; 2025-08-12: Straighten; 2025-08-13: Visual Examination Perfection; 2025-08-14: Visual Examination Perfection; 2025-08-15: Visual Examination Perfection; 2025-08-18: Visual Examination Perfection; 2025-08-19: Visual Examination Perfection; 2025-08-20: Visual Examination Perfection; 2025-08-21: Visual Examination Perfection; 2025-08-22: Face; 2025-08-25: Face; 2025-08-26: Deburr; 2025-08-27: INS; 2025-08-28: INS; 2025-08-29: Weigh; 2025-09-01: L-Etch; 2025-09-02: L-Etch; 2025-09-03: INS Marking; 2025-09-04: Passivate Electro-Kleen; 2025-09-05: Passivate Electro-Kleen; 2025-09-08: Passivate Electro-Kleen; 2025-09-09: Passivate Electro-Kleen; 2025-09-10: Passivate Electro-Kleen; 2025-09-11: Passivate Electro-Kleen; 2025-09-12: Passivate Electro-Kleen; 2025-09-13: Receive,INS; 2025-09-16: Pack; 2025-09-22: Passivate to ASTM Electro Kleen; 2025-09-23: Passivate to ASTM Electro Kleen; 2025-09-24: Passivate to ASTM Electro Kleen; 2025-09-25: Passivate to ASTM Electro Kleen; 2025-09-26: Passivate to ASTM Electro Kleen; 2025-09-29: Passivate to ASTM Electro Kleen; 2025-09-30: Passivate to ASTM Electro Kleen; 2025-10-01: Receive,INS; 2025-10-02: INS,DIR; 2025-10-03: INS,DIR; 2025-10-06: INS,DIR; 2025-10-07: INS,DIR; 2025-10-08: Pack; 2025-10-09: Pack; 2025-10-10: Ship
72488 | 89053- Rev.1 | ATS-Corp | Cable Reel Bracket Weldment | 700460807 | 1 | 2025-07-22 | ★外注あり（済） | Receive,INS |  | 2025-07-18: Fit,Tack,Weld; 2025-07-29: Receive,INS; 2025-08-06: Paint; 2025-08-07: Doc; 2025-08-08: Doc; 2025-08-11: Doc; 2025-08-12: Doc; 2025-08-13: Pack; 2025-08-14: Pack; 2025-08-15: Ship
72489 | 89053- Rev.1 | ATS-Corp | Drive Weldment | 700465242 | 1 | 2025-07-25 | ★外注あり（済） | Fit,Tack,Weld |  | 2025-07-23: Fit,Tack,Weld; 2025-07-31: Deburr; 2025-08-01: INS; 2025-08-04: MPI Perfection; 2025-08-05: Sand Blast; 2025-08-06: Sand Blast; 2025-08-07: Mill,Drill,Tap; 2025-08-08: Mill,Drill,Tap; 2025-08-11: Mill,Drill,Tap; 2025-08-12: Mill,Drill,Tap; 2025-08-13: Drill&Tap; 2025-08-14: Drill&Tap; 2025-08-15: Mill; 2025-08-18: Mill; 2025-08-19: Mill; 2025-08-20: Mill; 2025-08-21: Deburr; 2025-08-22: Stamp; 2025-08-25: INS,DIR; 2025-08-26: INS,DIR; 2025-08-27: Paint; 2025-08-28: Paint; 2025-08-29: Pack; 2025-09-01: Pack; 2025-09-02: Ship
72490 | 721700 | BWXT(GE) | Pinion G.01/ G.02 / G.03 | X80-5212 | 300 @ | 2025-08-29 | ★外注あり | Passivete per ASTM Electrokleen |  | 2025-07-28: Passivete per ASTM Electrokleen; 2025-07-29: Passivete per ASTM Electrokleen; 2025-07-30: Passivete per ASTM Electrokleen; 2025-07-31: Passivete per ASTM Electrokleen; 2025-08-01: Passivete per ASTM Electrokleen; 2025-08-04: Passivete per ASTM Electrokleen; 2025-08-05: Passivete per ASTM Electrokleen; 2025-08-06: Receive,INS; 2025-08-07: Receive,INS; 2025-08-08: Receive,INS; 2025-08-11: Receive,INS; 2025-08-12: Receive,INS; 2025-08-13: Receive,INS; 2025-08-14: Pack; 2025-08-15: Pack; 2025-08-18: Pack
72490 | 721700 | BWXT(GE) | Bearing G.01/ G.02/ G.03 | X80-5212 | 300 @ | 2025-08-29 | ★外注あり | Passivete per ASTM Electrokleen |  | 2025-07-28: Passivete per ASTM Electrokleen; 2025-07-29: Passivete per ASTM Electrokleen; 2025-07-30: Passivete per ASTM Electrokleen; 2025-07-31: Passivete per ASTM Electrokleen; 2025-08-01: Passivete per ASTM Electrokleen; 2025-08-04: Passivete per ASTM Electrokleen; 2025-08-05: Passivete per ASTM Electrokleen; 2025-08-06: Receive,INS; 2025-08-07: Receive,INS; 2025-08-08: Receive,INS; 2025-08-11: Receive,INS; 2025-08-12: Receive,INS; 2025-08-13: Receive,INS; 2025-08-14: Pack; 2025-08-15: Pack; 2025-08-18: Pack
72490 | 721700 | BWXT(GE) | Brush- G.01 / G.02/ G.03 | X80-5212 | 300@ | 2025-08-29 | ★外注あり | Passivete per ASTM Electrokleen |  | 2025-07-28: Passivete per ASTM Electrokleen; 2025-07-29: Passivete per ASTM Electrokleen; 2025-07-30: Passivete per ASTM Electrokleen; 2025-07-31: Passivete per ASTM Electrokleen; 2025-08-01: Passivete per ASTM Electrokleen; 2025-08-04: Passivete per ASTM Electrokleen; 2025-08-05: Passivete per ASTM Electrokleen; 2025-08-06: Receive,INS; 2025-08-07: Receive,INS; 2025-08-08: Receive,INS; 2025-08-11: Receive,INS; 2025-08-12: Receive,INS; 2025-08-13: Receive,INS; 2025-08-14: Pack; 2025-08-15: Pack; 2025-08-18: Pack
72491 | 1114013 | BWXT Med | GR2 Titanium Heating Block | K129412-210- Option #2 | 1 | 2025-08-15 |  | DONE
72492 | 83139- Rev.1 | ATS-Corp | Piston Clamp Plate | 700614242 | 4 | 2025-07-21 |  | Ship |  | 2025-07-04: Receive,INS; 2025-07-31: Bend; 2025-08-01: INS; 2025-08-04: INS; 2025-08-05: Pack; 2025-08-06: Pack; 2025-08-07: Ship
72493 | 83139- Rev.1 | ATS-Corp | Trough Section | 700470628 | 2 | 2025-07-21 | Ship date : 10/6/2025 | INS |  | 2025-07-31: Receive,INS; 2025-08-01: Cut(Done); 2025-08-04: Cut; 2025-08-05: Turn; 2025-08-06: Turn; 2025-08-07: Mill; 2025-08-08: Mill; 2025-08-11: Deburr; 2025-08-12: INS; 2025-08-13: INS; 2025-08-14: Pack; 2025-08-15: Pack; 2025-08-18: Ship; 2025-10-02: INS; 2025-10-03: DIR; 2025-10-06: Ship
72495 | 8451433- Rev.2 | ATS-Corp | Box Slide | 700657767 | 1 | 2025-08-06 | ★外注あり(済) | Ship |  | 2025-07-22: Mill; 2025-07-24: Fit,Tack,Weld; 2025-07-31: Drill&Tap; 2025-08-01: Deburr; 2025-08-04: INS; 2025-08-05: Nitride A&M; 2025-08-06: Nitride A&M; 2025-08-07: Nitride A&M; 2025-08-08: Nitride A&M; 2025-08-11: Nitride A&M; 2025-08-12: Nitride A&M; 2025-08-13: Nitride A&M; 2025-08-14: Receive,INS; 2025-08-15: Receive,INS; 2025-08-19: Receive,INS; 2025-08-26: INS; 2025-08-27: INS; 2025-08-28: Pack
72496 | 3739266 | DJ Ind. | Malomar Depositor Slide (Ertalyte) | 66812-MD | 2 | 2025-07-17 |  | DONE
72497 | 721701 | BWXT(GE) | Housing | 208370-1 | 170 | 2025-10-21 | ★外注あり | Order Complete |  | 2025-09-25: Order Complete Shiny Tech; 2025-09-26: Order Complete Shiny Tech; 2025-09-29: Order Complete Shiny Tech; 2025-09-30: Order Complete Shiny Tech; 2025-10-01: Order Complete Shiny Tech; 2025-10-02: Order Complete Shiny Tech; 2025-10-03: Order Complete Shiny Tech; 2025-10-06: Receive,INS; 2025-10-07: Receive,INS; 2025-10-08: Receive,INS; 2025-10-09: INS; 2025-10-10: INS; 2025-10-13: INS; 2025-10-14: Pack; 2025-10-15: Pack; 2025-10-16: Pack; 2025-10-17: Ship
72498 | 721701 | BWXT(GE) | Front Plate | 208380-1 | 170 | 2025-10-21 | ★外注あり | Order Complete |  | 2025-09-25: Order Complete Shiny Tech; 2025-09-26: Order Complete Shiny Tech; 2025-09-29: Order Complete Shiny Tech; 2025-09-30: Order Complete Shiny Tech; 2025-10-01: Order Complete Shiny Tech; 2025-10-02: Order Complete Shiny Tech; 2025-10-03: Order Complete Shiny Tech; 2025-10-06: Receive,INS; 2025-10-07: Receive,INS; 2025-10-08: Receive,INS; 2025-10-09: INS; 2025-10-10: INS; 2025-10-13: INS; 2025-10-14: Pack; 2025-10-15: Pack; 2025-10-16: Pack; 2025-10-17: Ship
72499 | 721701 | BWXT(GE) | Rear Plate | 208381-1 | 350 | 2025-10-21 | ★外注あり | Order Complete |  | 2025-09-25: Order Complete Shiny Tech; 2025-09-26: Order Complete Shiny Tech; 2025-09-29: Order Complete Shiny Tech; 2025-09-30: Order Complete Shiny Tech; 2025-10-01: Order Complete Shiny Tech; 2025-10-02: Order Complete Shiny Tech; 2025-10-03: Order Complete Shiny Tech; 2025-10-06: Receive,INS; 2025-10-07: Receive,INS; 2025-10-08: Receive,INS; 2025-10-09: INS; 2025-10-10: INS; 2025-10-13: INS; 2025-10-14: Pack; 2025-10-15: Pack; 2025-10-16: Pack; 2025-10-17: Ship
72500 | 721701 | BWXT(GE) | Middle Plate | 208382-1 | 170 | 2025-10-21 | ★外注あり | Order Complete |  | 2025-09-25: Order Complete Shiny Tech; 2025-09-26: Order Complete Shiny Tech; 2025-09-29: Order Complete Shiny Tech; 2025-09-30: Order Complete Shiny Tech; 2025-10-01: Order Complete Shiny Tech; 2025-10-02: Order Complete Shiny Tech; 2025-10-03: Order Complete Shiny Tech; 2025-10-06: Receive,INS; 2025-10-07: Receive,INS; 2025-10-08: Receive,INS; 2025-10-09: INS; 2025-10-10: INS; 2025-10-13: INS; 2025-10-14: Pack; 2025-10-15: Pack; 2025-10-16: Pack; 2025-10-17: Ship
72501 | 721701 | BWXT(GE) | Retaining Ring | 460072-1 | 350 | 2025-10-21
72502 | 721701 | BWXT(GE) | Front Plate | 213025-1 | 180 | 2025-10-21 | ★外注あり | Order Complete |  | 2025-09-25: Order Complete Shiny Tech; 2025-09-26: Order Complete Shiny Tech; 2025-09-29: Order Complete Shiny Tech; 2025-09-30: Order Complete Shiny Tech; 2025-10-01: Order Complete Shiny Tech; 2025-10-02: Order Complete Shiny Tech; 2025-10-03: Order Complete Shiny Tech; 2025-10-06: Receive,INS; 2025-10-07: Receive,INS; 2025-10-08: Receive,INS; 2025-10-09: INS; 2025-10-10: INS; 2025-10-13: INS; 2025-10-14: Pack; 2025-10-15: Pack; 2025-10-16: Pack; 2025-10-17: Ship
72503 | 721701 | BWXT(GE) | Housing | 213026-1 | 180 | 2025-10-21 | ★外注あり | Order Complete |  | 2025-09-25: Order Complete Shiny Tech; 2025-09-26: Order Complete Shiny Tech; 2025-09-29: Order Complete Shiny Tech; 2025-09-30: Order Complete Shiny Tech; 2025-10-01: Order Complete Shiny Tech; 2025-10-02: Order Complete Shiny Tech; 2025-10-03: Order Complete Shiny Tech; 2025-10-06: Receive,INS; 2025-10-07: Receive,INS; 2025-10-08: Receive,INS; 2025-10-09: INS; 2025-10-10: INS; 2025-10-13: INS; 2025-10-14: Pack; 2025-10-15: Pack; 2025-10-16: Pack; 2025-10-17: Ship
72504 | 721704 | BWXT(GE) | Hub | 203346-1 | 350 | 2025-10-21 | ★外注あり | Order Complete |  | 2025-09-25: Order Complete Shiny Tech; 2025-09-26: Order Complete Shiny Tech; 2025-09-29: Order Complete Shiny Tech; 2025-09-30: Order Complete Shiny Tech; 2025-10-01: Order Complete Shiny Tech; 2025-10-02: Order Complete Shiny Tech; 2025-10-03: Order Complete Shiny Tech; 2025-10-06: Receive,INS; 2025-10-07: Receive,INS; 2025-10-08: Receive,INS; 2025-10-09: INS; 2025-10-10: INS; 2025-10-13: INS; 2025-10-14: Pack; 2025-10-15: Pack; 2025-10-16: Pack; 2025-10-17: Ship
72505 | 721704 | BWXT(GE) | Mounting Plate | 205626-12 & 15 | 670+710 | 2025-10-21 | ★外注あり | Order Complete |  | 2025-09-25: Order Complete Shiny Tech; 2025-09-26: Order Complete Shiny Tech; 2025-09-29: Order Complete Shiny Tech; 2025-09-30: Order Complete Shiny Tech; 2025-10-01: Order Complete Shiny Tech; 2025-10-02: Order Complete Shiny Tech; 2025-10-03: Order Complete Shiny Tech; 2025-10-06: Receive,INS; 2025-10-07: Receive,INS; 2025-10-08: Receive,INS; 2025-10-09: INS; 2025-10-10: INS; 2025-10-13: INS; 2025-10-14: Pack; 2025-10-15: Pack; 2025-10-16: Pack; 2025-10-17: Ship
72506 | 721704 | BWXT(GE) | End Cap | 28369-1 | 170 | 2025-10-21 | ★外注あり | Order Complete
72507 | 721704 | BWXT(GE) | Housing | 208374-1 | 170 | 2025-10-21 | 10pc ship : 8/25 10pc ship : 9/23 | Order Complete |  | 2025-09-25: Order Complete Shiny Tech; 2025-09-26: Order Complete Shiny Tech; 2025-09-29: Order Complete Shiny Tech; 2025-09-30: Order Complete Shiny Tech; 2025-10-01: Order Complete Shiny Tech; 2025-10-02: Order Complete Shiny Tech; 2025-10-03: Order Complete Shiny Tech; 2025-10-06: Receive,INS; 2025-10-07: Receive,INS; 2025-10-08: Receive,INS; 2025-10-09: INS; 2025-10-10: INS; 2025-10-13: INS; 2025-10-14: Pack; 2025-10-15: Pack; 2025-10-16: Pack; 2025-10-17: Ship
72508 | 721704 | BWXT(GE) | Standoff Post | 208373-1 | 340 | 2025-10-21 | ★外注あり | Order Complete |  | 2025-09-25: Order Complete Shiny Tech; 2025-09-26: Order Complete Shiny Tech; 2025-09-29: Order Complete Shiny Tech; 2025-09-30: Order Complete Shiny Tech; 2025-10-01: Order Complete Shiny Tech; 2025-10-02: Order Complete Shiny Tech; 2025-10-03: Order Complete Shiny Tech; 2025-10-06: Receive,INS; 2025-10-07: Receive,INS; 2025-10-08: Receive,INS; 2025-10-09: INS; 2025-10-10: INS; 2025-10-13: INS; 2025-10-14: Pack; 2025-10-15: Pack; 2025-10-16: Pack; 2025-10-17: Ship
72509 | 721704 | BWXT(GE) | Brush Block Shaft | 208376-1 | 690 | 2025-10-21 | ★外注あり | Order Complete |  | 2025-09-25: Order Complete Shiny Tech; 2025-09-26: Order Complete Shiny Tech; 2025-09-29: Order Complete Shiny Tech; 2025-09-30: Order Complete Shiny Tech; 2025-10-01: Order Complete Shiny Tech; 2025-10-02: Order Complete Shiny Tech; 2025-10-03: Order Complete Shiny Tech; 2025-10-06: Receive,INS; 2025-10-07: Receive,INS; 2025-10-08: Receive,INS; 2025-10-09: INS; 2025-10-10: INS; 2025-10-13: INS; 2025-10-14: Pack; 2025-10-15: Pack; 2025-10-16: Pack; 2025-10-17: Ship
72510 | 721704 | BWXT(GE) | Brush Block Shaft | 208377-1 | 350 | 2025-10-21 | ★外注あり | Order Complete |  | 2025-09-25: Order Complete Shiny Tech; 2025-09-26: Order Complete Shiny Tech; 2025-09-29: Order Complete Shiny Tech; 2025-09-30: Order Complete Shiny Tech; 2025-10-01: Order Complete Shiny Tech; 2025-10-02: Order Complete Shiny Tech; 2025-10-03: Order Complete Shiny Tech; 2025-10-06: Receive,INS; 2025-10-07: Receive,INS; 2025-10-08: Receive,INS; 2025-10-09: INS; 2025-10-10: INS; 2025-10-13: INS; 2025-10-14: Pack; 2025-10-15: Pack; 2025-10-16: Pack; 2025-10-17: Ship
72511 | 721704 | BWXT(GE) | Spacer Round & Mounting Standoff Round | 205624-13 & 14 | 1380+1380 | 2025-10-21 | ★外注あり | Order Complete |  | 2025-09-25: Order Complete Shiny Tech; 2025-09-26: Order Complete Shiny Tech; 2025-09-29: Order Complete Shiny Tech; 2025-09-30: Order Complete Shiny Tech; 2025-10-01: Order Complete Shiny Tech; 2025-10-02: Order Complete Shiny Tech; 2025-10-03: Order Complete Shiny Tech; 2025-10-06: Receive,INS; 2025-10-07: Receive,INS; 2025-10-08: Receive,INS; 2025-10-09: INS; 2025-10-10: INS; 2025-10-13: INS; 2025-10-14: Pack; 2025-10-15: Pack; 2025-10-16: Pack; 2025-10-17: Ship
72512 | 721704 | BWXT(GE) | Post | 205065-1 | 1380 | 2025-10-21 | ★外注あり | Order Complete |  | 2025-09-25: Order Complete Shiny Tech; 2025-09-26: Order Complete Shiny Tech; 2025-09-29: Order Complete Shiny Tech; 2025-09-30: Order Complete Shiny Tech; 2025-10-01: Order Complete Shiny Tech; 2025-10-02: Order Complete Shiny Tech; 2025-10-03: Order Complete Shiny Tech; 2025-10-06: Receive,INS; 2025-10-07: Receive,INS; 2025-10-08: Receive,INS; 2025-10-09: INS; 2025-10-10: INS; 2025-10-13: INS; 2025-10-14: Pack; 2025-10-15: Pack; 2025-10-16: Pack; 2025-10-17: Ship
72513 | 721704 | BWXT(GE) | Gearshaft | 208371-1 | 350 | 2025-10-21 | 8pc ship : 9/24 | Order Complete |  | 2025-09-25: Order Complete Shiny Tech; 2025-09-26: Order Complete Shiny Tech; 2025-09-29: Order Complete Shiny Tech; 2025-09-30: Order Complete Shiny Tech; 2025-10-01: Order Complete Shiny Tech; 2025-10-02: Order Complete Shiny Tech; 2025-10-03: Order Complete Shiny Tech; 2025-10-06: Receive,INS; 2025-10-07: Receive,INS; 2025-10-08: Receive,INS; 2025-10-09: INS; 2025-10-10: INS; 2025-10-13: INS; 2025-10-14: Pack; 2025-10-15: Pack; 2025-10-16: Pack; 2025-10-17: Ship
72514 | 721733 | BWXT(GE) | Shaft | 208375-1 | 350 | 2025-10-21 | 35pc ship : 8/25 35pc ship : 9/23 | Order Complete |  | 2025-09-30: Order Complete Shiny Tech; 2025-10-01: Order Complete Shiny Tech; 2025-10-02: Order Complete Shiny Tech; 2025-10-03: Order Complete Shiny Tech; 2025-10-06: Receive,INS; 2025-10-07: Receive,INS; 2025-10-08: Receive,INS; 2025-10-09: INS; 2025-10-10: INS; 2025-10-13: INS; 2025-10-14: Pack; 2025-10-15: Pack; 2025-10-16: Pack; 2025-10-17: Ship
72515 | 721733 | BWXT(GE) | Input Shaft | 208372-1 | 170 | 2025-10-21 |  | Order Complete
72516 | 721733 | BWXT(GE) | Input Shaft | 213747-1 | 180 | 2025-10-21 |  | Order Complete
72517 | RT79-87840-PN-R002 | Candu | CV FME Inspection Tool | RT-87840-70000-1000-1-GA-B | 3 | 2025-11-17 |  | Sub-parts are on order
|  |  | CV FME Inspection Tool-Camera Boom | RT-87840-70110-1000-1-GA-B | 3 | 2025-11-17 |  | Receive,Stock,INS | Receive,Stock,INS
|  |  | CV FME Inspection Tool-Adapter Compl. | RT-87840-70210-1000-1-GA-B | 3 | 2025-11-17 |  | Receive,INS |  | 2025-07-08: Receive,INS
|  |  | Adapter | RT-87840-70210-1001-1-DD-B | 3 |  |  | Receive or INS |  | 2025-07-16: Receive or INS
|  |  | CV FME Inspection Tool-Front Outer Tube | RT-87840-70110-1001-1-DD-B | 3 | 2025-11-17 |  | Check stock
|  |  | CV FME Inspection Tool-Front Inner Tube | RT-87840-70110-1002-1-DD-B | 3 | 2025-11-17 |  | Cut |  | 2025-08-13: Cut; 2025-08-27: Turn; 2025-08-28: Turn; 2025-08-29: Mill; 2025-09-01: Mill; 2025-09-02: Deburr; 2025-09-03: INS,DIR; 2025-09-04: INS,DIR
|  |  | CV FME Inspection Tool-Front Guide | RT-87840-70110-1003-1-DD-B | 3 | 2025-11-17
|  |  | CV FME Inspection Tool-Rear Guide | RT-87840-70110-1004-1-DD-B | 3 | 2025-11-17 | ★外注あり | TURN |  | 2025-07-21: TURN
|  |  | CV FME Inspection Tool-Coupling | RT-87840-70110-1005-1-DD-B | 3 | 2025-11-17 |  | Turn |  | 2025-07-18: Turn
|  |  | CV FME Inspection Tool-Flange | RT-87840-70110-1006-1-DD-B | 3 | 2025-11-17 |  | DRILL |  | 2025-07-21: DRILL
|  |  | CV FME Inspection Tool-Retainer | RT-87840-70110-1007-1-DD-B | 3 | 2025-11-17 |  | Water jet |  | 2025-07-21: Water jet
|  |  | CV FME Inspection Tool-Bushing | RT-87840-70110-1009-1-DD-B | 3 | 2025-11-17 |  | Receive,INS |  | 2025-07-08: Receive,Stock,INS
|  |  | CV FME Inspection Tool-Front Conduit | RT-87840-70110-1010-1-DD-B | 3 | 2025-11-17 |  | Cut |  | 2025-08-13: Cut; 2025-08-28: Turn; 2025-08-29: Turn; 2025-09-01: Deburr; 2025-09-02: INS,DIR; 2025-09-03: INS,DIR
|  |  | CV FME Inspection Tool-Frear Outer Tube | RT-87840-70110-1011-1-DD-B | 3 | 2025-11-17 |  | Check stock
|  |  | CV FME Inspection Tool-Rear Inner Tube | RT-87840-70110-1012-1-DD-B | 3 | 2025-11-17 |  | Turn |  | 2025-08-25: Turn; 2025-08-26: Turn; 2025-08-27: Mill; 2025-08-28: Mill; 2025-08-29: Deburr; 2025-09-01: L-Etch; 2025-09-02: L-Etch; 2025-09-03: INS,DIR; 2025-09-04: INS,DIR
|  |  | CV FME Inspection Tool-Rear Inner Tube | RT-87840-70110-1013-1-DD-B | 3 | 2025-11-17 | ★EDM | Turn |  | 2025-08-25: Turn; 2025-08-26: Mill; 2025-08-27: Mill; 2025-08-28: Drill; 2025-08-29: Drill; 2025-09-01: Deburr; 2025-09-02: INS,DIR; 2025-09-03: INS,DIR
|  |  | CV FME Inspection Tool-Rear Conduit | RT-87840-70110-1014-1-DD-B | 3 | 2025-11-17 |  | Cut |  | 2025-08-13: Cut; 2025-08-28: Turn; 2025-08-29: Turn; 2025-09-01: Deburr; 2025-09-02: INS,DIR; 2025-09-03: INS,DIR
|  |  | CV FME Inspection Tool-Flange | RT-87840-70110-1015-1-DD-B | 3 | 2025-11-17
|  |  | CV FME Inspection Tool-Bushing | RT-87840-70110-1016-1-DD-B | 3 | 2025-11-17
|  |  | CV FME Inspection Tool-Bushing | RT-87840-70110-1017-1-DD-B | 3 | 2025-11-17 |  | Turn |  | 2025-08-13: Turn; 2025-08-14: Grind; 2025-08-15: Grind; 2025-08-18: Deburr; 2025-08-19: Deburr; 2025-08-20: iNS,DIR; 2025-08-21: INS,DIR
|  |  | CV FME Inspection Tool-Wire Clip | RT-87840-70110-1018-1-DD-B | 3 | 2025-11-17 |  | DEBURR |  | 2025-07-11: DEBURR
|  |  | CV FME Inspection Tool-Wire Retainer | RT-87840-70110-1019-1-DD-B | 3 | 2025-11-17 |  | Drill&Bore |  | 2025-07-11: Drill&Bore
|  |  | CV FME Inspection Tool-Wire Guide | RT-87840-70110-1020-1-DD-B | 3 | 2025-11-17 |  | Mill |  | 2025-07-11: Mill
|  |  | CV FME Inspection Tool-ID Plate | RT-87840-70110-1022-1-DD-B | 3 | 2025-11-17
|  |  | CV FME Inspection Tool-Camera Pull Cable | RT-87840-70114-1000-1-GA-B | 3 | 2025-11-17 |  | Receive,INS | Receive,Stock,INS
|  |  | CV FME Inspection Tool-Eye Bracket | RT-87840-70110-1023-1-DD-B | 3 | 2025-11-17 |  | CUT |  | 2025-07-15: CUT
|  |  | CV FME Inspection Tool-Pulley | RT-87840-70110-1024-1-DD-B | 3 | 2025-11-17 |  | CUT |  | 2025-07-15: CUT
|  |  | CV FME Inspection Tool-Return Reel-Modified | RT-87840-70171-1001-1-DD-B | 3 | 2025-11-17 |  | Receive,INS | Receive,Stock,INS
|  |  | CV FME Inspection Tool-Return Reel ASSY | RT-87840-70171-1000-1-GA-B | 3 | 2025-11-17 |  | Receive,INS | Receive,Stock,INS
|  |  | CV FME Inspection Tool-Rear Mount | RT-87840-70120-1000-1-GA-B | 3 | 2025-11-17 |  | Receive,INS | Receive,Stock,INS
|  |  | CV FME Inspection Tool-Rear Base Plate | RT-87840-70120-1001-1-DD-B | 3 | 2025-11-17 |  | Mill |  | 2025-07-15: Mill
|  |  | CV FME Inspection Tool-Saddle Plate | RT-87840-70120-1002-1-DD-B | 6 | 2025-11-17
|  |  | CV FME Inspection Tool-Clamp | RT-87840-70120-1003-1-DD-B | 6 | 2025-11-17
|  |  | CV FME Inspection Tool-ID Plate | RT-87840-70120-1005-1-DD-B | 3 | 2025-11-17
|  |  | CV FME Inspection Tool-Weight Plate | RT-87840-70120-1006-1-DD-B | 3 | 2025-11-17
|  |  | CV FME Inspection Tool-ID Plate | RT-87840-70120-1007-1-DD-B | 3 | 2025-11-17
|  |  | CV FME Inspection Tool-Pointer | RT-87840-70120-1008-1-DD-B | 3 | 2025-11-17 |  | DEBURR |  | 2025-07-16: DEBURR
|  |  | CV FME Inspection Tool-Adapter Compl. | RT-87840-70120-1000-1-GA-B | 3 | 2025-11-17
|  |  | CV FME Inspection Tool-Adapter | RT-87840-70120-1001-1-DD-B | 3 | 2025-11-17
|  |  | CV FME Inspection Tool-ID Plate | RT-87840-70120-1002-1-DD-B | 3 | 2025-11-17
|  |  | CV FME Inspection Tool-FME Camera Tool | RT-87840-70000-1000-1-GA-B | 3 | 2025-11-17
|  |  | CV FME Inspection Tool-Front Roller Assembly |  | 3 | 2025-11-17 |  | Receive,INS | Receive,Stock
|  |  | CV FME Inspection Tool-Front Base Plate | RT-87840-70130-1001-1-DD-B | 3 | 2025-11-17 | ★Hard Anodize | Receive,INS |  | 2025-07-17: DEBURR; 2025-08-27: Hard Anodize; 2025-08-28: Receive,INS; 2025-08-29: INS,DIR; 2025-09-01: INS,DIR
|  |  | CV FME Inspection Tool-Roller MTG Plate LH | RT-87840-70130-1002-1-DD-B | 3 | 2025-11-17 | ★Hard Anodize | Receive,INS |  | 2025-08-27: Hard Anodize; 2025-08-28: Receive,INS; 2025-08-29: Mill; 2025-09-01: Mill; 2025-09-02: Drill; 2025-09-03: Drill; 2025-09-04: Deburr; 2025-09-05: INS; 2025-09-08: INS; 2025-09-09: INS,DIR; 2025-09-10: INS,DIR
|  |  | CV FME Inspection Tool-Roller MTG Plate RH | RT-87840-70130-1003-1-DD-B | 3 | 2025-11-17 | ★Hard Anodize | Receive,INS |  | 2025-08-27: Hard Anodize; 2025-08-28: Receive,INS; 2025-08-29: Drill; 2025-09-01: Drill; 2025-09-02: Deburr; 2025-09-03: INS; 2025-09-04: INS; 2025-09-05: INS,DIR; 2025-09-08: INS,DIR
|  |  | CV FME Inspection Tool-Gusset | RT-87840-70130-1004-1-DD-B | 3 | 2025-11-17 |  | DEBURR |  | 2025-07-15: DEBURR
|  |  | CV FME Inspection Tool-Roller | RT-87840-70130-1005-1-DD-B | 3 | 2025-11-17 |  | Receive,INS |  | 2025-07-16: Receive,Stock
|  |  | CV FME Inspection Tool-Shaft | RT-87840-70130-1006-1-DD-B | 3 | 2025-11-17 |  | Drill |  | 2025-07-09: Receive,Stock; 2025-08-28: Drill; 2025-08-29: Grind; 2025-09-01: Grind; 2025-09-02: Deburr; 2025-09-03: INS,DIR; 2025-09-04: INS,DIR
|  |  | CV FME Inspection Tool-Spacer Bushing | RT-87840-70130-1007-1-DD-B | 3 | 2025-11-17 |  | TURN |  | 2025-07-14: TURN
|  |  | CV FME Inspection Tool-Washer | RT-87840-70130-1008-1-DD-B | 3 | 2025-11-17 |  | TURN |  | 2025-07-11: TURN
|  |  | CV FME Inspection Tool-Guard | RT-87840-70130-1009-1-DD-B | 3 | 2025-11-17 |  | DEBURR |  | 2025-07-16: DEBURR
|  |  | CV FME Inspection Tool-ID Plate | RT-87840-70130-1010-1-DD-B | 3 | 2025-11-17
|  |  | CV FME Inspection Tool-FME Camera Tool | RT-87840-70100-1000-1-GA-B | 3 | 2025-11-17 |  | Gather All items
72520 |  | Hunstville | MZ2x2 Adjustable Injector F/I to Refurbish | MZ2x2-D-AI- R/W | 3 | 2025-07-18 | ★Check to Gus
72521 |  | Hunstville | MZ2x2-D- Bypass Valve F/I to refurbish | MZ2x2-D-BV- R/W | 2 | 2025-07-18
72522 |  | Hunstville | MZ2x2-D- Injector - F/I to Refurbish | MZ2x2-D- R/W | 6 (4;stock) | 2025-07-18 | Ask Gus about schedule | A&M |  | 2025-07-24: A&M
72523 | 89130- Rev.2 | ATS-Corp | Handle Extension | 700673679 | 4 | 2025-07-24 |  | Parts machining by an external supplier Electro-Kleen |  | 2025-07-18: Parts machining by an external supplier Electro-Kleen
72524 | 89130- Rev.2 | ATS-Corp | T-Handle Wrench- Handle | 700543934- F/I | 1 | 2025-07-25 |  | DONE
72525 | 280102819 | Kinectrics | Enclosure Cutouts- Sht # 1- F/I Mat'l | NPD0059-4920-MCC | 1 | 2025-07-17 | Ask Gus | Mill |  | 2025-07-23: Receive,INS; 2025-07-31: Mill
72526 | 280102819 | Kinectrics | PSU Enclosure Cutouts Sht# 8- F/I Mat'l | NPD0059-4920-MCC | 1 | 2025-07-17 | Ask Gus | Mill |  | 2025-07-23: Receive,INS; 2025-08-01: Mill; 2025-08-04: INS; 2025-08-05: INS; 2025-08-06: Pack; 2025-08-07: Ship
72527 | 280102819 | Kinectrics | Enclosure Back Plate- Sht # 1 F/I Mat'l | NPD0059-4921-RIO | 1 | 2025-07-17 |  | INS |  | 2025-07-23: Receive,INS; 2025-08-01: Deburr Clean; 2025-08-04: INS; 2025-08-05: INS; 2025-08-06: INS; 2025-08-07: INS; 2025-08-08: INS; 2025-08-11: INS; 2025-08-12: Pack; 2025-08-13: Ship
72528 | 280102819 | Kinectrics | Enclosure Back Plate- Sht # 2 F/I Mat'l | NPD0059-4921-RIO | 1 | 2025-07-17 | Ask Gus | Receive,INS |  | 2025-07-23: Receive,INS
72529 | 280102819 | Kinectrics | Add cut-outs per R01 Dwg F/I Mat'l | NPD0059-DET-2114 | 1 | 2025-07-17 | Ask Gus | DONE
72530 | 280102819 | Kinectrics | Heater PSU Mtg Plate ( new) | NPD0059-GA-4920 | 4 | 2025-07-17 | Ask Gus | DONE |  | 2025-07-31: Mill; 2025-08-01: INS; 2025-08-04: INS; 2025-08-05: Pack; 2025-08-06: Ship
72531 | 280102819 | ComEnCo | Burner End Plates R/w | 91592C03 | 2 | 2025-07-08
72532 | 91614-004 | Bombardier | Slotted & Drill Bushing | NPN | 3+2 | 2025-07-07
72533 | 211249978 | Husky | Leveling Bar | 2604680 | 2 | 2025-08-12 | ★Black oxide | Receive,INS |  | 2025-07-04: Material; 2025-07-21: Receive,INS; 2025-07-22: Receive,INS; 2025-07-23: Receive,INS; 2025-07-24: Receive,INS; 2025-07-25: Drill; 2025-07-31: Grind RTD; 2025-08-01: Grind RTD; 2025-08-04: Grind RTD; 2025-08-05: Grind RTD; 2025-08-06: Grind RTD; 2025-08-07: Grind RTD; 2025-08-08: Grind RTD; 2025-08-11: Grind RTD; 2025-08-12: Grind RTD; 2025-08-13: Grind RTD; 2025-08-14: Grind RTD; 2025-08-15: Grind RTD; 2025-08-18: Grind RTD; 2025-08-19: Grind RTD; 2025-08-20: Grind RTD; 2025-08-21: Grind RTD; 2025-08-22: Grind RTD; 2025-08-25: Grind RTD; 2025-08-26: Receive,INS
72534 | 216-02123-PN-T110 | Candu | Front Tube Support Retainer | RT-87920-74245-034-1-DD-B | 1 | 2025-08-27 |  | DONE
72535 | 216-02123-PN-T110 | Candu | Front Tube Support | RT-87920-74245-032-1-DD-B |  | 2025-08-27 |  | DONE
72536 | 216-02123-PN-T110 | Candu | Front Support Screw Retainer | RT-87920-74245-033-1-DD-B | 1 | 2025-08-27 |  | DONE |  | 2025-07-10: Turn,Drill; 2025-07-29: Deburr; 2025-07-30: INS; 2025-07-31: INS; 2025-08-01: Pack; 2025-08-04: Pack; 2025-08-05: Ship; 2025-08-06: Ship
72537 | 216-02123-PN-T110 | Candu | Front Support Pivot Base | RT-87920-74245-030-1-DD-B |  | 2025-08-27 |  | DONE |  | 2025-07-11: DEBURR; 2025-07-29: INS; 2025-07-30: INS; 2025-07-31: Pack; 2025-08-01: Pack
72538 | 216-02123-PN-T110 | Candu | Front Support Spacer | RT-87920-74245-029-1-DD-B |  | 2025-08-27 |  | DONE
72539 | 216-02123-PN-T110 | Candu | Base Plate | RT-87920-74245-028-1-DD-B |  | 2025-08-27 |  | DONE
72540 | 216-02123-PN-T110 | Candu | Screw Pivot | RT-87920-74245-031-1-DD-B |  | 2025-08-27 |  | DONE |  | 2025-07-11: DEBURR; 2025-07-29: INS; 2025-07-30: INS; 2025-07-31: Pack; 2025-08-01: Pack
72541 | 216-02123-PN-T110 | Candu | Coupling | RT-87920-74245-048-1-DD-B |  | 2025-09-08 |  | DONE |  | 2025-07-22: TURN; 2025-08-22: INS; 2025-08-25: A&M Cabonized; 2025-08-26: A&M Cabonized; 2025-08-27: A&M Cabonized; 2025-08-28: A&M Cabonized; 2025-08-29: A&M Cabonized; 2025-09-01: A&M Cabonized; 2025-09-02: A&M Cabonized; 2025-09-03: Receive,INS; 2025-09-04: INS; 2025-09-05: Grind; 2025-09-08: INS,DIR; 2025-09-09: INS,DIR; 2025-09-10: Pack
72542 | 216-02123-PN-T110 | Candu | Front Support Spacer | RT-87920-74245-047-1-DD-B |  | 2025-08-27 |  | DONE
72543 | 216-02123-PN-T110 | Candu | Split Collar | RT-87920-74245-024-1-DD-B |  | 2025-08-27 |  | DONE
72546 | 7000543134- Rev.1 | Safran (Messier) | LG Handling Dolly | CAT5880-2 |  | 2025-09-23 |  | Prep |  | 2025-07-28: CUT; 2025-07-29: Prep(Done); 2025-08-04: Prep; 2025-08-05: Mill(itemB); 2025-08-06: Mill(itemC）; 2025-08-07: Deburr; 2025-08-08: INS; 2025-08-11: INS; 2025-08-12: Gather All items; 2025-08-13: Fit,Tack,Weld; 2025-08-14: Fit,Tack,Weld; 2025-08-15: Deburr; 2025-08-18: INS; 2025-08-19: INS; 2025-08-20: Mill,Drill; 2025-08-21: Mill,Drill; 2025-08-22: Mill,Drill; 2025-08-25: Mill,Drill; 2025-08-26: Drill&Tap; 2025-08-27: Drill&Tap; 2025-08-28: Deburr; 2025-08-29: INS; 2025-09-01: INS; 2025-09-02: Stamp; 2025-09-03: Paint; 2025-09-04: Store for ASSY
|  |  | LG Handling Dolly | CAT5880-2 Item#4 |  |  |  | Deburr |  | 2025-07-28: Deburr
|  |  | Bottom Pivot Bracket | CAT5880-2 Item#8 | 1 |  |  | INS |  | 2025-08-04: Weld; 2025-08-05: Deburr; 2025-08-06: INS; 2025-08-07: INS; 2025-08-08: INS; 2025-08-11: INS; 2025-08-28: Black Oxide Ampere; 2025-08-29: Black Oxide Ampere; 2025-09-01: Black Oxide Ampere; 2025-09-02: Black Oxide Ampere; 2025-09-03: Black Oxide Ampere; 2025-09-04: Black Oxide Ampere; 2025-09-05: Black Oxide Ampere; 2025-09-08: Receive,INS; 2025-09-09: INS; 2025-09-10: INS
|  |  | Top Pivot Bracket | CAT5880-2 Item#9 | 1 |  |  | INS |  | 2025-08-04: Weld; 2025-08-05: Deburr; 2025-08-06: INS; 2025-08-07: INS; 2025-08-08: INS; 2025-08-11: INS; 2025-08-12: Black Oxide Ampere; 2025-08-13: Black Oxide Ampere; 2025-08-14: Black Oxide Ampere; 2025-08-15: Black Oxide Ampere; 2025-08-18: Black Oxide Ampere; 2025-08-19: Black Oxide Ampere; 2025-08-20: Black Oxide Ampere; 2025-08-21: Receive,INS; 2025-08-22: INS; 2025-08-25: INS
|  |  | L Bracket | CAT5880-2 Item#2 | 1 |  |  | Deburr |  | 2025-08-15: Deburr; 2025-08-18: INS; 2025-08-19: INS; 2025-08-20: Stamp; 2025-08-21: Stamp; 2025-08-22: Paint; 2025-08-25: Paint
|  |  | Dolly Body | CAT5880-2 Item#1 | 1 |  |  | Weld 中 |  | 2025-08-08: Prep; 2025-08-22: Weld; 2025-08-25: Weld
|  |  | Pivot Block | CAT5880-2 Item#15 | 2 |  |  | Cut |  | 2025-08-25: Cut; 2025-08-26: Mill; 2025-08-27: Mill; 2025-08-28: Drill; 2025-08-29: Drill; 2025-09-01: Drill; 2025-09-02: Drill; 2025-09-03: Deburr; 2025-09-04: INS; 2025-09-05: INS; 2025-09-08: Black Oxide; 2025-09-09: Black Oxide; 2025-09-10: Black Oxide; 2025-09-11: Black Oxide; 2025-09-12: Black Oxide; 2025-09-13: Black Oxide; 2025-09-16: Black Oxide; 2025-09-17: Receive,INS; 2025-09-18: INS; 2025-09-19: INS
|  |  | Secure Pin | CAT5880-2 Item#16 | 2 |  |  | Form |  | 2025-08-25: Cut; 2025-08-26: Turn; 2025-08-27: Turn; 2025-08-28: Drill; 2025-08-29: Form; 2025-09-01: Deburr; 2025-09-02: INS; 2025-09-03: INS; 2025-09-04: Gather all items; 2025-09-05: Weld; 2025-09-08: Weld; 2025-09-09: Deburr; 2025-09-10: INS; 2025-09-11: INS; 2025-09-12: Black Oxide; 2025-09-13: Black Oxide; 2025-09-16: Black Oxide; 2025-09-17: Black Oxide; 2025-09-18: Black Oxide; 2025-09-19: Black Oxide; 2025-09-22: Black Oxide; 2025-09-23: Receive,INS; 2025-09-24: INS; 2025-09-25: INS
|  |  | Pivot Plate | CAT5880-2 Item#6 | 1 |  |  | Cut |  | 2025-08-25: Cut; 2025-08-26: Mill; 2025-08-27: Drill; 2025-08-28: Drill; 2025-08-29: Deburr; 2025-09-01: INS; 2025-09-02: INS
|  |  | Gear Attachment | CAT5880-2 Item#5 | 1 |  |  | Mill |  | 2025-08-27: Mill; 2025-08-28: Drill; 2025-08-29: Drill; 2025-09-01: Drill; 2025-09-02: Drill; 2025-09-03: Deburr; 2025-09-04: INS; 2025-09-05: INS
72547 | 19603 | Hybrid | 4-Pis. Inj.Blk-R/W- WO#25-7006- Kyushu | NMP6-3B-Asy-R/W |  | 2025-07-30 |  | DONE
72548 | 19603 | Hybrid | Atrim HFH-R/W- WO#25-7020- Blenheim - 1.25mm | ALTRIM-HFH R/W |  | 2025-07-30
72549 | 19603 | Hybrid | Altrim HFH-R/W- WO#25-7075- Fremont - 1.25mm | ALTRIM-HFH- R/W |  | 2025-07-30
72550 | 19603 | Hybrid | 4-Pis. Inj.Blk-R/W- WO#25-7090- Fremont | NMP6-3B-Asy-R/W | 1 |  |  | DONE
72551 | 19603 | Hybrid | Atrim HFH-R/W- WO#25-7091- Fremont - 1.25mm | ALTRIM-HFH R/W
72552 | 19603 | Hybrid | Atrim HFH-R/W- WO#25-7108- Guangzhou- 1.25mm | ALTRIM-HFH R/W |  | 2025-07-30
72553 | 19603 | Hybrid | Atrim HFH-R/W- WO#25-7109- Guangzhou - 1.25mm | ALTRIM-HFH R/W
72554 | 19603 | Hybrid | 4-Pis. Inj.Blk-R/W-WO#25-7110-Guangzhou | NMP6-3B-Asy-R/W | 1 |  |  | DONE
72555 | 19603 | Hybrid | Atrim HFH-R/W- WO#25-7111- Anjo- 0.85mm | ALTRIM-HFH R/W |  | 2025-07-30
72556 | PO1020373 | M.D.A | Frame Assembly | 4038371 |  | 2025-08-26 |  | DONE
72590 | RT98-88010-PN-R008 | Candu | Gauge AS Length Gauge |  |  | 2025-09-30
|  | Candu |  | RT-88010-0052-1-DD-B |  | 2025-09-15
|  | Candu |  | RT-88010-0051-1-DD-B |  | 2025-09-15 |  | Deburr |  | 2025-08-22: Deburr; 2025-08-28: INS,DIR; 2025-08-29: INS,DIR
|  | Candu | Ring Gauge For Bore Gauge | RT-88000-70210-060-1-DD-B |  | 2025-09-15
|  | Candu | Movable Hub ASSY | RT-88000-70034-002-2-DD-D |  | 2025-09-15
|  | Candu | Moveable Hub ASSY (Opposite Hand) | RT-88000-70034-009-2-DD-D |  | 2025-09-15
|  | Candu | General ASSY | RT-88000-70034-000-1-GA-E |  | 2025-09-15
|  | Candu | Moveable Hub ASSY (Opposite Hand) | RT-88000-70034-009-1-DD-D |  | 2025-09-15 | ★Visual Examination | Cut |  | 2025-08-26: Cut; 2025-08-27: Mill; 2025-08-28: Mill; 2025-08-29: Deburr; 2025-09-01: INS; 2025-09-02: Gather all items; 2025-09-03: Weld; 2025-09-04: Weld; 2025-09-05: Deburr; 2025-09-08: INS,DIR; 2025-09-09: INS,DIR; 2025-09-10: Visual Examination; 2025-09-11: Visual Examination; 2025-09-12: Visual Examination; 2025-09-13: Visual Examination; 2025-09-16: Visual Examination; 2025-09-17: Visual Examination; 2025-09-18: Visual Examination
|  | Candu | Movable Hub ASSY | RT-88000-70034-002-1-DD-D |  | 2025-09-15
|  | Candu | General ASSY | RT-88000-70051-000-1-GA-E |  | 2025-09-15
|  | Candu | Fixed Hub | RT-88000-70034-003-1-DD-D |  | 2025-09-15
|  | Candu | Length Gauge | RT-88000-70034-001-1-DD-D |  | 2025-09-15
|  | Candu | Fixed Hub | RT-88000-70034-003-2-DD-D |  | 2025-09-15
|  | Candu | E Face Protective Cap | RT-88000-70210-044-1-DD-D |  | 2025-09-15 |  | Receive,INS |  | 2025-07-15: Receive,INS
|  | Candu | PT Category Check Tool | RT-88000-70210-041-1-DD-D |  | 2025-09-15
|  | Candu | Micrometer Extension | RT-88000-70034-112-1-DD-B |  | 2025-09-15
|  | Candu | Mount Plate1 | RT-88000-70034-102-1-DD-B |  | 2025-09-15
|  | Candu | Saddle | RT-88000-70051-004-1-DD-B |  | 2025-09-15
|  | Candu | Pipe | RT-88000-70051-002-1-DD-B |  | 2025-09-15 |  | Cut |  | 2025-08-28: Cut
|  | Candu | Guage Finger | RT-88000-70051-001-1-DD-B |  | 2025-09-15
|  | Candu | Vertical Plate 2 | RT-88000-70034-105-1-DD-B |  | 2025-09-15
|  | Candu | Tag | RT-88000-70051-006-1-DD-B |  | 2025-09-15
|  | Candu | Spring Collar | RT-88000-70034-007-1-DD-B |  | 2025-09-15 |  | Cut |  | 2025-08-28: Cut; 2025-09-02: Turn; 2025-09-03: Turn; 2025-09-04: Deburr; 2025-09-05: INS,DIR; 2025-09-08: INS,DIR
|  | Candu | Vertical Plate 1 | RT-88000-70034-100-1-DD-B |  | 2025-09-15
|  | Candu | Tag | RT-88000-70034-113-1-DD-B |  | 2025-09-15
|  | Candu | Gusset 1 | RT-88000-70034-101-1-DD-B |  | 2025-09-15 |  | Waterjet |  | 2025-08-26: Waterjet; 2025-09-02: Deburr; 2025-09-03: INS,DIR; 2025-09-04: INS,DIR
|  | Candu | Collar | RT-88000-70034-006-1-DD-B |  | 2025-09-15
|  | Candu | Gusset 2 | RT-88000-70034-106-1-DD-B |  | 2025-09-15 |  | Waterjet |  | 2025-08-26: Waterjet; 2025-08-28: Deburr; 2025-08-29: INS,DIR; 2025-09-01: INS,DIR
|  | Candu | Connecting Plug | RT-88000-70034-111-1-DD-B |  | 2025-09-15 |  | Cut |  | 2025-08-28: Cut; 2025-08-29: Turn; 2025-09-01: Turn; 2025-09-02: Deburr; 2025-09-03: INS,DIR; 2025-09-04: INS,DIR
|  | Candu | Precision Shaft | RT-88000-70034-109-1-DD-B |  | 2025-09-15
|  | Candu | Guage Tip | RT-88000-70051-005-1-DD-B |  | 2025-09-15
|  | Candu | Bar 1 | RT-88000-70034-103-1-DD-B |  | 2025-09-15
|  | Candu | Tube | RT-88000-70034-110-1-DD-B |  | 2025-09-15 |  | Cut |  | 2025-08-28: Cut; 2025-08-29: Turn; 2025-09-01: Turn; 2025-09-02: Deburr; 2025-09-03: INS,DIR; 2025-09-04: INS,DIR
|  | Candu | General ASSY | RT-88010-0050-1-GA-C |  | 2025-09-15
|  | Candu | PT Ring Gauge 1 Tool | RT-88010-0031-1-DD-B |  | 2025-09-15
|  | Candu | PT Ring Gauge 2 Tool | RT-88010-0032-1-DD-B |  | 2025-09-15
|  | Candu | PT Ring Gauge 3 Tool | RT-88010-0033-1-DD-B |  | 2025-09-15
|  | Candu | Plug Detail | RT-88010-0121-1-DD-B |  | 2025-09-15
|  | Candu | Ring Gauge (4.152") | RT-88040-0040-01-DD-C |  | 2025-09-15
|  | Candu | Gauge Block Detail | RT-88010-0120-1-DD-C |  | 2025-09-15
|  | Candu | Head Detail | RT-88010-0052-1-DD-B |  | 2025-09-15
|  | Candu | Handle Weldment | RT-88010-0051-1-DD-B |  | 2025-09-15
72557 | 1114137 | BWXT Med | GR2 Titanium Heating Block | K129412-210- Option #2 | 1 | 2025-08-15 | ★外注あり（済） | Turn |  | 2025-07-15: Titanium IND; 2025-07-29: Turn
72558 | 216-02123-PN-T117 | Candu | Rack&Pinion Manual Adaptor | RT-87730-0486-01-DD-D |  | 2025-09-17 | ★Rush | Nickel |  | 2025-08-14: Turn; 2025-08-15: Mill; 2025-08-18: Mill; 2025-08-19: Mill; 2025-08-20: Mill; 2025-08-21: Mill; 2025-08-22: Mill; 2025-08-25: Deburr; 2025-08-26: INS; 2025-08-27: EDM; 2025-08-28: EDM; 2025-08-29: EDM; 2025-09-01: EDM; 2025-09-02: EDM; 2025-09-03: CMC; 2025-09-04: CMC; 2025-09-05: CMC; 2025-09-08: CMC; 2025-09-09: CMC; 2025-09-10: CMC; 2025-09-11: CMC; 2025-09-12: Receive,INS; 2025-09-13: L-Etch; 2025-09-16: L-Etch; 2025-09-17: INS,DIR; 2025-09-18: INS,DIR; 2025-09-19: Pack; 2025-09-22: Ship
72559 | 216-02123-PN-T117 | Candu | Gripper Manual Adaptor | RT-87730-0487-01-DD-D |  | 2025-09-11 | ★Rush | EDM |  | 2025-07-29: Turn; 2025-07-30: Mill; 2025-07-31: Mill; 2025-08-01: Grind; 2025-08-04: INS; 2025-08-05: INS; 2025-08-06: INS; 2025-08-07: INS; 2025-08-08: INS; 2025-08-11: EDM; 2025-08-12: EDM; 2025-08-13: EDM; 2025-08-14: EDM; 2025-08-15: EDM; 2025-08-18: EDM; 2025-08-19: EDM; 2025-08-20: EDM; 2025-08-21: EDM; 2025-08-22: EDM; 2025-08-25: Receive,INS; 2025-08-26: CMC; 2025-08-27: CMC; 2025-08-28: CMC; 2025-08-29: CMC; 2025-09-01: CMC; 2025-09-02: CMC; 2025-09-03: CMC; 2025-09-04: Receive, INS; 2025-09-05: L-Etch; 2025-09-08: L-Etch; 2025-09-09: INS,DIR; 2025-09-10: INS,DIR; 2025-09-11: Pack; 2025-09-12: Pack; 2025-09-13: Ship
72560 | 216-02123-PN-T117 | Candu | VAS Bung-CT Guide Ram | RT-87730-0488-01-DD-D |  | 2025-09-16 | ★Rush | Receive,INS |  | 2025-07-29: Cut; 2025-07-30: Turn; 2025-07-31: Turn; 2025-08-01: Mill; 2025-08-04: Mill; 2025-08-05: Deburr; 2025-08-06: INS; 2025-08-07: INS; 2025-08-08: INS; 2025-08-11: INS; 2025-08-12: INS; 2025-08-13: INS; 2025-08-14: INS; 2025-08-15: INS; 2025-08-18: INS; 2025-08-19: INS; 2025-08-20: INS; 2025-08-21: INS; 2025-08-22: Black Anolize West-Tech/AST; 2025-08-25: Black Anolize West-Tech/AST; 2025-08-26: Black Anolize West-Tech/AST; 2025-08-27: Black Anolize West-Tech/AST; 2025-08-28: Receive,INS; 2025-08-29: INS; 2025-09-01: INS; 2025-09-02: Engrave; 2025-09-03: Engrave; 2025-09-04: Deburr; 2025-09-05: L-Etch; 2025-09-08: L-Etch; 2025-09-09: INS,DIR; 2025-09-10: INS,DIR; 2025-09-11: Pack; 2025-09-12: Pack; 2025-09-13: Ship
72561 | 25034SP-01 | ComEnCo | SS Window Frame | Sketch |  | 2025-07-31 |  | Heat treat
72568 | 4890038686 | Safran (Messier) | Roller Pin | DSK30308M03-101 | 4 | 2025-08-29 | ★HT(済),Electrokleen（72569と一緒に送る） | Passivate |  | 2025-07-30: Turn; 2025-07-31: Mill; 2025-08-01: Mill; 2025-08-04: Grind; 2025-08-05: Grind; 2025-08-06: Grind; 2025-08-07: Grind; 2025-08-08: Grind; 2025-08-11: Deburr; 2025-08-12: L-Etch; 2025-08-13: L-Etch; 2025-08-14: INS; 2025-08-15: INS; 2025-08-18: Passivate Electro Kleen; 2025-08-19: Passivate Electro Kleen; 2025-08-20: Passivate Electro Kleen; 2025-08-21: Passivate Electro Kleen; 2025-08-22: Passivate Electro Kleen; 2025-08-25: Passivate Electro Kleen; 2025-08-26: Passivate Electro Kleen; 2025-08-27: Receive,INS; 2025-08-28: INS; 2025-08-29: INS; 2025-09-01: Pack; 2025-09-02: Pack; 2025-09-03: Ship; 2025-09-18: Passivate; 2025-09-19: Passivate; 2025-09-22: Passivate; 2025-09-23: Passivate; 2025-09-24: Receive,INS; 2025-09-25: INS; 2025-09-26: Pack; 2025-09-29: Ship
72569 | 4890038686 | Safran (Messier) | Dummy Hook S475 mat'l by Safran | DSK30308M04-101 | 1 | 2025-08-29 | ★外注あり（72568と一緒に送る） | Passivate |  | 2025-07-28: HT A＆M; 2025-07-29: HT A＆M; 2025-07-30: HT A＆M; 2025-07-31: HT A＆M; 2025-08-01: HT A＆M; 2025-08-04: HT A＆M; 2025-08-05: HT A＆M; 2025-08-06: HT A＆M; 2025-08-07: HT A＆M; 2025-08-08: HT A＆M; 2025-08-11: HT A＆M; 2025-08-12: HT A＆M; 2025-08-13: HT A＆M; 2025-08-14: HT A＆M; 2025-08-15: HT A＆M; 2025-08-18: HT A＆M; 2025-08-19: HT A＆M; 2025-08-20: HT A＆M; 2025-08-21: HT A＆M; 2025-08-22: HT A＆M; 2025-08-25: Receive,INS; 2025-08-26: Cut; 2025-08-27: Cut; 2025-08-28: Mill; 2025-08-29: Mill; 2025-09-01: Drill; 2025-09-02: Drill; 2025-09-03: INS; 2025-09-04: INS; 2025-09-05: L-Etch; 2025-09-08: L-Etch; 2025-09-09: Passivate ElectroKleen; 2025-09-10: Passivate ElectroKleen; 2025-09-11: Passivate ElectroKleen; 2025-09-12: Passivate ElectroKleen; 2025-09-13: Passivate ElectroKleen; 2025-09-16: Passivate ElectroKleen; 2025-09-17: Passivate ElectroKleen; 2025-09-18: Passivate; 2025-09-19: Passivate; 2025-09-22: Passivate; 2025-09-23: Passivate; 2025-09-24: Receive,INS; 2025-09-25: INS; 2025-09-26: Pack; 2025-09-29: Ship
72569 | 4890038686 | Safran (Messier) | Dummy Hook S475 mat'l by Safran | DSK30308M04-103 | 1 | 2025-08-29 | ★外注あり（72568と一緒に送る） | Passivate |  | 2025-09-22: Nitride A＆M; 2025-09-23: Nitride A＆M; 2025-09-24: Nitride A＆M; 2025-09-25: Nitride A＆M; 2025-09-26: Nitride A＆M; 2025-09-29: Nitride A＆M; 2025-09-30: Nitride A＆M; 2025-10-01: Receive,INS; 2025-10-02: INS; 2025-10-03: L-Etch INS; 2025-10-06: Pack; 2025-10-07: Ship
72566 | 3737964-00 | DJ Ind. | Spiral Groove Drum LH ＆RH （Spiral Opp） | 31221 | 2LH+2RH | 2025-08-14 |  | Cut |  | 2025-07-23: Receive or stock; 2025-08-28: Cut; 2025-08-29: Cut; 2025-09-01: Turn; 2025-09-02: Turn; 2025-09-03: Deburr; 2025-09-04: INS; 2025-09-05: INS; 2025-09-08: Pack; 2025-09-09: Pack; 2025-09-10: Ship
72567 | 3737961-00 | DJ Ind. | Spiral Groove Drum LH ＆RH （Spiral Opp） | 31221 | 2LH+2RH | 2025-08-14 |  | Assembly |  | 2025-07-23: Assembly
72563 |  | Kinectrics | Sheave Wheel-F/I mat'l to r/w | Assem1 | 1 | 2025-07-30 |  | DONE |  | 2025-07-23: Store for ASSY
|  |  | Sheave Wheel-F/I mat'l to r/w-S.S. Plate | Aluminum Segment | 8 |  |  | DONE |  | 2025-07-18: Turn
|  |  | Sheave Wheel-F/I mat'l to r/w-Small Wheel | Sheave Wheel-1.42in, 800mm | 1 |  |  | DONE
|  |  | Sheave Wheel-F/I mat'l to r/w-UHMW Plate | UHMW Segment | 4 |  |  | DONE
72564 | PO1020435 | MDA | Frame ASSY-Extrusion,24"LG | 4033515-101 | 2 | 2025-09-10 |  | HOLD |  | 2025-07-30: Water jet; 2025-08-28: Deburr; 2025-08-29: INS; 2025-09-01: INS; 2025-09-02: Chemical Conversion Coat; 2025-09-03: Chemical Conversion Coat; 2025-09-04: Chemical Conversion Coat; 2025-09-05: Chemical Conversion Coat; 2025-09-08: Chemical Conversion Coat; 2025-09-09: Chemical Conversion Coat; 2025-09-10: Receive,INS; 2025-09-11: Receive,iINS; 2025-09-12: L-Etch; 2025-09-13: L-Etch; 2025-09-16: INS; 2025-09-17: INS
|  |  | Ring Roll | 4033510-101 | 2 | 2025-09-10 | ★外注あり | HOLD |  | 2025-07-31: Water jet; 2025-08-21: Tune; 2025-08-22: Mill; 2025-08-25: Mill; 2025-08-26: Mill; 2025-08-27: Mill; 2025-08-28: Deburr; 2025-08-29: INS; 2025-09-01: Chemical Conversion Coat; 2025-09-02: Chemical Conversion Coat; 2025-09-03: Chemical Conversion Coat; 2025-09-04: Chemical Conversion Coat; 2025-09-05: Chemical Conversion Coat; 2025-09-08: Chemical Conversion Coat; 2025-09-09: Chemical Conversion Coat; 2025-09-10: Receive,INS; 2025-09-11: Receive,INS; 2025-09-12: L-Etch; 2025-09-13: L-Etch; 2025-09-16: INS; 2025-09-17: INS; 2025-09-23: Receive,INS; 2025-09-24: water jet; 2025-09-25: Turn; 2025-09-26: Turn Hole; 2025-09-29: Hole Slot; 2025-09-30: Slot Deburr INS; 2025-10-01: Chemical Conversion Coat; 2025-10-02: Chemical Conversion Coat; 2025-10-03: Chemical Conversion Coat; 2025-10-06: Chemical Conversion Coat; 2025-10-07: Chemical Conversion Coat; 2025-10-08: Receive,INS; 2025-10-09: L-Etch INS
|  |  | PLATE MAIN | 4033507-101 | 2 | 2025-09-10 | ★Chemical Conversion Coat | HOLD
72565 | 33745678-00 | DJ Ind | Alum Rosina Quill Holder | 72565-QH | 5 | 2025-07-31 |  | Tap |  | 2025-07-31: Tap; 2025-08-01: Mill; 2025-08-04: Mill; 2025-08-05: Drill; 2025-08-06: Drill; 2025-08-07: INS; 2025-08-08: INS; 2025-08-11: Pack; 2025-08-12: Pack; 2025-08-13: Ship
72572 | 169536 #1+2 | Eclips | Main-Body-Rear Tube | RT-87850-1017-01-DD-E | 4 | 2025-10-15 |  | Deburr |  | 2025-07-28: Receive,INS; 2025-07-29: Cut; 2025-07-30: Cut; 2025-07-31: Turn; 2025-08-01: Turn; 2025-08-04: Mill; 2025-08-05: Mill; 2025-08-06: Mill; 2025-08-07: Mill; 2025-08-08: Deburr; 2025-08-11: INS,DIR; 2025-08-12: INS,DIR; 2025-08-13: Pack; 2025-08-14: Pack; 2025-08-15: Ship; 2025-08-20: Deburr; 2025-08-21: Deburr; 2025-08-22: Deburr; 2025-08-25: Deburr
72574 | 169536 #5 | Eclips | Motor Mtg End Cap | RT-87850-71100-107-1-DD-B | 4 | 2025-10-15 | ★外注あり | Cut |  | 2025-07-25: Cut
72574 | 169536 #6 | Eclips | Motor Mtg End Cap | RT-87850-71100-107-1-DD-B | 4 | 2025-10-15 | ★外注あり | Cut |  | 2025-07-25: Cut
72576 | 806794 | Woodbridge-kipling | 38-Uploading Fixture Transfer Block | RTD-3B04 (040318) | 1 | 2025-08-29 |  | Receive,INS |  | 2025-07-29: Receive,INS; 2025-07-30: Machine; 2025-07-31: Machine; 2025-08-01: Mill; 2025-08-04: Mill; 2025-08-05: Deburr; 2025-08-06: INS; 2025-08-07: INS; 2025-08-08: Pack; 2025-08-11: Pack; 2025-08-12: Ship
72577 | 806794
72580 | RT-98-88010-PN-R009 | Candu | CT Removal Thrust Sleeve-Body Protective Sleeve | RT-87000-70201-6100-1-GA-B | 1 | 2025-09-29 |  | Weld |  | 2025-08-27: Weld; 2025-08-28: Weld; 2025-08-29: Deburr; 2025-09-01: INS; 2025-09-02: Turn; 2025-09-03: Turn; 2025-09-04: Mill; 2025-09-05: Mill; 2025-09-08: Mill; 2025-09-09: Mill; 2025-09-10: Deburr; 2025-09-11: L-Etch; 2025-09-12: L-Etch; 2025-09-13: INS,DIR; 2025-09-16: INS,DIR
|  |  | Leak Test Tool Check Sleeve-Bearing | RT-87000-70201-6001-1-DD-B | 2 | 2025-09-29 |  | Waterjetcut |  | 2025-08-14: Receive,INS; 2025-08-20: Cut; 2025-08-21: Cut; 2025-08-22: Waterjet; 2025-08-25: Waterjet; 2025-08-26: Turn; 2025-08-27: Turn; 2025-08-28: Drill; 2025-08-29: Drill; 2025-09-01: Split; 2025-09-02: Split; 2025-09-03: Deburr; 2025-09-04: INS,DIR; 2025-09-05: INS,DIR
72581 | RT98-88010-PN-R009 | Candu | CT Removal Thrust Sleeve | RT-87000-70600-6000-1-GA-B | 1 | 2025-09-29 |  | HT | bar: 2025-08-27 to 2025-09-04
|  |  | Thrust Sleeve Wedge Interface | RT-87000-70600-6004-1-DD-B | 1 | 2025-09-29 |  | Turn |  | 2025-08-22: Turn; 2025-08-26: Mill; 2025-08-27: Mill; 2025-08-28: Deburr; 2025-08-29: INS,DIR; 2025-09-01: INS,DIR
|  |  | Flange Thrust Sleeve | RT-87000-70600-6102-1-DD-B | 1 | 2025-09-29 |  | Waterjetcut |  | 2025-08-22: Waterjetcut; 2025-08-26: Bore; 2025-08-27: Bore; 2025-08-28: Deburr; 2025-08-29: L-Etch; 2025-09-01: L-Etch; 2025-09-02: INS,DIR; 2025-09-03: INS,DIR
|  |  | Tube -Protective Sleeve Body | RT-87000-70201-6102-DD-B | 1 | 2025-09-29 |  | Turn |  | 2025-08-21: Turn; 2025-08-27: Deburr; 2025-08-28: INS,DIR; 2025-08-29: INS,DIR
|  |  | Shell | RT-87000-70600-6002-1-DD-B | 2 | 2025-09-29 |  | Cut |  | 2025-08-27: Cut; 2025-08-28: Turn; 2025-08-29: Turn; 2025-09-01: Deburr; 2025-09-02: INS,DIR; 2025-09-03: INS,DIR
|  |  | Bar | RT-87000-70600-6001-1-DD-B | 1 | 2025-09-29 |  | HT
|  |  | Thrust Sleeve Weldment | RT-87000-70600-6100-1-GA-B | 1 | 2025-09-29 |  | Turn |  | 2025-08-27: Turn; 2025-08-29: Mill; 2025-09-01: Mill; 2025-09-02: Deburr; 2025-09-03: L-Etch; 2025-09-04: L-Etch; 2025-09-05: INS,DIR; 2025-09-08: INS,DIR
|  |  | Aluminum | RT-8700-70600-6101-2-DD-B | 1 | 2025-09-29 |  | Turn |  | 2025-08-21: Turn; 2025-08-29: Deburr; 2025-09-01: INS,DIR; 2025-09-02: INS,DIR
72582 | RT98-88010-PN-R009 | Candu | Leak Test Tool Check Sleeve | RT98-88000-70067-000-1-GA-D | 1 | 2025-09-29 |  | Drill |  | 2025-08-11: Receive,INS; 2025-08-12: Gather All items; 2025-08-13: ASSY; 2025-08-14: ASSY; 2025-08-15: Clean; 2025-08-18: L-Etch; 2025-08-19: L-Etch; 2025-08-20: INS,DIR; 2025-08-21: INS,DIR; 2025-08-22: Pack; 2025-08-25: Pack
|  |  | Sleeve | RT-88000-70067-001-1-DD-B | 1 | 2025-09-29 |  | Turn |  | 2025-08-20: Receive; 2025-08-21: Cut; 2025-08-22: Cut; 2025-08-25: Turn; 2025-08-26: Turn; 2025-08-27: Drill; 2025-08-28: Drill; 2025-08-29: Deburr; 2025-09-01: INS,DIR; 2025-09-02: INS,DIR
72583 | RT98-88010-PN-R009 | Candu | Bore Gauge Protective Sleeve | RT-88010-0080-01-DD-B | 2 | 2025-09-29 |  | DONE
72585 |  | Speedway Pkg | Poppet Tip | 1000231 | 40 | 2025-08-14 | ★外注あり | Stainless Steel HSUN |  | 2025-07-25: Stainless Steel HSUN; 2025-07-28: Stainless Steel HSUN; 2025-07-29: Stainless Steel HSUN; 2025-07-30: Stainless Steel HSUN; 2025-07-31: Stainless Steel HSUN; 2025-08-01: Stainless Steel HSUN; 2025-08-04: Mill; 2025-08-05: Mill; 2025-08-06: Deburr; 2025-08-07: Deburr; 2025-08-08: INS; 2025-08-11: INS; 2025-08-12: Pack; 2025-08-13: Pack; 2025-08-14: Ship
72584 |  | Speedway Pkg | Poppet Rod | 1000230 | 40 | 2025-08-14 | ★外注あり | Stainless Steel HSUN |  | 2025-06-18: 1020435; 2025-07-25: Stainless Steel HSUN; 2025-07-28: Stainless Steel HSUN; 2025-07-29: Stainless Steel HSUN; 2025-07-30: Stainless Steel HSUN; 2025-07-31: Stainless Steel HSUN; 2025-08-01: Stainless Steel HSUN; 2025-08-04: Mill; 2025-08-05: Mill; 2025-08-06: Deburr; 2025-08-07: Deburr; 2025-08-08: INS; 2025-08-11: INS; 2025-08-12: Pack; 2025-08-13: Pack; 2025-08-14: Ship
72586 | 3747324-00 | DJ Ind. | Paddle Switch-Base | C500-003 | 2 | 2025-08-19 |  | DONE |  | 2025-08-11: Cut; 2025-08-12: Prep; 2025-08-13: Prep; 2025-08-14: Gather all items; 2025-08-15: Fit,Tack; 2025-08-18: Fit,Tack; 2025-08-19: INS; 2025-08-20: Weld; 2025-08-21: Weld; 2025-08-22: Deburr; 2025-08-25: INS; 2025-08-26: INS; 2025-08-27: Drill; 2025-08-28: Drill; 2025-08-29: Deburr; 2025-09-01: INS; 2025-09-02: INS; 2025-09-03: Pack; 2025-09-04: Ship
72588 | 3747324-00 | DJ Ind. | Pivot Pin | C500-003 | 2 | 2025-08-19 |  | Paint |  | 2025-07-29: CUT; 2025-07-30: Prep; 2025-07-31: Gather All items; 2025-08-01: Fit; 2025-08-04: Bore,Dill,Tap; 2025-08-05: Deburr; 2025-08-06: INS; 2025-08-07: INS; 2025-08-08: Paint; 2025-08-11: Pack; 2025-08-12: Ship
72589 | RT98-88010-PN-R008 | Candu | Gauge Expander Tool-Ring Gauge | RT-88040-0040-01-DD-C | 2 | 2025-09-30 | ★外注あり | HT |  | 2025-08-05: Receive,INS; 2025-08-06: Cut; 2025-08-07: Cut; 2025-08-08: Turn; 2025-08-11: Turn; 2025-08-12: Deburr; 2025-08-13: INS,DIR; 2025-08-14: INS,DIR; 2025-08-25: HT; 2025-08-26: HT; 2025-08-27: HT; 2025-08-28: HT; 2025-08-29: HT; 2025-09-01: HT; 2025-09-02: HT; 2025-09-03: Receive,INS; 2025-09-04: Grind; 2025-09-05: Grind; 2025-09-08: INS,DIR; 2025-09-09: INS,DIR; 2025-09-10: L-Etch; 2025-09-11: L-Etch; 2025-09-12: L-Etch; 2025-09-13: L-Etch; 2025-09-16: Pack; 2025-09-17: Pack
72590 | RT98-88010-PN-R008 | Candu | Gauge AS Lemgth Gauge | RT-88000-70034-000-1-GA-E |  | 2025-09-30
|  |  | Gauge AS Lemgth Gauge-Tag | RT-88000-70034-113-1-DD-B | 4 |  |  |  |  | 2025-08-18: Check Stock; 2025-08-19: Receive,INS; 2025-08-20: Cut; 2025-08-21: Cut; 2025-08-22: Mill; 2025-08-25: Mill; 2025-08-26: Deburr; 2025-08-27: INS,DIR; 2025-08-28: INS,DIR
|  |  | Gauge AS Lemgth Gauge-Spring Collar | RT-88000-70034-007-1-DD-B | 8 |  |  | Cut |  | 2025-08-18: Check Stock; 2025-08-19: Receive,INS; 2025-08-28: Cut; 2025-08-29: Cut; 2025-09-01: Turn; 2025-09-02: Turn; 2025-09-03: Deburr; 2025-09-04: INS,DIR; 2025-09-05: INS,DIR
|  |  | Gauge AS Lemgth Gauge-Collar | RT-88000-70034-006-1-DD-B | 4 |  |  | DONE |  | 2025-08-18: Check Stock; 2025-08-19: Receive,INS; 2025-08-20: Cut; 2025-08-21: Cut; 2025-08-22: Turn; 2025-08-25: Turn; 2025-08-26: Drill; 2025-08-27: Drill; 2025-08-28: Deburr; 2025-08-29: INS,DIR; 2025-09-01: INS,DIR
|  |  | Gauge AS Lemgth Gauge-Length Gauge | RT-88000-70034-001-1-DD-D | 4 |  |  |  |  | 2025-08-18: Receive,INS; 2025-08-19: Gather All items; 2025-08-20: ASSY; 2025-08-21: ASSY; 2025-08-22: Drill＆Ream; 2025-08-25: Drill＆Ream; 2025-08-26: Deburr; 2025-08-27: L-Etch; 2025-08-28: L-Etch; 2025-08-29: INS,DIR; 2025-09-01: INS,DIR
|  |  | Gauge AS Lemgth Gauge-Connecting Plug | RT-88000-70034-111-1-DD-B | 4 |  |  |  |  | 2025-08-18: Check Stock; 2025-08-19: Receive,INS; 2025-08-20: Cut; 2025-08-21: Cut; 2025-08-22: Turn; 2025-08-25: Turn; 2025-08-26: Deburr; 2025-08-27: INS,DIR; 2025-08-28: INS,DIR
|  |  | Gauge AS Lemgth Gauge-Precision Shaft | RT-88000-70034-109-1-DD-B | 4 |  | ★INA Shaft |  |  | 2025-08-18: INA Shaft; 2025-08-19: INA Shaft; 2025-08-20: INA Shaft; 2025-08-21: INA Shaft; 2025-08-22: INA Shaft; 2025-08-25: INA Shaft; 2025-08-26: INA Shaft; 2025-08-27: Receive,INS; 2025-08-28: INS,DIR; 2025-08-29: INS,DIR
|  |  | Gauge AS Lemgth Gauge-Tube | RT-88000-70034-110-1-DD-B | 8 |  |  |  |  | 2025-08-18: MTR; 2025-08-19: Receive,INS; 2025-08-20: Cut; 2025-08-21: Cut; 2025-08-22: Turn; 2025-08-25: Turn; 2025-08-26: Deburr; 2025-08-27: INS,DIR; 2025-08-28: INS,DIR
|  |  | Gauge AS Lemgth Gauge-Movable Hub Assy | RT-88000-70034-002-1-DD-D | 2 |  | ★Visual Examination | Cut |  | 2025-08-18: Check Stock; 2025-08-19: Receive,INS; 2025-08-28: Cut; 2025-08-29: Cut; 2025-09-01: Mill; 2025-09-02: Mill; 2025-09-03: Deburr; 2025-09-04: INS; 2025-09-05: INS; 2025-09-08: Gather All items; 2025-09-09: Fit,Tack,Weld; 2025-09-10: Fit,Tack,Weld; 2025-09-11: Deburr; 2025-09-12: INS,DIR; 2025-09-13: INS,DIR; 2025-09-16: Perfection; 2025-09-17: Perfection; 2025-09-18: Perfection; 2025-09-19: Perfection; 2025-09-22: Perfection; 2025-09-23: Perfection; 2025-09-24: Perfection
|  |  | Gauge AS Lemgth Gauge-Bar1 | RT-88000-70034-103-1-DD-B | 2 |  |  |  |  | 2025-08-18: Check Stock; 2025-08-19: Receive,INS; 2025-08-20: Cut; 2025-08-21: Cut; 2025-08-22: Turn; 2025-08-25: Turn; 2025-08-26: Deburr; 2025-08-27: INS,DIR; 2025-08-28: INS,DIR
|  |  | Gauge AS Lemgth Gauge-Gusset1 | RT-88000-70034-101-1-DD-B | 2 |  |  | Waterjet |  | 2025-08-18: Check Stock; 2025-08-19: Receive,INS; 2025-08-26: Waterjet; 2025-08-27: Waterjet; 2025-08-28: Deburr; 2025-08-29: INS,DIR; 2025-09-01: INS,DIR
|  |  | Gauge AS Lemgth Gauge-Vertical Plate1 | RT-88000-70034-100-1-DD-B | 2 |  |  |  |  | 2025-08-18: Check Stock; 2025-08-19: Receive,INS; 2025-08-20: Cut; 2025-08-21: Cut; 2025-08-22: Mill; 2025-08-25: Mill; 2025-08-26: Deburr; 2025-08-27: INS,DIR; 2025-08-28: INS,DIR
|  |  | Gauge AS Lemgth Gauge-Movable Hub Assy | RT-88000-70034-002-2-DD-D | 2 |  | ★Visual Examination |  |  | 2025-08-18: Receive,INS; 2025-08-19: Bore（Item0102）; 2025-08-20: Bore（Item0102）; 2025-08-21: Mill; 2025-08-22: Mill; 2025-08-25: Mill; 2025-08-26: Mill; 2025-08-27: Mill; 2025-08-28: Mill; 2025-08-29: Drill&Ream; 2025-09-01: Drill&Ream; 2025-09-02: Drill&Tap; 2025-09-03: Drill&Tap; 2025-09-04: Drill; 2025-09-05: Drill; 2025-09-08: Deburr; 2025-09-09: INS; 2025-09-10: INS; 2025-09-11: Paint; 2025-09-12: Paint; 2025-09-13: Gather all items; 2025-09-16: ASSY; 2025-09-17: ASSY; 2025-09-18: Grind（Item1010）; 2025-09-19: Grind（Item1010）; 2025-09-22: Clean; 2025-09-23: INS,DIR; 2025-09-24: INS,DIR
|  |  | Gauge AS Lemgth Gauge-Micrometer Extension | RT-88000-70034-0112-1-DD-B | 2 |  | ★need HT |  |  | 2025-08-18: Check Stock; 2025-08-19: Receive,INS; 2025-08-20: Cut; 2025-08-21: Cut; 2025-08-22: Turn; 2025-08-25: Turn; 2025-08-26: Mill; 2025-08-27: Mill; 2025-08-28: Deburr; 2025-08-29: INS; 2025-09-01: HT; 2025-09-02: HT; 2025-09-03: HT; 2025-09-04: HT; 2025-09-05: HT; 2025-09-08: HT; 2025-09-09: HT; 2025-09-10: Receive,INS; 2025-09-11: INS,DIR; 2025-09-12: INS,DIR
|  |  | Gauge AS Lemgth Gauge-Mount Plate1 | RT-88000-70034-0102-1-DD-B | 2 |  |  |  |  | 2025-08-18: Check Stock; 2025-08-19: Receive,INS; 2025-08-20: Cut; 2025-08-21: Cut; 2025-08-22: Mill; 2025-08-25: Mill; 2025-08-26: Deburr; 2025-08-27: INS,DIR; 2025-08-28: INS,DIR
|  |  | Gauge AS Lemgth Gauge-Fixed Hub | RT-88000-70034-003-1-DD-D | 4 |  | ★Visual Examination |  |  | 2025-08-18: Check Stock; 2025-08-19: Receive,INS; 2025-08-20: Cut; 2025-08-21: Cut; 2025-08-22: Turn(Item0107); 2025-08-25: Turn(Item10107); 2025-08-26: Mill(Item0108); 2025-08-27: Mill(Item0108); 2025-08-28: Deburr; 2025-08-29: INS; 2025-09-01: Gather All items; 2025-09-02: Fit,Tack,Weld; 2025-09-03: Fit,Tack,Weld; 2025-09-04: Deburr; 2025-09-05: INS,DIR; 2025-09-08: Perfection; 2025-09-09: Perfection; 2025-09-10: Perfection; 2025-09-11: Perfection; 2025-09-12: Perfection; 2025-09-13: Perfection; 2025-09-16: Perfection
|  |  | Gauge AS Lemgth Gauge-Gusset2 | RT-88000-70034-106-1-DD-B | 4 |  |  |  |  | 2025-08-18: Check Stock; 2025-08-19: Receive,INS; 2025-08-20: Waterjet; 2025-08-21: Waterjet; 2025-08-22: Deburr; 2025-08-25: INS,DIR; 2025-08-26: INS,DIR
|  |  | Gauge AS Lemgth Gauge-Vertical Plate2 | RT-88000-70034-105-1-DD-B | 4 |  |  |  |  | 2025-08-18: Check Stock; 2025-08-19: Receive,INS; 2025-08-20: Cut; 2025-08-21: Cut; 2025-08-22: Mill; 2025-08-25: Mill; 2025-08-26: Deburr; 2025-08-27: INS,DIR; 2025-08-28: INS,DIR
|  |  | Gauge AS Lemgth Gauge-Fixed Hub | RT-88000-70034-003-2-DD-D | 4
|  |  | Gauge AS Lemgth Gauge-Movable Hub Assy (Opposite Hand) | RT-88000-70034-009-1-DD-D | 2 |  | ★Visual Examination |  |  | 2025-08-18: Check Stock(Item0104); 2025-08-19: Receive,INS; 2025-08-26: Cut; 2025-08-27: Cut; 2025-08-28: Mill; 2025-08-29: Mill; 2025-09-01: Deburr; 2025-09-02: INS; 2025-09-03: Gather All items; 2025-09-04: Fit,Tack,Weld; 2025-09-05: Fit,Tack,Weld; 2025-09-08: Deburr; 2025-09-09: INS,DIR; 2025-09-10: INS,DIR; 2025-09-11: Perfection; 2025-09-12: Perfection; 2025-09-13: Perfection; 2025-09-16: Perfection; 2025-09-17: Perfection; 2025-09-18: Perfection; 2025-09-19: Perfection
|  |  | Gauge AS Lemgth Gauge-Bar1 | RT-88000-70034-103-1-DD-B | 2 |  |  |  |  | 2025-08-18: Check Stock; 2025-08-19: Receive,INS; 2025-08-20: Cut; 2025-08-21: Cut; 2025-08-22: Turn; 2025-08-25: Turn; 2025-08-26: Deburr; 2025-08-27: INS,DIR; 2025-08-28: INS,DIR
|  |  | Gauge AS Lemgth Gauge-Gusset1 | RT-88000-70034-101-1-DD-B | 2 |  |  |  |  | 2025-08-18: Check Stock; 2025-08-19: Receive,INS; 2025-08-20: Waterjet; 2025-08-21: Waterjet; 2025-08-22: Deburr; 2025-08-25: INS,DIR; 2025-08-26: INS,DIR
|  |  | Gauge AS Lemgth Gauge-Vertical Plate1 | RT-88000-70034-100-1-DD-B | 2 |  |  |  |  | 2025-08-18: Check Stock; 2025-08-19: Receive,INS; 2025-08-20: Cut; 2025-08-21: Cut; 2025-08-22: Mill; 2025-08-25: Mill; 2025-08-26: Deburr; 2025-08-27: INS,DIR; 2025-08-28: INS,DIR
|  |  | Gauge AS Lemgth Gauge-Movable Hub Assy (Opposite Hand) | RT-88000-70034-009-2-DD-D | 2 |  |  |  |  | 2025-08-18: Receive,INS; 2025-08-19: Bore（Item0102）; 2025-08-20: Bore（Item0102）; 2025-08-21: Mill; 2025-08-22: Mill; 2025-08-25: Mill; 2025-08-26: Mill; 2025-08-27: Mill; 2025-08-28: Mill; 2025-08-29: Drill&Ream; 2025-09-01: Drill&Ream; 2025-09-02: Drill&Tap; 2025-09-03: Drill&Tap; 2025-09-04: Drill; 2025-09-05: Drill; 2025-09-08: Deburr; 2025-09-09: INS; 2025-09-10: INS; 2025-09-11: Paint; 2025-09-12: Paint; 2025-09-13: Gather all items; 2025-09-16: ASSY; 2025-09-17: ASSY; 2025-09-18: Grind（Item1010）; 2025-09-19: Grind（Item1010）; 2025-09-22: Clean; 2025-09-23: INS,DIR; 2025-09-24: INS,DIR
|  |  | Gauge AS Lemgth Gauge-Micrometer Extension | RT-88000-70034-0112-1-DD-B | 2 |  | ★need HT |  |  | 2025-08-18: Check Stock; 2025-08-19: Receive,INS; 2025-08-20: Cut; 2025-08-21: Cut; 2025-08-22: Turn; 2025-08-25: Turn; 2025-08-26: Mill; 2025-08-27: Mill; 2025-08-28: Deburr; 2025-08-29: INS; 2025-09-01: HT; 2025-09-02: HT; 2025-09-03: HT; 2025-09-04: HT; 2025-09-05: HT; 2025-09-08: HT; 2025-09-09: HT; 2025-09-10: Receive,INS; 2025-09-11: INS,DIR; 2025-09-12: INS,DIR
|  |  | Gauge AS Lemgth Gauge-Mount Plate1 | RT-88000-70034-0102-1-DD-B | 2
72591 | RT98-88010-PN-R008 | Candu | Gauge P/T Expander Reach setting Gauge | RT-88000-70051-000-1-GA-E | 1 | 2025-09-30
|  |  | Gauge Tip | RT-88000-70051-005-1-DD-B | 1 | 2025-09-30 |  | Cut |  | 2025-08-18: Cut; 2025-08-26: Turn; 2025-08-27: Turn; 2025-08-28: Deburr; 2025-08-29: INS,DIR; 2025-09-01: INS,DIR
|  |  | Tag | RT-88000-70051-006-1-DD-B | 1 | 2025-09-30 |  | Cert |  | 2025-08-27: Cert; 2025-08-28: Receive; 2025-08-29: Cut; 2025-09-01: Cut; 2025-09-02: Mill; 2025-09-03: Mill; 2025-09-04: Deburr; 2025-09-05: INS,DIR; 2025-09-08: INS,DIR
|  |  | Gauge Finger | RT-88000-70051-01-1-DD-B | 1 | 2025-09-30 |  |  |  | 2025-08-27: Receive; 2025-08-28: Cut; 2025-08-29: Cut; 2025-09-01: Mill; 2025-09-02: Mill; 2025-09-03: Deburr; 2025-09-04: INS,DIR; 2025-09-05: INS,DIR
|  |  | Pipe | RT-88000-70051-002-1-DD-B | 1 | 2025-09-30 |  |  |  | 2025-08-27: Receive; 2025-08-28: Cut; 2025-08-29: Cut; 2025-09-01: Mill; 2025-09-02: Mill; 2025-09-03: Drill&Tap; 2025-09-04: Drill&Tap; 2025-09-05: Deburr; 2025-09-08: INS,DIR
|  |  | Saddle | RT-88000-70051-004-1-DD-B | 2
72592 | RT98-88010-PN-R008 | Candu | Pressure tube ring gauges PT ring gauge 3 Tool | RT-88010-0033-1-DD-B | 1 | 2025-09-30 | ★need HT | Receive |  | 2025-08-05: Receive; 2025-08-27: Cut; 2025-08-28: Turn; 2025-08-29: Turn; 2025-09-01: Deburr; 2025-09-02: INS,DIR; 2025-09-03: INS,DIR; 2025-09-04: HT; 2025-09-05: HT; 2025-09-08: HT; 2025-09-09: HT; 2025-09-10: HT; 2025-09-11: HT; 2025-09-12: HT; 2025-09-13: Receive,INS; 2025-09-16: Grind; 2025-09-17: Grind; 2025-09-18: INS,DIR; 2025-09-19: INS,DIR; 2025-09-22: Paint; 2025-09-23: Paint; 2025-09-24: L-Etch; 2025-09-25: L-Etch; 2025-09-26: INS; 2025-09-29: Pack
72593 | RT98-88010-PN-R008 | Candu | Gauge P/T Ring Gauge (Red) | RT-88010-0032-1-DD-B | 1 | 2025-09-30 | ★need HT |  |  | 2025-08-26: Receive,INS; 2025-08-27: Cut; 2025-08-28: Turn; 2025-08-29: Turn; 2025-09-01: Deburr; 2025-09-02: INS,DIR; 2025-09-03: INS,DIR; 2025-09-04: HT; 2025-09-05: Deburr; 2025-09-08: INS,DIR; 2025-09-09: INS,DIR; 2025-09-10: HT; 2025-09-11: Deburr; 2025-09-12: INS,DIR; 2025-09-13: Receive,INS; 2025-09-16: Grind; 2025-09-17: Grind; 2025-09-18: INS,DIR; 2025-09-19: INS,DIR; 2025-09-22: Paint; 2025-09-23: Paint; 2025-09-24: L-Etch; 2025-09-25: L-Etch; 2025-09-26: INS; 2025-09-29: Pack
72594 | RT98-88010-PN-R008 | Candu | Gauge P/T Ring Gauge(Yellow) | RT-88010-0031-1-DD-B | 1 | 2025-09-30 | ★need HT | Receive |  | 2025-08-05: Receive; 2025-08-27: Cut; 2025-08-28: Turn; 2025-08-29: Turn; 2025-09-01: Deburr; 2025-09-02: INS,DIR; 2025-09-03: INS,DIR; 2025-09-04: HT; 2025-09-05: HT; 2025-09-08: HT; 2025-09-09: HT; 2025-09-10: HT; 2025-09-11: HT; 2025-09-12: HT; 2025-09-13: Receive,INS; 2025-09-16: Grind; 2025-09-17: Grind; 2025-09-18: INS,DIR; 2025-09-19: INS,DIR; 2025-09-22: Paint; 2025-09-23: Paint; 2025-09-24: L-Etch; 2025-09-25: L-Etch; 2025-09-26: INS; 2025-09-29: Pack
72595 | RT98-88010-PN-R008 | Candu | Gauge Ring Gauge for Bore Gauge | RT-88000-70210-060-1-DD-B | 2 | 2025-09-30 | ★need HT | Receive |  | 2025-08-05: Receive; 2025-08-27: Cut; 2025-08-28: Turn; 2025-08-29: Turn; 2025-09-01: Deburr; 2025-09-02: INS,DIR; 2025-09-03: INS,DIR; 2025-09-04: HT; 2025-09-05: HT; 2025-09-08: HT; 2025-09-09: HT; 2025-09-10: HT; 2025-09-11: HT; 2025-09-12: HT; 2025-09-13: Receive,INS; 2025-09-16: Grind; 2025-09-17: Grind; 2025-09-18: L-Etch; 2025-09-19: L-Etch; 2025-09-22: INS,DIR; 2025-09-23: INS,DIR; 2025-09-24: Pack
72596 | RT98-88010-PN-R008 | Candu | Gauge P/T Category Check Tool | RT-88010-0120-1-DD-C | 2 | 2025-09-30 |  | INS,DIR ★Need to fix |  | 2025-08-21: INS,DIR; 2025-08-22: INS,DIR
72597 | RT98-88010-PN-R008 | Candu | Plug Detail | RT-88010-0121-1-DD-B | 2 | 2025-09-30 |  | Turn |  | 2025-08-22: Turn; 2025-08-25: Deburr; 2025-08-26: INS; 2025-08-27: INS; 2025-08-28: Pack
72598 | RT98-88010-PN-R008 | Candu | Gauge P/T Category Check Tool | RT-88000-70210-041-1-DD-D | 2 | 2025-09-30 |  | INS,DIR ★Need to fix |  | 2025-08-21: INS,DIR; 2025-08-22: INS,DIR
72599 | RT-88010-0050-1-GA-C | Candu | Gauge EF Liner Tube Plug Gauge | RT-88010-0050-1-GA-C | 1 | 2025-09-30
|  |  | Head Detail | RT-88010-0052-1-DD-B | 1 | 2025-09-30 |  | Receive,INS |  | 2025-07-31: Receive,INS; 2025-08-27: Cut; 2025-08-28: Turn; 2025-08-29: Turn; 2025-09-01: L-Etch; 2025-09-02: L-Etch; 2025-09-03: INS,DIR; 2025-09-04: INS,DIR
|  |  | Handle Weldment | RT-88010-0051-1-DD-B | 1 | 2025-09-30 |  | Deburr |  | 2025-08-22: Deburr; 2025-08-25: INS,DIR; 2025-08-26: INS,DIR
|  |  | E' Face Protective cap | RT-88000-70210-044-1-DD-D | 1 | 2025-09-30 |  | Receive |  | 2025-07-31: Receive; 2025-08-27: Cut; 2025-08-28: Turn; 2025-08-29: Turn; 2025-09-01: Slit; 2025-09-02: Slit; 2025-09-03: Deburr; 2025-09-04: INS,DIR; 2025-09-05: INS,DIR
72601 |  | Superwake | Rear Spar Mold | S92201-105 | 1 | 2025-08-22 |  | Cut |  | 2025-07-28: Check stock; 2025-08-04: Receive or Stock; 2025-08-05: Receive or Stock; 2025-08-19: Cut; 2025-08-20: Mill; 2025-08-21: Mill; 2025-08-22: Deburr; 2025-08-25: INS; 2025-08-26: INS; 2025-08-27: Pack; 2025-08-28: Pack
72602 | RT-98-87530-PN-R001 | Candu | Enhanced FIF Tool | RT-87530-70001-1-GA-D |  | 2025-10-28
|  |  | Central Plunger | RT-87530-70015-1-DD-C | 10 | 2025-10-28 | ★HT | Receive,INS |  | 2025-08-11: Receive,INS; 2025-08-28: Cut; 2025-08-29: HT; 2025-09-01: HT; 2025-09-02: HT; 2025-09-03: HT; 2025-09-04: HT; 2025-09-05: HT; 2025-09-08: HT; 2025-09-09: Receive,INS; 2025-09-10: Turn; 2025-09-11: Turn; 2025-09-12: Mill; 2025-09-13: Mill; 2025-09-16: Deburr; 2025-09-17: INS,DIR; 2025-09-18: INS,DIR
|  |  | Trigger | RT-87530-70011-1-DD-C | 20 | 2025-10-28 |  | Receive,INS |  | 2025-08-11: Receive,INS; 2025-08-28: Cut; 2025-08-29: Mill; 2025-09-01: Mill; 2025-09-02: Drill; 2025-09-03: Drill; 2025-09-04: Deburr; 2025-09-05: INS,DIR; 2025-09-08: INS,DIR
|  |  | Palm Grip | RT-87530-70010-1-DD-C | 20 | 2025-10-28 |  | Receive,INS |  | 2025-08-11: Receive,INS; 2025-08-28: Cut; 2025-08-29: Mill; 2025-09-01: Mill; 2025-09-02: Drill; 2025-09-03: Drill; 2025-09-04: Deburr; 2025-09-05: INS,DIR; 2025-09-08: INS,DIR
|  |  | Palm Grip | RT-87530-70009-1-DD-C | 10 | 2025-10-28 |  | Stock,INS |  | 2025-08-07: Stock,INS; 2025-08-28: Cut; 2025-08-29: Turn; 2025-09-01: Turn; 2025-09-02: Mill; 2025-09-03: Mill; 2025-09-04: Deburr; 2025-09-05: INS,DIR; 2025-09-08: INS,DIR
|  |  | Crank Arm | RT-87530-70008-1-GA-C | 10 | 2025-10-28 | ★EDM | Stock,INS |  | 2025-08-07: Stock,INS; 2025-08-28: Cut; 2025-08-29: Turn Waterjet cut; 2025-09-01: Turn Waterjet cut; 2025-09-02: Drill; 2025-09-03: Drill; 2025-09-04: Deburr; 2025-09-05: INS; 2025-09-08: INS; 2025-09-09: Form; 2025-09-10: Deburr; 2025-09-11: INS; 2025-09-12: INS; 2025-09-13: Gather all items; 2025-09-16: Weld; 2025-09-17: Weld; 2025-09-18: Deburr; 2025-09-19: INS; 2025-09-22: INS; 2025-09-23: Drill; 2025-09-24: Drill; 2025-09-25: Deburr; 2025-09-26: INS; 2025-09-29: INS; 2025-09-30: EDM; 2025-10-01: EDM; 2025-10-02: EDM; 2025-10-03: EDM; 2025-10-06: EDM; 2025-10-07: EDM; 2025-10-08: EDM; 2025-10-09: Receive,INS; 2025-10-10: INS,DIR; 2025-10-13: INS,DIR
|  |  | Screw | RT-87560-70007-1-DD-C | 10 | 2025-10-28 |  | Receive,INS |  | 2025-08-21: Receive,INS; 2025-08-28: Cut; 2025-08-29: Turn; 2025-09-01: Turn; 2025-09-02: Mill; 2025-09-03: Mill; 2025-09-04: Mill; 2025-09-05: Mill; 2025-09-08: Grind; 2025-09-09: Grind; 2025-09-10: Deburr; 2025-09-11: INS,DIR; 2025-09-12: INS,DIR
|  |  | Cover | RT-87530-70006-1-DD-C | 10 | 2025-10-28 |  | Receive,INS |  | 2025-08-07: Receive,INS; 2025-08-28: Cut; 2025-08-29: Turn; 2025-09-01: Turn; 2025-09-02: Mill; 2025-09-03: Mill; 2025-09-04: Deburr; 2025-09-05: INS,DIR; 2025-09-08: INS,DIR
|  |  | Inner Inspection Fix | RT-87530-70005-1-DD-C | 10 | 2025-10-28 |  | Receive,INS |  | 2025-08-07: Receive,INS; 2025-08-28: Cut; 2025-08-29: Turn; 2025-09-01: Turn; 2025-09-02: Drill; 2025-09-03: Drill; 2025-09-04: Drill; 2025-09-05: Drill; 2025-09-08: Deburr; 2025-09-09: INS,DIR; 2025-09-10: INS,DIR
|  |  | Inner Cone | RT-87530-70004-1-DD-C | 10 | 2025-10-28 |  | Receive,INS |  | 2025-08-21: Receive,INS; 2025-08-28: Cut; 2025-08-29: Turn; 2025-09-01: Turn; 2025-09-02: Deburr; 2025-09-03: INS,DIR; 2025-09-04: INS,DIR
|  |  | Housing | RT-87530-70003-1-DD-D | 10 | 2025-10-28 | ★HT | Receive,INS |  | 2025-08-11: Receive,INS; 2025-08-28: Cut; 2025-08-29: HT; 2025-09-01: HT; 2025-09-02: HT; 2025-09-03: HT; 2025-09-04: HT; 2025-09-05: HT; 2025-09-08: HT; 2025-09-09: Receive,INS; 2025-09-10: Turn; 2025-09-11: Turn; 2025-09-12: Mill; 2025-09-13: Mill; 2025-09-16: Mill; 2025-09-17: Mill; 2025-09-18: Deburr; 2025-09-19: Deburr; 2025-09-22: INS,DIR; 2025-09-23: INS,DIR
|  |  | Latch Tube | RT-87530-70002-1-DD-C | 10 | 2025-10-28 | ★HT | Receive,INS |  | 2025-08-21: Receive,INS; 2025-08-28: Cut; 2025-08-29: HT; 2025-09-01: HT; 2025-09-02: HT; 2025-09-03: HT; 2025-09-04: HT; 2025-09-05: HT; 2025-09-08: HT; 2025-09-09: Receive,INS; 2025-09-10: Turn; 2025-09-11: Turn; 2025-09-12: Drill; 2025-09-13: Drill; 2025-09-16: Deburr; 2025-09-17: INS,DIR; 2025-09-18: INS,DIR
72603 | RT98-87530-PN-R001 | Candu | General Inspection Fixture | 98-31952-83-1-GA-E |  | 2025-10-28
|  |  | Padded Stud ASSY | 98-31952-80-1-GA-B | 2 | 2025-10-28 |  | Gather all items |  | 2025-09-10: Gatherall items; 2025-09-11: ASSY; 2025-09-12: ASSY; 2025-09-13: Clean; 2025-09-16: INS,DIR; 2025-09-17: INS,DIR
|  |  | Nylon Stud | 98-31952-81-1-DD-B | 2 | 2025-10-28 |  | Stock,INS |  | 2025-08-08: Stock,INS; 2025-08-29: Cut; 2025-09-01: Turn; 2025-09-02: Turn; 2025-09-03: Deburr; 2025-09-04: INS,DIR; 2025-09-05: INS,DIR
|  |  | Threaded Stud | 98-31952-82-1-DD-B | 2 | 2025-10-28 |  | Receive,INS |  | 2025-08-22: Receive,INS; 2025-08-29: Cut; 2025-09-01: Turn; 2025-09-02: Turn; 2025-09-03: Drill; 2025-09-04: Drill; 2025-09-05: Deburr; 2025-09-08: INS,DIR; 2025-09-09: INS,DIR
|  |  | Latch Tube | 98-31952-84-1-DD-C | 2 | 2025-10-28 | ★HT | Receive,INS |  | 2025-08-18: Receive,INS; 2025-08-29: Cut; 2025-09-01: HT; 2025-09-02: HT; 2025-09-03: HT; 2025-09-04: HT; 2025-09-05: HT; 2025-09-08: HT; 2025-09-09: HT; 2025-09-10: Reveive,INS; 2025-09-11: Turn; 2025-09-12: Turn; 2025-09-13: Deburr; 2025-09-16: INS,DIR; 2025-09-17: INS,DIR
|  |  | Dog | 98-31952-85-1-DD-B | 4 | 2025-10-28 | ★HT | Stock,INS |  | 2025-08-07: Stock,INS; 2025-08-29: Cut; 2025-09-01: HT; 2025-09-02: HT; 2025-09-03: HT; 2025-09-04: HT; 2025-09-05: HT; 2025-09-08: HT; 2025-09-09: HT; 2025-09-10: Reveive,INS; 2025-09-11: Turn; 2025-09-12: Turn; 2025-09-13: Mill; 2025-09-16: Mill; 2025-09-17: Deburr; 2025-09-18: INS,DIR; 2025-09-19: INS,DIR
|  |  | Stud | 98-31952-86-1-DD-B | 4 | 2025-10-28 |  | Receive,INS |  | 2025-08-08: Receive,INS; 2025-08-29: Cut; 2025-09-01: Turn; 2025-09-02: Turn; 2025-09-03: Deburr; 2025-09-04: INS,DIR; 2025-09-05: INS,DIR
|  |  | Height Comparison Post | 98-31952-90-1-DD-B | 2 | 2025-10-28 |  | Receive,INS |  | 2025-08-08: Receive,INS; 2025-08-29: Cut; 2025-09-01: Turn; 2025-09-02: Turn; 2025-09-03: Drill; 2025-09-04: Drill; 2025-09-05: Grind; 2025-09-08: Grind; 2025-09-09: Deburr; 2025-09-10: L-Etch; 2025-09-11: L-Etch; 2025-09-12: INS,DIR; 2025-09-13: INS,DIR
|  |  | Crank | 98-31952-91-1-DD-C | 2 | 2025-10-28 | ★EDM | Stock,INS |  | 2025-08-08: Stock,INS; 2025-08-29: Cut Waterjet cut; 2025-09-01: Cut Waterjet cut; 2025-09-02: Turn; 2025-09-03: Turn; 2025-09-04: Deburr; 2025-09-05: INS; 2025-09-08: INS; 2025-09-09: Gather all items; 2025-09-10: Weld; 2025-09-11: Weld; 2025-09-12: Deburr; 2025-09-13: INS; 2025-09-16: INS; 2025-09-17: Drill; 2025-09-18: Drill; 2025-09-19: Drill; 2025-09-22: Drill; 2025-09-23: Deburr; 2025-09-24: INS; 2025-09-25: INS; 2025-09-26: EDM; 2025-09-29: EDM; 2025-09-30: EDM; 2025-10-01: EDM; 2025-10-02: EDM; 2025-10-03: EDM; 2025-10-06: EDM; 2025-10-07: Receive,INS; 2025-10-08: INS,DIR; 2025-10-09: INS,DIR
|  |  | Hand Knob Extension | 98-31952-92-1-DD-C | 2 | 2025-10-28 |  | Stock,INS |  | 2025-08-08: Stock,INS; 2025-08-29: Cut; 2025-09-01: Turn; 2025-09-02: Turn; 2025-09-03: Drill; 2025-09-04: Drill; 2025-09-05: Mill; 2025-09-08: Mill; 2025-09-09: Grind; 2025-09-10: Grind; 2025-09-11: Deburr; 2025-09-12: INS,DIR; 2025-09-13: INS,DIR
|  |  | Hand Knob | 98-31952-93-1-DD-C | 2 | 2025-10-28 |  | Receive,INS |  | 2025-08-08: Receive,INS; 2025-08-29: Drill; 2025-09-01: Drill; 2025-09-02: Drill; 2025-09-03: Drill; 2025-09-04: Deburr; 2025-09-05: Deburr; 2025-09-08: INS,DIR; 2025-09-09: INS,DIR
72600 |  | Superwake | Main Spar Mold "A" | S93501-105 | 1 | 2025-08-22 |  | Check stock |  | 2025-07-28: Check stock; 2025-07-31: Receive or Stock; 2025-08-01: Receive or Stock; 2025-08-04: Cut; 2025-08-05: Cut; 2025-08-06: Mill; 2025-08-07: Mill; 2025-08-08: Drill; 2025-08-11: Drill; 2025-08-12: Deburr; 2025-08-13: INS; 2025-08-14: INS; 2025-08-15: Pack; 2025-08-18: Pack; 2025-08-19: Ship
72600 |  | Superwake | Main Spar Mold "B" | S93502-105 | 1 | 2025-08-22 |  | Receive |  | 2025-07-28: Check stock; 2025-07-29: Receive; 2025-07-31: Receive or Stock; 2025-08-01: Receive or Stock; 2025-08-04: Cut; 2025-08-05: Cut; 2025-08-06: Mill; 2025-08-07: Mill; 2025-08-08: Drill; 2025-08-11: Drill; 2025-08-12: Deburr; 2025-08-13: INS; 2025-08-14: INS; 2025-08-15: Pack; 2025-08-18: Pack; 2025-08-19: Ship
72587 | 89321-Rev.1 | ATS-Corp | Weldment ASSY-Sensor Mtg Tube | 700693434 | 2 | 2025-08-15 | ★外注あり ★Need contuct | Passivate to ASTM Electro-Kleen |  | 2025-07-28: HT; 2025-07-29: HT; 2025-07-30: HT; 2025-07-31: HT; 2025-08-01: HT; 2025-08-04: HT; 2025-08-05: HT; 2025-08-06: Receive,INS; 2025-08-07: Submit Doc; 2025-08-08: Submit Doc; 2025-08-11: Receive Approval; 2025-08-12: Passivate to ASTM Electro-Kleen; 2025-08-13: Passivate to ASTM Electro-Kleen; 2025-08-14: Passivate to ASTM Electro-Kleen; 2025-08-15: Passivate to ASTM Electro-Kleen; 2025-08-18: Passivate to ASTM Electro-Kleen; 2025-08-19: Passivate to ASTM Electro-Kleen; 2025-08-20: Passivate to ASTM Electro-Kleen; 2025-08-21: Receive,INS; 2025-08-22: INS; 2025-08-25: INS; 2025-08-26: Pack; 2025-08-27: Pack; 2025-08-28: Ship
72607 | RT98-87900-PN-R002 | Candu | PT Liner Tube Gap Measuring Tool (Reactor Gace) | RT-88000-70095-000-1-GA-E | 2 | 2025-09-05 |  | Order sub parts
|  |  | PT Liner Tube Gap Measuring Tool-Outer Tube | RT-88000-70095-001-1-DD-D | 2 |  |  | Weld |  | 2025-07-29: Order MTR; 2025-08-07: Receive,INS; 2025-08-22: Weld; 2025-08-25: Deburr; 2025-08-26: INS,DIR; 2025-08-27: INS,DIR; 2025-08-28: Perfection; 2025-08-29: Perfection; 2025-09-01: Perfection; 2025-09-02: Perfection; 2025-09-03: Perfection; 2025-09-04: Perfection; 2025-09-05: Perfection
|  |  | Slide Rod | RT-88000-70095-002-1-DD-B | 2 |  |  | DONE |  | 2025-07-31: Cut; 2025-08-01: Turn; 2025-08-21: INS,DIR
|  |  | End Tongue | RT-88000-70095-003-1-DD-B | 2 |  |  | Turn |  | 2025-08-01: Cut; 2025-08-05: Turn; 2025-08-06: Turn; 2025-08-07: Drill; 2025-08-08: Drill; 2025-08-11: Deburr; 2025-08-12: INS,DIR; 2025-08-13: INS,DIR
|  |  | Rod | RT-88000-70095-007-1-DD-B | 2 |  |  | Turn |  | 2025-07-31: Cut; 2025-08-01: Turn
|  |  | Flange | RT-88000-70095-101-1-DD-B | 2 |  |  | Turn |  | 2025-07-31: Cut; 2025-08-01: Turn; 2025-08-26: Deburr; 2025-08-27: INS,DIR; 2025-08-28: INS,DIR
|  |  | Shield Plug-Plug | RT-88000-70095-010-1-DD-B | 2 |  |  | Cut |  | 2025-08-01: Cut
72610 | PO1020694 #1 | MDA | Plate,Adaptor | 4036813-101 | 1 | 2025-09-15 | material:stock ★外注あり(72610,72611,72613,72614一緒に送る) ★INS done NCR | HOLD |  | 2025-08-04: Receive,INS; 2025-08-05: Cut; 2025-08-06: Cut; 2025-08-07: Turn; 2025-08-08: Turn; 2025-08-11: Mill; 2025-08-12: Mill; 2025-08-13: Deburr; 2025-08-14: INS; 2025-08-15: INS; 2025-08-18: Chemical Conversion Coat West-Tech; 2025-08-19: Chemical Conversion Coat West-Tech; 2025-08-20: Chemical Conversion Coat West-Tech; 2025-08-21: Chemical Conversion Coat West-Tech; 2025-08-22: Chemical Conversion Coat West-Tech; 2025-08-25: Chemical Conversion Coat West-Tech; 2025-08-26: Chemical Conversion Coat West-Tech; 2025-08-27: Gather all parts; 2025-08-28: ASSY; 2025-08-29: ASSY; 2025-09-01: Clean; 2025-09-02: L-Etch; 2025-09-03: L-Etch; 2025-09-04: INS; 2025-09-05: INS; 2025-09-08: Pack; 2025-09-09: Pack; 2025-09-10: Ship
72611 | PO1020695 #1 | MDA | Mount,Readhead | 4037705-101 | 1 | 2025-09-25 | material:stock ★外注あり★Dimention out→check Gus | Receive,INS |  | 2025-08-04: Check stock; 2025-08-05: Check Stock; 2025-08-06: Stock,INS; 2025-08-07: Waterjet; 2025-08-08: Waterjet; 2025-08-11: Mill; 2025-08-12: Mill; 2025-08-13: Deburr; 2025-08-14: INS; 2025-08-15: INS; 2025-08-18: Chemical Conversion Coat West-Tech; 2025-08-19: Chemical Conversion Coat West-Tech; 2025-08-20: Chemical Conversion Coat West-Tech; 2025-08-21: Chemical Conversion Coat West-Tech; 2025-08-22: Chemical Conversion Coat West-Tech; 2025-08-25: Chemical Conversion Coat West-Tech; 2025-08-26: Chemical Conversion Coat West-Tech; 2025-08-27: Receive,INS; 2025-08-28: L-Etch; 2025-08-29: L-Etch; 2025-09-01: INS; 2025-09-02: INS; 2025-09-08: Pack; 2025-09-09: Pack; 2025-09-17: CCC; 2025-09-18: CCC; 2025-09-19: Receive,INS; 2025-09-22: INS,DIR; 2025-09-23: Pack Ship
72612 | PO1020696 #1 | MDA | Shaft,Output | 4038009-101 | 1 | 2025-09-15 | material:stock ★外注あり(72610,72611,72613,72614一緒に送る) ★Dimention out→check Gus | Passivate to ASTM Electro-Kleen |  | 2025-08-05: Check Stock; 2025-08-06: Check Stock; 2025-08-07: Stock,INS; 2025-08-08: Cut; 2025-08-11: Cut; 2025-08-12: Turn; 2025-08-13: Turn; 2025-08-14: Drill; 2025-08-15: Drill; 2025-08-18: Deburr; 2025-08-19: INS; 2025-08-20: INS; 2025-08-21: Passivate CMC Nickel; 2025-08-22: Passivate CMC Nickel; 2025-08-25: Passivate CMC Nickel; 2025-08-26: Passivate CMC Nickel; 2025-08-27: Passivate CMC Nickel; 2025-08-28: Passivate CMC Nickel; 2025-08-29: Passivate CMC Nickel; 2025-09-01: Receive,INS; 2025-09-02: L-Etch; 2025-09-03: L-Etch; 2025-09-04: INS; 2025-09-05: INS; 2025-09-08: Pack; 2025-09-09: Pack; 2025-09-17: CCC; 2025-09-18: Passivate to ASTM Electro-Kleen; 2025-09-19: Passivate to ASTM Electro-Kleen; 2025-09-22: Passivate to ASTM Electro-Kleen; 2025-09-23: Passivate to ASTM Electro-Kleen; 2025-09-24: Passivate to ASTM Electro-Kleen; 2025-09-25: INS,DIR; 2025-09-26: INS,DIR; 2025-09-29: Pack; 2025-09-30: Ship
72613 | PO1020697 #1 | MDA | Adaptor,Torque,Sensor | 4037978-101 | 1 | 2025-09-15 | material:stock ★外注あり(72610,72611,72613,72614一緒に送る) ★INS will done 8/20 NCR | HOLD |  | 2025-08-04: Receive,INS; 2025-08-05: Cut; 2025-08-06: Cut; 2025-08-07: Turn; 2025-08-08: Turn; 2025-08-11: Mill; 2025-08-12: Mill; 2025-08-13: Deburr; 2025-08-14: INS; 2025-08-15: INS; 2025-08-18: Chemical Conversion Coat West-Tech; 2025-08-19: Chemical Conversion Coat West-Tech; 2025-08-20: Chemical Conversion Coat West-Tech; 2025-08-21: Chemical Conversion Coat West-Tech; 2025-08-22: Chemical Conversion Coat West-Tech; 2025-08-25: Chemical Conversion Coat West-Tech; 2025-08-26: Chemical Conversion Coat West-Tech; 2025-08-27: Gather all parts; 2025-08-28: ASSY; 2025-08-29: ASSY; 2025-09-01: Clean; 2025-09-02: L-Etch; 2025-09-03: L-Etch; 2025-09-04: INS; 2025-09-05: INS; 2025-09-08: Pack; 2025-09-09: Pack; 2025-09-24: Receive,INS; 2025-09-25: Cut Turn Mill; 2025-09-26: Cut Turn Mill; 2025-09-29: Deburr INS; 2025-09-30: Chemical Conversion Coat; 2025-10-01: Chemical Conversion Coat; 2025-10-02: Chemical Conversion Coat; 2025-10-03: Chemical Conversion Coat; 2025-10-06: Chemical Conversion Coat; 2025-10-07: Receive,INS; 2025-10-08: INS; 2025-10-09: ASSY; 2025-10-10: Clean; 2025-10-13: L-Etch INS; 2025-10-14: Pack Ship; 2025-10-15: Pack Ship
72614 | PO1020698 #1 | MDA | Plate,Adaptor | 4036812-101 | 1 | 2025-09-15 | material:order ★外注あり(72610,72611,72613,72614一緒に送る) ★Charos Area | Receive,INS |  | 2025-08-04: Receive,INS; 2025-08-05: Waterjet; 2025-08-06: Waterjet; 2025-08-07: Mill; 2025-08-08: Mill; 2025-08-11: Deburr; 2025-08-12: INS; 2025-08-13: INS; 2025-08-18: Chemical Conversion Coat West-Tech; 2025-08-19: Chemical Conversion Coat West-Tech; 2025-08-20: Chemical Conversion Coat West-Tech; 2025-08-21: Chemical Conversion Coat West-Tech; 2025-08-22: Chemical Conversion Coat West-Tech; 2025-08-25: Chemical Conversion Coat West-Tech; 2025-08-26: Chemical Conversion Coat West-Tech; 2025-08-27: Gather all parts; 2025-08-28: ASSY; 2025-08-29: ASSY; 2025-09-01: Clean; 2025-09-02: L-Etch; 2025-09-03: L-Etch; 2025-09-04: INS; 2025-09-05: INS; 2025-09-08: Pack; 2025-09-09: Pack; 2025-09-17: CCC; 2025-09-18: CCC; 2025-09-19: Receive,INS; 2025-09-22: INS,DIR; 2025-09-23: INS,DIR; 2025-09-24: Pack; 2025-09-25: Ship
72618 | RT98-88010-PN-R011 | Candu | EF BB Bore Gauge Calibration Hub | RT-88000-70210-031-1-DD-D | 1 | 2025-08-26 |  | Drill |  | 2025-07-31: Material ordered; 2025-08-11: Receive,INS; 2025-08-12: Cut; 2025-08-13: Cut; 2025-08-14: Turn; 2025-08-15: Turn; 2025-08-18: Drill; 2025-08-19: Drill; 2025-08-20: Deburr; 2025-08-21: INS,DIR; 2025-08-22: INS,DIR; 2025-08-25: Pack; 2025-08-26: Pack; 2025-08-27: Ship
72619 | 4520025922 | Safran (Messier) | Dome | DSK30901G04-105 | 1 | 2025-08-21 |  | Receive,INS |  | 2025-07-31: Material ordered; 2025-08-06: Receive,Ins; 2025-08-07: Cut; 2025-08-08: Cut; 2025-08-11: INS; 2025-08-12: INS; 2025-08-13: Turn; 2025-08-14: Turn; 2025-08-15: Deburr; 2025-08-18: INS; 2025-08-19: INS; 2025-08-20: Pack; 2025-08-21: Ship
72620 | 211251475 | Buffalo | Plate A Weld ASSY | 2800097 | 1 | 2025-08-29 |  | Weld |  | 2025-08-20: Weld; 2025-08-26: Deburr; 2025-08-27: INS; 2025-08-28: INS; 2025-08-29: Mill; 2025-09-01: Mill; 2025-09-02: Deburr; 2025-09-03: INS; 2025-09-04: INS; 2025-09-05: Stamp; 2025-09-08: Stamp; 2025-09-09: Paint; 2025-09-10: Paint; 2025-09-11: INS; 2025-09-12: INS; 2025-09-13: Pack; 2025-09-16: Ship
72621 | RT98-87710-PN-R006 | Candu | End Shield Mesurement Tool Sys | RT-87713-0001-1-GA-D |  | 2025-11-14
|  |  | Base Detail Design | RT-87713-70010-1-DD-B | 10 | 2025-11-14 |  | Mill |  | 2025-08-13: Cut; 2025-08-26: Mill; 2025-08-27: Mill; 2025-08-28: Mill; 2025-08-29: Drill; 2025-09-01: Drill; 2025-09-02: Deburr; 2025-09-03: Deburr; 2025-09-04: INS,DIR; 2025-09-05: INS,DIR
72636 | 89468-Rev.1 | ATS-Crop | Long Extension | 700465157 | 1 | 2025-08-28 | 2025-09-26 | DIR |  | 2025-08-06: Material receive; 2025-08-11: Submit MITP; 2025-08-12: Receive approval from ATS; 2025-08-13: Receive approval from ATS; 2025-08-14: Receive approval from ATS; 2025-08-15: Cut; 2025-08-18: Cut; 2025-08-19: Weld; 2025-08-25: Deburr; 2025-08-26: INS; 2025-08-27: LPI; 2025-08-29: Turn; 2025-09-01: Drill; 2025-09-02: Deburr; 2025-09-03: L-Etch; 2025-09-04: INS,DIR; 2025-09-05: INS,DIR; 2025-09-08: Doc; 2025-09-09: Doc; 2025-09-10: Pack; 2025-09-11: Ship
72643 | RT98-87290-PN-R004 | Candu | 5 TON PUSH CART GENERAL ARRANGEMENT | RT-87290-7000-1-GA-D | 8 | 2025-12-17 | Caster will arrive at 10/15 | waiting for the parts
|  |  | 5 TON PUSH CART ASSY | RT-87290-7002-1-GA-D | 8 | 2025-12-17
|  |  | 5 TON PUSH CART WELDMENT | RT-87290-7003-1-GA-D | 8 | 2025-12-17
|  |  | PUSH CART HANDLE DETAIL | RT-87290-7004-1-GA-D | 8 | 2025-12-17
|  |  | PUSH CART HANDLE DETAIL | RT-87290-7005-1-GA-D | 8 | 2025-12-17
|  |  | PUSH CART STAINLESS STEEL COVER | RT-97290-7006-1-DD-D | 8 | 2025-12-17
72645 | RT79-87630-PN-R011 | Candu | PT Lunch Box | RT-87630-71521-1000-1-GA-E | 1 | 2025-12-11 |  | Order Material |  | 2025-11-04: ASSY; 2025-11-05: ASSY; 2025-11-06: ASSY; 2025-11-07: ASSY; 2025-11-10: ASSY; 2025-11-11: Grind; 2025-11-12: Drill; 2025-11-13: Drill; 2025-11-14: Drill; 2025-11-17: L-Etch; 2025-11-18: INS,DIR; 2025-11-19: INS,DIR; 2025-11-20: INS,DIR
|  |  | Weldment TOP BOX | RT-87630-71521-1001-2-DD-D | 1 | 2025-12-11
|  |  | FRONT PLATE | RT-87630-71521-1002-1-DD-D | 1 | 2025-12-11
|  |  | VACUUM SIDE PLATE | RT-87630-71521-1003-1-DD-D | 1 | 2025-12-11
|  |  | SIDE PLATE | RT-87630-71521-1004-1-DD-D | 1 | 2025-12-11
|  |  | TOP PLATE | RT-87630-71521-1005-1-DD-D | 1 | 2025-12-11
|  |  | FRONT GUIDE BAR | RT-87630-71521-1006-1-DD-D | 1 | 2025-12-11
|  |  | REAR GUIDE BAR | RT-87630-71521-1007-1-DD-D | 1 | 2025-12-11
|  |  | VACUUM PORT | RT-87630-71521-1008-1-DD-D | 1 | 2025-12-11
|  |  | TOP DOOR | RT-87630-71521-1009-1-DD-D | 1 | 2025-12-11
|  |  | BOTTOM PLATE | RT-87630-71521-1011-1-DD-D | 1 | 2025-12-11
|  |  | BOTTOM FRONT PLATE | RT-87630-71521-1012-1-DD-B | 2 | 2025-12-11
|  |  | TOP REAR PLATE | RT-87630-71521-1013-1-DD-D | 2 | 2025-12-11
|  |  | PT LUNCH BOX C OF G TAG | RT-87630-71521-1014-1-DD-B | 2 | 2025-12-11
|  |  | FRONT DOOR LEFT | RT-87630-71521-1015-1-DD-D | 1 | 2025-12-11
|  |  | FRONT DOOR RIGHT | RT-87630-71521-1016-1-DD-D | 1 | 2025-12-11
|  |  | POSITION INDICATOR-LUNCH BOX | RT-87630-71521-1017-1-DD-B | 2 | 2025-12-11
|  |  | REAR DOOR | RT-87630-71521-1018-1-DD-D | 1 | 2025-12-11
|  |  | END PLATE | RT-87630-71521-1019-1-DD-D | 1 | 2025-12-11
|  |  | REAR SUPPORT | RT-87630-71521-1020-1-DD-D | 1 | 2025-12-11
|  |  | ROLLER BLOCK | RT-87630-71521-1021-1-DD-B | 2 | 2025-12-11
|  |  | VACUUM SHIELD | RT-87630-71521-1023-1-DD-B | 1 | 2025-12-11
|  |  | SHIELD SUPPORT BAR | RT-87630-71521-1024-1-DD-B | 2 | 2025-12-11
|  |  | PIN BLOCK | RT-87630-71521-1025-1-DD-B | 1 | 2025-12-11
|  |  | FILLER PLATE | RT-87630-71521-1026-1-DD-B | 1 | 2025-12-11
|  |  | TAPERED GUIDE BLOCK | RT-87630-71521-1027-1-DD-B | 4 | 2025-12-11
|  |  | SMALL DIA PT HEAD HINGE SUPPORT | RT-87630-71521-1031-1-DD-D | 1 | 2025-12-11
|  |  | HEAD SUPPORT HINGE BASE | RT-87630-71521-1035-1-DD-D | 1 | 2025-12-11
|  |  | HINGED HEAD SUPPORT VEE | RT-87630-71521-1036-1-DD-B | 1 | 2025-12-11
|  |  | SHAFT | RT-87630-71521-1037-1-DD-B | 1 | 2025-12-11
|  |  | HANDLE | RT-87630-71521-1038-1-DD-B | 1 | 2025-12-11
72646 | RT79-87630-PN-R011 | Candu | VRS Baseline- PT Small OD Gripper Hd | RT-87630-71622-1000-1-GA-E | 1 | 2025-12-11 |  | waiting sub parts |  | 2025-11-10: ASSY; 2025-11-11: ASSY; 2025-11-12: ASSY; 2025-11-13: ASSY; 2025-11-14: ASSY; 2025-11-17: INS,DIR; 2025-11-18: INS,DIR; 2025-11-19: INS,DIR
|  |  | HOUSING | RT-87630-71622-1001-1-DD-D | 1 | 2025-12-11
|  |  | RAM HEAD EXTENSION | RT-87630-71622-1002-1-DD-D | 1 | 2025-12-11
|  |  | PT FLANGE | RT-87630-71622-1003-DD-D | 1 | 2025-12-11
|  |  | BUSHING | RT-87630-71622-1004-DD-B | 2 | 2025-12-11
|  |  | NOSE | RT-87630-71622-1005-DD-B | 1 | 2025-12-11
|  |  | EXPANDING COLLET | RT-87630-71622-1006-1-DD-B | 1 | 2025-12-11
|  |  | COLLET GUIDE | RT-87630-71622-1007-1-DD-B | 1 | 2025-12-11
|  |  | GUIDE BUSHING | RT-87630-71622-1008-1-DD-B | 1 | 2025-12-11
|  |  | PRESSURE PLUG | RT-87630-71622-1009-1-DD-B | 1 | 2025-12-11
|  |  | SHAFT EXTENSION | RT-87630-81622-1010-1-DD-B | 1 | 2025-12-11
|  |  | PULL ROD | RT-87630-81622-1011-1-DD-B | 1 | 2025-12-11
|  |  | SLIDE | RT-87630-71622-1012-1-DD-B | 1 | 2025-12-11
|  |  | WEDGE | RT-87630-71622-1013-1-DD-D | 1 | 2025-12-11
|  |  | JAW | RT-87630-71622-1014-1-DD-D | 2 | 2025-12-11 | HEAT TREAT Chrome Plate | MIll |  | 2025-09-30: MIll; 2025-10-01: MIll; 2025-10-02: MIll; 2025-10-03: MIll; 2025-10-06: MIll; 2025-10-07: MIll; 2025-10-08: Deburr; 2025-10-09: INS; 2025-10-10: HEAT TREAT; 2025-10-13: HEAT TREAT; 2025-10-14: HEAT TREAT; 2025-10-15: HEAT TREAT; 2025-10-16: HEAT TREAT; 2025-10-17: Receive,INS; 2025-10-20: INS; 2025-10-21: Grind; 2025-10-22: Grind; 2025-10-23: INS; 2025-10-24: Chrome Plate; 2025-10-27: Chrome Plate; 2025-10-28: Chrome Plate; 2025-10-29: Chrome Plate; 2025-10-30: Chrome Plate; 2025-10-31: Chrome Plate; 2025-11-03: Chrome Plate; 2025-11-04: Receive,INS; 2025-11-05: INS,DIR; 2025-11-06: INS,DIR; 2025-11-07: INS,DIR
|  |  | KEY | RT-87630-71622-1015-1-DD-B | 2 | 2025-12-11
72647 | RT79-87630-PN-R011 | Candu | VRS Swab Loader- Mark 2 | RT-87630-71522-1000-1-GA-E | 1 | 2025-12-11 |  | waiting sub parts |  | 2025-11-10: ASSY; 2025-11-11: ASSY; 2025-11-12: ASSY; 2025-11-13: ASSY; 2025-11-14: ASSY; 2025-11-17: L-Etch; 2025-11-18: INS,DIR; 2025-11-19: INS,DIR; 2025-11-20: INS,DIR
|  |  | BASE PLATE | RT-87630-71522-1001-1-DD-D | 1 | 2025-12-11
|  |  | BRUSH LOCATE PLUG | RT-87630-71522-1002-1-DD-B | 1 | 2025-12-11
|  |  | WINE SWAB | RT-87630-71522-1003-1-DD-B | 1 | 2025-12-11
|  |  | BRUSH MOUNTING PLATE | RT-87630-71522-1004-1-DD-B | 1 | 2025-12-11
|  |  | SWING ARM | RT-87630-71522-1005-1-DD-D | 1 | 2025-12-11
|  |  | PIVOT PLATE | RT-87630-71522-1006-1-DD-B | 1 | 2025-12-11
|  |  | SLIDE LOCK | RT-87630-71522-1007-1-DD-B | 1 | 2025-12-11
|  |  | LOADER PRESSURE FOOT | RT-87630-71522-1008-1-DD-E | 1 | 2025-12-11
|  |  | ORIENTATION BRACKET | RT-87630-71522-1009-1-DD-B | 1 | 2025-12-11
|  |  | GUIDE BLOCK | RT-87630-71522-1010-1-DD-D | 1 | 2025-12-11
|  |  | LOCK BLOCK | RT-87630-71522-1011-1-DD-B | 1 | 2025-12-11
|  |  | CLOTH SWAB | RT-87630-71522-0012-1-DD-B | 1 | 2025-12-11
72648 | 21-31732-PN-R038 | Candu | Damper shaft Bearing | NK21-B-DD-N31732-45 | 10 | 2025-09-15 |  | Turn |  | 2025-08-18: Receive; 2025-08-26: Cut; 2025-08-27: Turn; 2025-08-28: Turn; 2025-08-29: Deburr; 2025-09-01: INS,DIR; 2025-09-02: INS,DIR; 2025-09-03: Pack; 2025-09-04: Ship
72649 | RT79-87630-PN-R009 | Candu | VRS Spreader Bar | RT-87630-71710-1000-1-GA-E | 1 | 2025-10-24 |  | Load test |  | 2025-09-30: Load test; 2025-10-01: Load test; 2025-10-02: Load test; 2025-10-03: Load test; 2025-10-06: Load test; 2025-10-07: Load test; 2025-10-08: Load test
72655 | 211252397 | Baffalo | Z Axis Beam | 3371285 | 1 | 2025-10-30 | ★Rush | SandBlast |  | 2025-09-18: Prep; 2025-09-19: Weld; 2025-09-22: Weld; 2025-09-23: Weld; 2025-09-24: Weld; 2025-09-25: Weld; 2025-09-26: Weld; 2025-09-29: Weld INS; 2025-09-30: Sand Blast; 2025-10-01: Sand Blast; 2025-10-02: Sand Blast; 2025-10-03: Sand Blast; 2025-10-06: Sand Blast; 2025-10-07: Machining; 2025-10-08: Machining; 2025-10-09: Machining; 2025-10-10: Bore,Drill,Ream; 2025-10-13: Bore,Drill,Ream; 2025-10-14: Bore,Drill,Ream; 2025-10-15: Bore,Drill,Ream; 2025-10-16: INS; 2025-10-17: INS; 2025-10-20: INS; 2025-10-21: Paint; 2025-10-22: Paint; 2025-10-23: Paint; 2025-10-24: Pack; 2025-10-27: Ship
72674 | 280103799 | Kinectrics | Mounting Plate, Kid of Stages | NPD0059-DET-2223 | 1 | 2025-11-07 |  | Free Issue
72676 | 280103799 | Kinectrics | Hand Tool End Knob | NPD0059-DET-5215 | 1 | 2025-11-07 |  | Cut |  | 2025-08-25: Cut; 2025-08-27: Turn; 2025-08-28: Turn; 2025-08-29: Mill; 2025-09-01: Mill; 2025-09-02: Deburr; 2025-09-03: INS,DIR; 2025-09-04: INS,DIR; 2025-09-05: Pack
72677 | 280103799 | Kinectrics | Hand Tool Spring Dowel | NPD0059-DET-5216 | 1 | 2025-11-07 |  | Cut |  | 2025-08-25: Cut; 2025-08-27: Turn; 2025-08-28: Turn; 2025-08-29: Drill; 2025-09-01: Drill; 2025-09-02: Deburr; 2025-09-03: INS,DIR; 2025-09-04: INS,DIR; 2025-09-05: Pack
72680 | 7000545635 | Safran （Messier） | Protective Cone / Guide | CAT5881-6 | 1 | 2025-09-05 | ★Super Rush ★Ship date;9/4 | Turn |  | 2025-08-19: Receive; 2025-08-26: Cut; 2025-08-27: Turn; 2025-08-28: Turn; 2025-08-29: Deburr; 2025-09-01: Stamp; 2025-09-02: Stamp; 2025-09-03: INS; 2025-09-04: INS; 2025-09-05: Pack; 2025-09-08: Ship
72682 |  | ATS-Corp | Valve Enclosure | 700790168 | 1 | 2025-08-29 |  | Form |  | 2025-08-22: Form; 2025-08-26: Prep; 2025-08-27: Prep; 2025-08-28: Drill; 2025-08-29: Drill; 2025-09-01: Weld; 2025-09-02: Weld; 2025-09-03: Fit; 2025-09-04: Fit; 2025-09-05: Skim; 2025-09-08: Skim; 2025-09-09: Deburr; 2025-09-10: Deburr; 2025-09-11: INS; 2025-09-12: ASSY; 2025-09-13: ASSY; 2025-09-16: INS; 2025-09-17: INS; 2025-09-18: Pack; 2025-09-19: Passivate; 2025-09-22: Passivate; 2025-09-23: Passivate; 2025-09-24: Passivate; 2025-09-25: Passivate; 2025-09-26: Passivate; 2025-09-29: Passivate; 2025-09-30: Pack; 2025-10-01: Ship
|  |  | Cover Plate | 700709292 | 1 | 2025-07-23 |  | Deburr |  | 2025-08-22: Deburr; 2025-08-26: INS; 2025-08-27: INS
|  |  | Gasket | 700710259 | 1 | 2025-07-23 |  | MIll |  | 2025-08-21: Waterjet; 2025-08-22: MIll; 2025-08-25: MIll; 2025-08-26: MIll; 2025-08-27: Deburr; 2025-08-28: INS; 2025-08-29: INS
72683 | 634828-12000-52BX-R | SNC-Lavalin | Ballscrew SMR Adapter | Sketch | 1 | 2025-09-09 |  | Turn |  | 2025-08-22: Mill; 2025-08-26: Deburr; 2025-08-27: INS; 2025-08-28: INS; 2025-08-29: Gatherallitems; 2025-09-01: ASSY; 2025-09-02: ASSY; 2025-09-03: Clean; 2025-09-04: INS; 2025-09-05: INS; 2025-09-08: Turn; 2025-09-09: Tuen; 2025-09-10: Deburr; 2025-09-11: INS; 2025-09-12: INS; 2025-09-13: Pack; 2025-09-16: Ship
72684 | 4590038772 | Safran (Messier) | Base plate | DSK30308M02-101 | 1 | 2025-09-20 |  | Receive,INS |  | 2025-08-25: Receive,INS; 2025-08-27: Cut; 2025-08-28: Cut; 2025-08-29: INS; 2025-09-01: Drill; 2025-09-02: Drill; 2025-09-03: Deburr; 2025-09-04: INS; 2025-09-05: INS; 2025-09-08: Pack; 2025-09-09: Ship
72685 | 4590038772 | Safran (Messier) | Adapter plate | DSK30308M02-103 | 1 | 2025-09-20 |  | Receive,INS |  | 2025-08-25: Receive,INS; 2025-08-27: Cut; 2025-08-28: Cut; 2025-08-29: INS; 2025-09-01: Drill; 2025-09-02: Drill; 2025-09-03: INS; 2025-09-04: INS; 2025-09-05: Pack; 2025-09-08: Ship
|  |  | Clevis | DSK30308M02-109 | 1 | 2025-09-20 |  | Receive,INS |  | 2025-08-25: Receive,INS; 2025-08-27: Cut; 2025-08-28: Cut; 2025-08-29: INS; 2025-09-01: Drill; 2025-09-02: Drill; 2025-09-03: INS; 2025-09-04: INS; 2025-09-05: Pack; 2025-09-08: Ship
|  |  | Angle Block | DSK30308M02-111 | 2 | 2025-09-20 |  | Receive,INS |  | 2025-08-25: Receive,INS; 2025-08-27: Cut; 2025-08-28: Cut; 2025-08-29: INS; 2025-09-01: Mill; 2025-09-02: Mill; 2025-09-03: INS; 2025-09-04: INS; 2025-09-05: Pack
|  |  | Beam | DSK30308M02-105 | 1 | 2025-09-20 |  | Cut |  | 2025-08-28: Cut; 2025-08-29: Drill; 2025-09-01: Drill; 2025-09-02: Deburr; 2025-09-03: INS; 2025-09-04: INS; 2025-09-05: Pack
72686 | 4590038772 | Safran (Messier) | Round Tube | DSK30308M02-115 | 1 | 2025-09-20 |  | Cut |  | 2025-08-28: Cut; 2025-08-29: INS; 2025-09-01: Bore; 2025-09-02: Bore; 2025-09-03: Mill; 2025-09-04: Mill; 2025-09-05: Deburr; 2025-09-08: INS; 2025-09-09: INS
|  |  | Shaft | DSK30308M02-113 | 1 | 2025-09-20 |  | Cut |  | 2025-08-28: Cut; 2025-08-29: INS; 2025-09-01: Turn; 2025-09-02: Turn; 2025-09-03: Mill; 2025-09-04: Mill; 2025-09-05: Deburr; 2025-09-08: INS; 2025-09-09: INS
72687 | PO1021164 | MDA | Plate,Lifting Jack | 4040044-101 | 5 | 2025-09-26 |  | Receive,INS |  | 2025-08-22: HT; 2025-08-25: Receive,INS; 2025-08-26: Cut; 2025-08-27: Turn; 2025-08-28: Turn; 2025-08-29: Mill; 2025-09-01: Mill; 2025-09-02: Deburr; 2025-09-03: INS; 2025-09-04: Gather all items; 2025-09-05: ASSY; 2025-09-08: ASSY; 2025-09-09: Clean; 2025-09-10: Bag&Tag; 2025-09-11: INS,DIR; 2025-09-12: INS,DIR; 2025-09-17: CCC; 2025-09-18: CCC; 2025-09-19: Receive,INS; 2025-09-22: INS,DIR; 2025-09-23: INS,DIR; 2025-09-24: Pack; 2025-09-25: Ship
72688 | PO1021076 | MDA | Liftjack Bracket Weldment | 912E1601 | 5 | 2025-09-23 |  | Deburr |  | 2025-08-22: HT; 2025-08-25: Receive,INS; 2025-08-26: Cut; 2025-08-27: Waterjet; 2025-08-28: Mill; 2025-08-29: Mill; 2025-09-01: Deburr; 2025-09-02: INS; 2025-09-03: Gather all items; 2025-09-04: Weld; 2025-09-05: Weld; 2025-09-08: Deburr; 2025-09-09: INS; 2025-09-10: Mill; 2025-09-11: Mill; 2025-09-12: Mill; 2025-09-13: Mill; 2025-09-16: Deburr; 2025-09-17: Deburr; 2025-09-18: Pack
72709 | RT98-88010-PN-R014 | Candu | ZCRJ Equalibium Leak Test Tool | RT-88010-0001-1-GA-E | 2 | 2025-10-03 |  |  |  | 2025-09-03: Receive,INS; 2025-09-17: Gather all items; 2025-09-18: INS all items; 2025-09-19: ASSY; 2025-09-22: ASSY; 2025-09-23: ASSY; 2025-09-24: L-Etch; 2025-09-25: L-Etch; 2025-09-26: INS; 2025-09-29: INS; 2025-09-30: Functiontest; 2025-10-01: Functiontest; 2025-10-02: Pack; 2025-10-03: Ship
|  |  | PT Seal Plate-EF Steal Plate - Gauge Cover (Item2,3,4) | RT-88010-0003-1-DD-D | 2 | 2025-10-03 |  | Stock,INS |  | 2025-09-02: Stock,INS; 2025-09-03: Delrin; 2025-09-04: Delrin; 2025-09-05: Waterjet; 2025-09-08: Waterjet; 2025-09-09: Turn; 2025-09-10: Turn; 2025-09-11: Drill; 2025-09-12: Drill; 2025-09-13: Deburr; 2025-09-16: INS,DIR; 2025-09-17: INS,DIR; 2025-09-18: Apply teflon tape; 2025-09-19: Apply teflon tape; 2025-09-22: INS,DIR; 2025-09-23: INS,DIR; 2025-09-24: Turn; 2025-09-25: Turn; 2025-09-26: Mill; 2025-09-29: Mill; 2025-09-30: INS,DIR; 2025-10-01: INS,DIR
|  |  | Seal Housing | RT-88010-0002-1-DD-D | 2 | 2025-10-03 |  |  |  | 2025-09-03: Receive,INS; 2025-09-04: teflon tape; 2025-09-05: teflon tape; 2025-09-08: Turn; 2025-09-09: Turn; 2025-09-10: Face; 2025-09-11: Face; 2025-09-12: Drill; 2025-09-13: Drill; 2025-09-16: Deburr; 2025-09-17: INS,DIR; 2025-09-18: INS,DIR; 2025-09-19: Apply teflon tape; 2025-09-22: Apply teflon tape; 2025-09-24: INS,DIR; 2025-09-25: INS,DIR
72746 | PO1021394 | MDA | Block, Clamping | 4039582-101 | 1 | 2025-09-26 |  | Stock,INS |  | 2025-09-19: Cut; 2025-09-22: Turn,Bore; 2025-09-23: Drill; 2025-09-24: Deburr; 2025-09-25: INS; 2025-09-26: Chemical Conversion Coat; 2025-09-29: Chemical Conversion Coat; 2025-09-30: Chemical Conversion Coat; 2025-10-01: Chemical Conversion Coat; 2025-10-02: Chemical Conversion Coat; 2025-10-03: Receive; 2025-10-06: L-Etch; 2025-10-07: INS; 2025-10-08: Pack; 2025-10-09: Ship
72748 | PO1021397 | MDA | Ring, Compression | 4039584-101 | 1 | 2025-09-26 |  | Stock,INS |  | 2025-09-19: Cut; 2025-09-22: Turn,Bore; 2025-09-23: Deburr; 2025-09-24: INS; 2025-09-26: Chemical Conversion Coat; 2025-09-29: Chemical Conversion Coat; 2025-09-30: Chemical Conversion Coat; 2025-10-01: Chemical Conversion Coat; 2025-10-02: Chemical Conversion Coat; 2025-10-03: Receive; 2025-10-06: Bag&Tag; 2025-10-07: INS; 2025-10-08: Pack; 2025-10-09: Ship
72765 | PO1021442 | MDA | Ring, Pushing | 4039498-101 | 1 | 2025-10-10 |  | Stock,INS |  | 2025-09-19: Cut; 2025-09-22: Turn,Drill; 2025-09-23: Deburr; 2025-09-24: INS; 2025-09-26: Chemical Conversion Coat; 2025-09-29: Chemical Conversion Coat; 2025-09-30: Chemical Conversion Coat; 2025-10-01: Chemical Conversion Coat; 2025-10-02: Chemical Conversion Coat; 2025-10-03: Receive; 2025-10-06: Bag&Tag; 2025-10-07: INS; 2025-10-08: Pack; 2025-10-09: Ship
72766 | PO1021443 | MDA | Spacer, Spring | 4039876-101 | 1 | 2025-10-10 |  | Stock,INS |  | 2025-09-19: Cut; 2025-09-22: Turn; 2025-09-23: Deburr; 2025-09-24: INS; 2025-09-25: Passivate; 2025-09-26: Passivate; 2025-09-29: Passivate; 2025-09-30: Passivate; 2025-10-01: Passivate; 2025-10-02: Receive,INS; 2025-10-03: Bag&Tag; 2025-10-06: INS; 2025-10-07: Pack; 2025-10-08: Ship
72769 | 89691- Rev.4 | ATS-Corp | Retraction Tool | 700623210 | 6 | 2025-09-12 | 9/26/2025 10/9? | Receive,INS |  | 2025-09-22: Receive,INS; 2025-09-23: Cut; 2025-09-24: Turn Turn Turn Waterjet; 2025-09-25: Turn Turn Turn; 2025-09-26: Mill Form Trim/Mill; 2025-09-29: Mill Form Trim/Mill; 2025-09-30: Deburr; 2025-10-01: INS; 2025-10-02: Gather all items; 2025-10-03: Weld; 2025-10-06: Weld; 2025-10-07: Weld; 2025-10-08: Deburr; 2025-10-09: INS; 2025-10-10: Stamp; 2025-10-13: Paint; 2025-10-14: Paint; 2025-10-15: INS,DIR; 2025-10-16: INS,DIR; 2025-10-17: INS,DIR; 2025-10-20: Doc; 2025-10-21: Doc; 2025-10-22: Pack; 2025-10-23: Ship
72795 |  | Kinectrics |  | K-940121-DET-7101 | 1
72796 |  | Kinectrics |  | K-940121-DET-7101
72797 |  | Kinectrics
72798 |  | Kinectrics
72799 |  | Kinectrics
72800 | PO1021744 | MDA | Plate, Master | 4038641 | 1 | 2025-10-31 |  |  |  | 2025-09-29: Waterjet; 2025-09-30: Mill; 2025-10-01: Mill Receive, INS; 2025-10-02: Mill Drill; 2025-10-03: Drill; 2025-10-06: Deburr; 2025-10-07: INS; 2025-10-08: INS; 2025-10-09: Chemical Conversion Coat; 2025-10-10: Chemical Conversion Coat; 2025-10-13: Chemical Conversion Coat; 2025-10-14: Chemical Conversion Coat; 2025-10-15: Chemical Conversion Coat; 2025-10-16: Chemical Conversion Coat; 2025-10-17: Chemical Conversion Coat; 2025-10-20: Receive,INS; 2025-10-21: ASSY; 2025-10-22: L-Etch; 2025-10-23: INS; 2025-10-24: INS; 2025-10-27: Pack; 2025-10-28: Ship
72801 | PO1021745 | MDA | Plate, Adapter | 4038642 | 1 | 2025-10-31
72808 | 280104654 | Kinectrics | MV Insulating Cap | NPD0059-7-DET-2558 | 2 | 2025-10-29
72809 | 280104654 | Kinectrics | Dock Insulating Standoff | NPD0059-7-DET-2536 | 4 | 2025-10-29
72810 | 280104654 | Kinectrics | Supression Insulating Standoff | NPD0059-7-DET-2545 | 4 | 2025-10-29

## DELIVERY SCHEDULE
O.E.: | Job #: | Customer: | Qty.: | Part # | Rev | Contact: | DWG Rel. | M | Descriptions: | Price: | P.O. : | Packing Slip | Qty.: | Invoice: | Del. Req'd: | Del. Ship'd: | Delay:
37721 | 69279 | MHI-Canada | 40 | GM223-1314-10 |  | Lana Bozic | 2023-04-06 | 2 | Angle | 523.72 | 51001 |  |  |  | 2024-03-07
37721 | 69279 | MHI-Canada | 40 | GM223-1314-9 |  | Lana Bozic | 2023-04-06 | 4 | Angle | 523.72 | 51001 |  |  |  | 2024-03-07
37832 | 69605 | BWXT Med | 2850 | K125912-003 | Iss. D | Krista Lentz | 2023-06-12 | 1 | Vial Shield Assy | 20.26 | 1109596 |  |  |  | 2023-07-28
37832 | 69605 | BWXT Med | 2850 | K125912-003 | Iss. D | Krista Lentz | 2023-06-12 | 2 | Vial Shield Assy | 20.26 | 1109596 |  |  |  | 2002-08-30
37832 | 69605 | BWXT Med | 2850 | K125912-003 | Iss. D | Krista Lentz | 2023-06-12 | 3 | Vial Shield Assy | 20.26 | 1109596 |  |  |  | 2023-09-29
37832 | 69605 | BWXT Med | 2850 | K125912-003 | Iss. D | Krista Lentz | 2023-06-12 | 4 | Vial Shield Assy | 20.26 | 1109596 |  |  |  | 2023-10-30
37832 | 69605 | BWXT Med | 2850 | K125912-003 | Iss. D | Krista Lentz | 2023-06-12 | 5 | Vial Shield Assy | 20.26 | 1109596 |  |  |  | 2023-11-30
37832 | 69605 | BWXT Med | 2850 | K125912-003 | Iss. D | Krista Lentz | 2023-06-12 | 6 | Vial Shield Assy | 20.26 | 1109596 |  |  |  | 2023-12-22
37979 | 70131 | Kipling | 1 | 052PLNAY01 | C00 | Aziza Arora | 2023-09-14 | 1 | Servo Guard Assy | 2125 | 804554 |  |  |  | 2023-10-05
38123 | 70586 | SNC-Lavalin | 1 | RT38-88080-0104-001-DD-1 | 1 | Ping He | 2024-01-09 | 21 | Toggle Clamp | 1188 | 634828-18000-52X-R231- R.03 |  |  |  | 2024-01-31
38170 | 70677 | BWXT Prec (Laker) | 2 | NK29-GEK-35367-0115 | 2 | Saadhna Bisram | 2024-02-08 | 1 | Lifting Rod Assy | 9840 | 4922243375-0 |  |  |  | 2024-03-28
38457 | 71276 | Candu | 3 | 98-35215-9-1-DD-D | 3 | Cindy Weng | 2024-09-03 | 1 | Link Holder F/I To Sink EDM | 3576 | 98-35215-PN-R019-R.1 |  |  |  | 2024-09-20
38502 | 71374 | Woodbridge | 3 | MZ2x2-D-N-S7N |  | Bobby Borshanpour | 2024-10-03 | 1 | Mz2x2-D Injector Nozzle | 675 | 20030822 |  |  |  | 2024-10-25
38502 | 71375 | Woodbridge | 3 | MZ2x2-D-AI-PIS | C | Bobby Borshanpour | 2024-10-03 | 2 | MZ2x2-D-AI-Piston | 1250 | 20030822 |  |  |  | 2024-10-25
38539 | 71480 | SNC-Lavalin | 5 | 21RT-88030-0182-01-DD-2-R/W | 0 | Vishnu Joshi | 2024-10-28 | 1 | Bayonet - F/I for Swaging | 700 | 634828-15000-52BX-R079-Rev.07 |  |  |  | 2024-11-11
38559 | 71512 | DJ Ind. | 2 | Sample |  | Chris Morrison | 2024-11-01 | 1 | SS. Air Curtain - Modified | [5 empty] | 2024-11-08
38608 | 71609 | Candu | 46 | 08-63500-0233-01-DD-2 | 5 | Ashan Syed | 2024-11-26 | 1 | Insert Housing Size 36-NEL-IH-36-00 | 269 | 87-63500-PN-R010 |  |  |  | 2025-04-14
38608 | 71610 | Candu | 65 | 08-63500-0252-01-DD-2 | 3 | Ashan Syed | 2024-11-26 | 2 | Insert Housing Size 24-NEL-IH-24-00 | 265 | 87-63500-PN-R010 |  |  |  | 2025-04-14
38608 | 71611 | Candu | 1100 | 08-63500-0224-01-DD-2 | 0 | Ashan Syed | 2024-11-26 | 4 | Pin Size 16-16 - NEL-PN-00-1616 | 13.95 | 87-63500-PN-R010 |  |  |  | 2025-04-14
38608 | 71612 | Candu | 1600 | 08-63500-0222-01-DD-2 | 0 | Ashan Syed | 2024-11-26 | 5 | Pin Size 16,20 - NEL-PN-00-1620 | 14.49 | 87-63500-PN-R010 |  |  |  | 2025-04-14
38608 | 71613 | Candu | 3500 | 08-63500-0229-01-DD-3 | 2 | Ashan Syed | 2024-11-26 | 6 | Contact Clip Size 16- NEL-CC-00-16 | 3.08 | 87-63500-PN-R010 |  |  |  | 2025-04-14
38615 | 71635 | Candu | 1 | RT-88000-70066-000-1-GA-D | 0 | Sanchia Bartley- Nddiaye | 2024-12-02 | 1 | Helium Leak Test Tool | 12681 | RT79-88010-PN-R003 |  |  |  | 2025-02-21
38615 | 71636 | Candu | 7 | RT-88000-70146-000-1-GA-E | 3 | Sanchia Bartley- Nddiaye | 2024-12-02 | 2 | Liner Tube Protective Sleeve | 2548 | RT79-88010-PN-R003 |  |  |  | 2025-02-21
38615 | 71637 | Candu | 2 | RT-88000-70069-000-1-GA-D | 1 | Sanchia Bartley- Nddiaye | 2024-12-02 | 3 | Helium Spray Tool | 1477 | RT79-88010-PN-R003 |  |  |  | 2025-02-21
38615 | 71638 | Candu | 17 | RT-88000-70038-000-1-GA-D | 1 | Sanchia Bartley- Nddiaye | 2024-12-02 | 4 | E/F Protective Sleeve | 1799 | RT79-88010-PN-R003 |  |  |  | 2025-02-21
38615 | 71639 | Candu | 4 | 80-01-00001-PRT- (Purchase) |  | Sanchia Bartley- Nddiaye | 2024-12-02 | 5 | Spring Loaded Centre Punch | 62 | RT79-88010-PN-R003 |  |  |  | 2025-02-21
38615 | 71640 | Candu | 2 | RT-88000-70068-000-1-GA-D | 1 | Sanchia Bartley- Nddiaye | 2024-12-02 | 6 | Vacuum Hose for Helium Leak Test | 2548 | RT79-88010-PN-R003 |  |  |  | 2025-02-21
38615 | 71641 | Candu | 5 | RT-0055-000-PRT ( Purchase) |  | Sanchia Bartley- Nddiaye | 2024-12-02 | 7 | Air Motor Socket | 2199 | RT79-88010-PN-R003 |  |  |  | 2025-02-21
38615 | 71642 | Candu | 2 | RT-88010-0005-01-GA-E | 1 | Sanchia Bartley- Nddiaye | 2024-12-02 | 8 | Calibrated Measuring Tape | 2998 | RT79-88010-PN-R003 |  |  |  | 2025-02-21
38615 | 71644 | Candu | 6 | RT-88000-70047-000-1-GA-D | 2 | Sanchia Bartley- Nddiaye | 2024-12-02 | 10 | Seal Face Protective Sleeve | 1799 | RT79-88010-PN-R003 |  |  |  | 2025-02-21
38616 | 71645 | Candu | 2 | RT-87540-0206-01-GA-E | 1 | David Weldon | 2024-12-02 | 1 | Removal PA Tool Cart-RT-7538-000-PRT | 16293 | RT79-87540-PN-R003 |  |  |  | 2025-04-11
38616 | 71646 | Candu | 16 | RT-87540-0105-01-GA-0 |  | David Weldon | 2024-12-02 | 2 | Yoke Removal/Inst Tool- RT-7545-000-PRT | 1985 | RT79-87540-PN-R003 |  |  |  | 2025-04-11
38616 | 71647 | Candu | 8 | RT-87540-0112-01-GA-2 |  | David Weldon | 2024-12-02 | 3 | Sheared Pin Punch Tool | 1935 | RT79-87540-PN-R003 |  |  |  | 2025-04-11
38616 | 71648 | Candu | 7 | RT-87540-0115-01-DD-2 |  | David Weldon | 2024-12-02 | 4 | Pin Holder- RT-8544-001- PRT | 258 | RT79-87540-PN-R003 |  |  |  | 2025-04-11
38616 | 71649 | Candu | 28 | RT-87540-0111-01-DD-2 |  | David Weldon | 2024-12-02 | 5 | Punch Pin- RT-8063-001-PRT | 188 | RT79-87540-PN-R003 |  |  |  | 2025-04-11
38616 | 71650 | Candu | 10 | RT-87540-0148-01-GA-2 |  | David Weldon | 2024-12-02 | 6 | Thread Hole Insp Tool LG- RT-7536-000-PRT | 1936 | RT79-87540-PN-R003 |  |  |  | 2025-04-11
38616 | 71651 | Candu | 10 | RT-87540-0184-01-GA-2 |  | David Weldon | 2024-12-02 | 7 | Thread Hole Repair Tool- RT-7536-000-PRT | 1195 | RT79-87540-PN-R003 |  |  |  | 2025-04-11
38616 | 71652 | Candu | 14 | RT-87540-0147-01-GA-2 |  | David Weldon | 2024-12-02 | 8 | Threaded Hole Insp Tool Lg- MOD | 568 | RT79-87540-PN-R003 |  |  |  | 2025-04-11
38616 | 71653 | Candu | 8 | RT-87540-0196-1-GA-E |  | David Weldon | 2024-12-02 | 9 | Foam Tray - RT-7547-001-PRT | 498 | RT79-87540-PN-R003 |  |  |  | 2025-04-11
38616 | 71654 | Candu | 8 | RT-87540-0107-1-DD-2 |  | David Weldon | 2024-12-02 | 10 | Nut Adjuster - RT-7542 | 1155 | RT79-87540-PN-R003 |  |  |  | 2025-04-11
38616 | 71655 | Candu | 8 | RT-87540-0109-01-GA-2 |  | David Weldon | 2024-12-02 | 11 | Spirol Pin Rem. Tool- RT-7543-000-PRT | 1357 | RT79-87540-PN-R003 |  |  |  | 2025-04-11
38616 | 71656 | Candu | 8 | RT-87540-0118-01-GA-D |  | David Weldon | 2024-12-02 | 12 | Catch Tray - RT-7547-000-PRT | 780 | RT79-87540-PN-R003 |  |  |  | 2025-04-11
38616 | 71657 | Candu | 8 | RT-87540-0117-1-GA-2 |  | David Weldon | 2024-12-02 | 13 | Stud Removal Tool - RT-7546-000-PRT | 754 | RT79-87540-PN-R003 |  |  |  | 2025-04-11
38616 | 71658 | Candu | 8 | RT-87540-0174-1-GA-0 |  | David Weldon | 2024-12-02 | 14 | Spring Pin Removal Tool - RT-7549-000-PRT | 4828 | RT79-87540-PN-R003 |  |  |  | 2025-04-11
38616 | 71659 | Candu | 8 | RT-87540-0101-01-GA-2 |  | David Weldon | 2024-12-02 | 15 | Yoke Ret. Clamp - RT-7541-000-PRT | 665 | RT79-87540-PN-R003 |  |  |  | 2025-04-11
38616 | 71660 | Candu | 8 | RT-87540-0178-01-GA-2 |  | David Weldon | 2024-12-02 | 16 | Spacer Clip Rem. Tool - RT-7541-000-PRT | 639 | RT79-87540-PN-R003 |  |  |  | 2025-04-11
38619 | 71669 | Candu | 5 | RT-87920-0351-01-GA-D | 0 | David Weldon | 2024-12-03 | 1 | CTI Bore Gauge | 34988 | RT79-87920-PN-R005 |  |  |  | 2025-03-21
38631 | 71699 | Candu | 2 | MCR-17300-030-00000-01-GA-E |  | Laila Parveen | 2024-12-06 | 3 | Anul Spacer Det.Tol-It#6,7,10,12,13,14,15,16,19,20,22,&23 | 20963 | MCR-17000-PN-R047- Rev.4 |  |  |  | Mar-21-25
38633 | 71710 | Candu | 3 | RT-88000-70085-000-1-GA-E | 1 | David Weldon | 2024-12-06 | 1 | PT Straightening Tool | 13925 | RT79-88040-PN-R002-R.1 |  |  |  | 2025-07-08
38633 | 71711 | Candu | 3 | RT-88000-70086-000-1-GA-E | B | David Weldon | 2024-12-06 | 2 | Actuator Tool | 5097 | RT79-88040-PN-R002-R.1 |  |  |  | 2024-03-11
38633 | 71712 | Candu | 3 | RT-88000-70118-000-1-GA-E | 2 | David Weldon | 2024-12-06 | 3 | EF/PT Guide Tool ( New) | 20139 | RT79-88040-PN-R002-R.1 |  |  |  | 2024-03-11
38633 | 71713 | Candu | 4 | RT-88030-0080-01-GA-C | 0 | David Weldon | 2024-12-06 | 5 | SSDO Saddle | 7704 | RT79-88040-PN-R002-R.1 |  |  |  | 2024-03-11
38633 | 71714 | Candu | 1 | RT-88000-70103-016-1-GA-D | 0 | David Weldon | 2024-12-06 | 6 | Removal Tool Trough | 5546 | RT79-88040-PN-R002-R.1 |  |  |  | 2024-03-11
38636 | 71717 | Woodbridge | 60000 | RTD-3040/3033 |  | James Kearns | 2024-12-10 | 1 | Puffer Caps & Nozzles 34 x 40 mesh | 3.44 | PD-20551 |  |  |  | 2025-12-01
38636 | 71718 | Woodbridge | 55500 | RTD-3040/3033 |  | James Kearns | 2024-12-10 | 2 | Puffer Caps & Nozzles 34 x 50 Mesh | 3.44 | PD-20551 |  |  |  | 2025-12-01
38644 | 71730 | Candu | 3 | RT-87540-0169-1-DD-2 |  | Brandon Kwakye-Longdon | 2024-12-12 | 1 | Positioning Stud Rotation tool | 794 | RT79-87540-PN-R001-R.1 |  |  |  | 2025-02-28
38644 | 71731 | Candu | 3 | RT-87540-0123-1-GA-1 |  | Brandon Kwakye-Longdon | 2024-12-12 | 2 | Spacer Clip Installation Tool | 1241 | RT79-87540-PN-R001-R.1 |  |  |  | 2025-02-28
38644 | 71732 | Candu | 3 | RT-87540-0120-1-GA-2 |  | Brandon Kwakye-Longdon | 2024-12-12 | 3 | Temporary Yoke Pin | 825 | RT79-87540-PN-R001-R.1 |  |  |  | 2025-02-28
38644 | 71733 | Candu | 3 | RT-87540-0205-1-DD-2 |  | Brandon Kwakye-Longdon | 2024-12-12 | 4 | Spring Pin Installation Spacer | 520 | RT79-87540-PN-R001-R.1 |  |  |  | 2025-02-28
38644 | 71734 | Candu | 7 | RT-87540-0144-1-GA-2 |  | Brandon Kwakye-Longdon | 2024-12-12 | 5 | Threaded Hole Insp. Tool ( Short) | 2017 | RT79-87540-PN-R001-R.1 |  |  |  | 2025-02-28
38644 | 71735 | Candu | 7 | RT-87540-0186-1-GA-2 |  | Brandon Kwakye-Longdon | 2024-12-12 | 6 | Threaded Hole Repairing tool ( Short) | 1350 | RT79-87540-PN-R001-R.1 |  |  |  | 2025-02-28
38644 | 71736 | Candu | 7 | RT-87540-0137-1-GA-2 |  | Brandon Kwakye-Longdon | 2024-12-12 | 7 | Spring Pin Insetion Tool | 1827 | RT79-87540-PN-R001-R.1 |  |  |  | 2025-02-28
38644 | 71737 | Candu | 14 | RT-87540-0140-1-DD-2 |  | Brandon Kwakye-Longdon | 2024-12-12 | 8 | Spring Pin Holder | 174 | RT79-87540-PN-R001-R.1 |  |  |  | 2025-02-28
38644 | 71738 | Candu | 14 | RT-87540-0125-1-DD-2 |  | Brandon Kwakye-Longdon | 2024-12-12 | 9 | PA Spacer Clip Inst. Tool- Detent Pin Mod | 138 | RT79-87540-PN-R001-R.1 |  |  |  | 2025-02-28
38644 | 71739 | Candu | 1 | RT-87600-0250-1-GA-E |  | Brandon Kwakye-Longdon | 2024-12-12 | 10 | Lattice Sleeve Rem. Tool HWT Mounted | 43580 | RT79-87540-PN-R001-R.1 |  |  |  | 2025-02-28
38644 | 71999 | Candu | 4 | RT-87540-0166-01-GA-E |  | Brandon Kwakye-Longdon | 2025-01-31 | 11 | Yoke Pin Replacement Tool | 3624 | RT79-87540-PN-R001-R.1
38647 | 71742 | Candu | 5 | RT-87920-0351-01-GA-D | 0 | David Weldon | 2024-12-03 | 1 | CTI Bore Gauge | 34988 | RT98-87920-PN-R006 |  |  |  | 2025-03-21
38648 | 71743 | Candu | 3 | RT-87920-0353-01-GA-C |  | Angelica de la Barrrera | 2024-12-16 | 1 | Leak Test Vacuum Grease Clean'g tool | 6273 | RT79-87920-PN-R006 |  |  |  | 2025-04-11
38648 | 71744 | Candu | 4 | RT-87920-0357-01-GA-C |  | Angelica de la Barrrera | 2024-12-16 | 2 | CTI Cleaning Tool | 4910 | RT79-87920-PN-R006 |  |  |  | 2025-04-11
38648 | 71745 | Candu | 8 | RT38-16300-024-000-0000-000-01-GA-C |  | Angelica de la Barrrera | 2024-12-16 | 3 | CTI Cleaning Tool - Head | 2317 | RT79-87920-PN-R006 |  |  |  | 2025-04-11
38648 | 71746 | Candu | 4 | RT-87920-0355-01-GA-C |  | Angelica de la Barrrera | 2024-12-16 | 4 | Vacuum Grease Cleaning Tool | 3497 | RT79-87920-PN-R006 |  |  |  | 2025-04-11
38669 | 71829 | Candu | 9 | RT-87540-0206-01-GA-E | 1 | David Weldon | 2024-12-23 | 1 | Removal PA Tool Cart-RT-7538-000-PRT | 16293 | RT98-87540-PN-R001 |  |  |  | 2025-05-02
38669 | 71830 | Candu | 16 | RT-87540-0105-01-GA-0 |  | David Weldon | 2024-12-23 | 2 | Yoke Removal/Inst Tool- RT-7545-000-PRT | 1985 | RT98-87540-PN-R001 |  |  |  | 2025-05-02
38669 | 71831 | Candu | 8 | RT-87540-0112-01-GA-2 |  | David Weldon | 2024-12-23 | 3 | Sheared Pin Punch Tool | 1935 | RT98-87540-PN-R001 |  |  |  | 2025-05-02
38669 | 71832 | Candu | 7 | RT-87540-0115-01-DD-2 |  | David Weldon | 2024-12-23 | 4 | Pin Holder- RT-7544-001- PRT | 258 | RT98-87540-PN-R001 |  |  |  | 2025-05-02
38669 | 71833 | Candu | 28 | RT-87540-0111-01-DD-2 |  | David Weldon | 2024-12-23 | 5 | Punch Pin- RT-8063-001-PRT | 188 | RT98-87540-PN-R001 |  |  |  | 2025-05-02
38669 | 650 | Candu | 11 | RT-87540-0148-01-GA-2 |  | David Weldon | 2024-12-23 | 6 | Thread Hole Insp Tool LG- RT-7536-000-PRT | 1936 | RT98-87540-PN-R001 |  |  |  | 2025-05-02
38669 | 71835 | Candu | 11 | RT-87540-0184-01-GA-2 |  | David Weldon | 2024-12-23 | 7 | Thread Hole Repair Tool- RT-7539-000-PRT | 1195 | RT98-87540-PN-R001 |  |  |  | 2025-05-02
38669 | 71836 | Candu | 14 | RT-87540-0147-01-GA-2 |  | David Weldon | 2024-12-23 | 8 | Threaded Hole Insp Tool Lg- MOD | 568 | RT98-87540-PN-R001 |  |  |  | 2025-05-02
38669 | 71837 | Candu | 8 | RT-87540-0196-1-GA-E |  | David Weldon | 2024-12-23 | 9 |  | 498 | RT98-87540-PN-R001 |  |  |  | 2025-05-02
38669 | 71838 | Candu | 8 | RT-87540-0107-1-DD-2 |  | David Weldon | 2024-12-23 | 10 | Nut Adjuster - RT-7542 | 1155 | RT98-87540-PN-R001 |  |  |  | 2025-05-02
38669 | 71839 | Candu | 8 | RT-87540-0109-01-GA-2 |  | David Weldon | 2024-12-23 | 11 | Spirol Pin Rem. Tool- RT-7543-000-PRT | 1357 | RT98-87540-PN-R001 |  |  |  | 2025-05-02
38669 | 71840 | Candu | 8 | RT-87540-0118-01-GA-D |  | David Weldon | 2024-12-23 | 12 | Catch Tray - RT-7547-000-PRT | 780 | RT98-87540-PN-R001 |  |  |  | 2025-05-02
38669 | 71841 | Candu | 8 | RT-87540-0117-1-GA-2 |  | David Weldon | 2024-12-23 | 13 | Stud Removal Tool - RT-7546-000-PRT | 754 | RT98-87540-PN-R001 |  |  |  | 2025-05-02
38669 | 71842 | Candu | 6 | RT-87540-0174-1-GA-0 |  | David Weldon | 2024-12-23 | 14 | Spring Pin Removal Tool - RT-7549-000-PRT | 4828 | RT98-87540-PN-R001 |  |  |  | 2025-05-02
38669 | 71843 | Candu | 8 | RT-87540-0101-01-GA-2 |  | David Weldon | 2024-12-23 | 15 | Yoke Ret. Clamp - RT-7541-000-PRT | 665 | RT98-87540-PN-R001 |  |  |  | 2025-05-02
38669 | 71844 | Candu | 8 | RT-87540-0178-01-GA-2 |  | David Weldon | 2024-12-23 | 16 | Spacer Clip Rem. Tool - RT-7541-000-PRT | 639 | RT98-87540-PN-R001 |  |  |  | 2025-05-02
38670 | 71845 | Candu | 3 | RT-88000-70085-000-1-GA-E | 1 | David Weldon | 2024-12-30 | 1 | PT Straightening Tool | 6125 | RT98-88040-PN-R002 |  |  |  | 2025-07-08
38670 | 71846 | Candu | 3 | RT-88000-70086-000-1-GA-E | B | David Weldon | 2024-12-30 | 2 | Actuator Tool | 5097 | RT98-88040-PN-R002 |  |  |  | 2025-04-04
38670 | 71847 | Candu | 3 | RT-88000-70118-000-1-GA-E | 2 | David Weldon | 2024-12-30 | 3 | EF/PT Guide Tool ( New) | 20139 | RT98-88040-PN-R002 |  |  |  | 2025-04-04
38670 | 71848 | Candu | 4 | RT-88030-0080-01-GA-C | 0 | David Weldon | 2024-12-30 | 5 | SSDO Saddle | 7704 | RT98-88040-PN-R002 |  |  |  | 2025-04-04
38670 | 71849 | Candu | 3 | RT-88000-70103-016-1-GA-D | 0 | David Weldon | 2024-12-30 | 6 | Removal Tool Trough | 5546 | RT98-88040-PN-R002 |  |  |  | 2025-04-04
38671 | 71850 | Candu | 10 | RT-87713-0001-1-GA-D | 2 | Sanchia Bartley-Ndiaye | 2024-12-30 | 1 | End Shield Measurement Tool Sys | 3319 +778 | RT79-87710-PN-R004 |  |  |  | Aug-1-25
38672 | 71851 | Candu | 2 | RT-87550-0100-01-GA-E | 0 | Brandon Kwakye-Longdon | 2024-12-30 | 1 | Bellows Cutting Tool (SFCR) | 141549.74 | RT79-87550-PN-R001 |  |  |  | 2025-07-04
38672 | 71873 | Candu | Lot | Spare parts |  | Brandon Kwakye | 0109/25 | 2 | To Capture cost for Spare parts | Included | RT79-87550-PN-R001 |  |  |  | 2025-07-04
38672 | 72330 | Candu | 1 + 1 | RT-87550-0145-01-GA-E |  | Brandon Kwakye | 2025-04-24 | 5 | Shell Installation Tool Assy | 1950 | RT79-87550-PN-R001-R.1 |  |  |  | 2025-07-21
38673 | 71852 | Candu | 3 | RT-87900-0400-1-GA-E |  | Barbara Vaz | 2024-12-30 | 1 | C6- Bore Gauge | 26451 | RT79-87900-PN-R003 |  |  |  | 2025-07-31
38673 | 71853 | Candu | 2 | RT-87900-0500-01-GA-E |  | Barbara Vaz | 2024-12-30 | 2 | C6 Bore Gauge- Narrow Landing | 26795 | RT79-87900-PN-R003 |  |  |  | 2025-07-31
38678 | 71859 | Candu | 3 | RT-87920-74282-000-1-GA-E | 3 | Angelica de La Barrera | 2025-01-03 | 1 | CTI Delivery Tool | 23520 | RT98-87920-PN-R007-R.1 |  |  |  | 2025-03-17
38679 | 71860 | Candu | 3 | RT-87540-0169-1-DD-2 |  | Ashna-Irani-Kavasji | 2025-01-07 | 1 | Positioning Stud Rotation tool | 794 | RT98-87540-PN-R002 |  |  |  | 2025-03-31
38679 | 71861 | Candu | 3 | RT-87540-0123-1-GA-1 |  | Ashna-Irani-Kavasji | 2025-01-07 | 2 | Spacer Clip Installation Tool | 1241 | RT98-87540-PN-R002 |  |  |  | 2025-03-31
38679 | 71862 | Candu | 3 | RT-87540-0120-1-GA-2 |  | Ashna-Irani-Kavasji | 2025-01-07 | 3 | Temporary Yoke Pin | 825 | RT98-87540-PN-R002 |  |  |  | 2025-03-31
38679 | 71863 | Candu | 3 | RT-87540-0205-1-DD-2 |  | Ashna-Irani-Kavasji | 2025-01-07 | 4 | Spring Pin Installation Spacer | 520 | RT98-87540-PN-R002 |  |  |  | 2025-03-31
38679 | 71864 | Candu | 7 | RT-87540-0144-1-GA-2 |  | Ashna-Irani-Kavasji | 2025-01-07 | 5 | Threaded Hole Insp. Tool ( Short) | 2017 | RT98-87540-PN-R002 |  |  |  | 2025-03-31
38679 | 71865 | Candu | 7 | RT-87540-0186-1-GA-2 |  | Ashna-Irani-Kavasji | 2025-01-07 | 6 | Threaded Hole Repairing tool ( Short) | 1350 | RT98-87540-PN-R002 |  |  |  | 2025-03-31
38679 | 71866 | Candu | 7 | RT-87540-0137-1-GA-2 |  | Ashna-Irani-Kavasji | 2025-01-07 | 7 | Spring Pin Insetion Tool | 1827 | RT98-87540-PN-R002 |  |  |  | 2025-03-31
38679 | 71867 | Candu | 14 | RT-87540-0140-1-DD-2 |  | Ashna-Irani-Kavasji | 2025-01-07 | 8 | Spring Pin Holder | 174 | RT98-87540-PN-R002 |  |  |  | 2025-03-31
38679 | 71868 | Candu | 14 | RT-87540-0125-1-DD-2 |  | Ashna-Irani-Kavasji | 2025-01-07 | 9 | PA Spacer Clip Inst. Tool- Detent Pin Mod | 138 | RT98-87540-PN-R002 |  |  |  | 2025-03-31
38679 | 71869 | Candu | 1 | RT-87600-0250-1-GA-E |  | Ashna-Irani-Kavasji | 2025-01-07 | 10 | Lattice Sleeve Rem. Tool HWT Mounted | 43580 | RT98-87540-PN-R002 |  |  |  | 2025-03-31
37679 | 71870 | Candu | 4 | RT-87540-0166-01-GA-E |  | Ashna-Irani-Kavasji | clean | 11 | Yoke Pin Replacement Tool | 3642 | RT98-87540-PN-R002 |  |  |  | 2025-03-31
38687 | 71879 | Candu | 1 | RT-88000-70066-000-1-GA-D | 0 | Ashna Irani-Kavsji | 2025-01-13 | 1 | Helium Leak Test Tool | 12681 | RT98-88010-PN-R001 |  |  |  | 2025-03-31
38687 | 71880 | Candu | 7 | RT-88000-70146-000-1-GA-E | 3 | Ashna Irani-Kavsji | 2025-01-13 | 2 | Liner Tube Protective Sleeve | 2548 | RT98-88010-PN-R001 |  |  |  | 2025-03-31
38687 | 71881 | Candu | 2 | RT-88000-70069-000-1-GA-D | 1 | Ashna Irani-Kavsji | 2025-01-13 | 3 | Helium Spray Tool | 1477 | RT98-88010-PN-R001 |  |  |  | 2025-03-31
38687 | 71882 | Candu | 17 | RT-88000-70038-000-1-GA-D | 1 | Ashna Irani-Kavsji | 2025-01-13 | 4 | E/F Protective Sleeve | 1799 | RT98-88010-PN-R001 |  |  |  | 2025-03-31
38687 | 71883 | Candu | 4 | 80-01-00001-PRT- (Purchase) |  | Ashna Irani-Kavsji | 2025-01-13 | 5 | Spring Loaded Centre Punch | 62 | RT98-88010-PN-R001 |  |  |  | 2025-03-31
38687 | 71884 | Candu | 2 | RT-88000-70068-000-1-GA-D | 1 | Ashna Irani-Kavsji | 2025-01-13 | 6 | Vacuum Hose for Helium Leak Test | 2548 | RT98-88010-PN-R001 |  |  |  | 2025-03-31
38687 | 71885 | Candu | 5 | RT-0055-000-PRT ( Purchase) |  | Ashna Irani-Kavsji | 2025-01-13 | 7 | Air Motor Socket | 2199 | RT98-88010-PN-R001 |  |  |  | 2025-03-31
38687 | 71886 | Candu | 2 | RT-88010-0005-01-GA-E | 1 | Ashna Irani-Kavsji | 2025-01-13 | 8 | Calibrated Measuring Tape | 2998 | RT98-88010-PN-R001 |  |  |  | 2025-03-31
38687 | 71888 | Candu | 6 | RT-88000-70047-000-1-GA-D | 2 | Ashna Irani-Kavsji | 2025-01-13 | 10 | Seal Face Protective Sleeve | 1799 | RT98-88010-PN-R001 |  |  |  | 2025-03-31
38740 | 72023 | Candu | 2 | RT-87550-0100-01-GA-E | 0 | Sanchai Bartley-Ndiaye | 2025-02-11 | 1 | Bellows Cutting Tool (SFCR) | 141549.74 | RT98-87550-PN-R004-R.1 |  |  |  | 2025-09-19
38740 | 72024 | Candu | Lot | Spare parts |  | Sanchai Bartley-Ndiaye | 02/1125 | 2 | To Capture cost for Spare parts | Included | RT98-87550-PN-R004-R.1 |  |  |  | 2025-09-19
38740 | 72331 | Candu | 1 +1 | RT-87550-0145-01-GA-E |  | Brandon Kwakye | 2025-04-24 | 5 | Shell Installatin Tool Assy | 1950 | RT98-87550-PN-R004-R.1 |  |  |  | 2025-09-19
38744 | 72028 | DJ Ind. | 1 | NPN |  | Chris | 2025-02-15 | 1 | Auger to measure & Prelim Dwgs |  | NPO # |  |  |  | 2025-02-21
38752 | 72045 | Candu | 3 | RT-87920-0353-01-GA-C |  | Sanchia Bartley-Ndiaye | 2025-02-20 | 1 | Leak Test Vacuum Grease Clean'g tool | 6273 | RT98-87920-PN-R011 |  |  |  | 2025-06-27
38752 | 72046 | Candu | 4 | RT-87920-0357-01-GA-C |  | Sanchia Bartley-Ndiaye | 2025-02-20 | 2 | CTI Cleaning Tool | 4910 | RT98-87920-PN-R011 |  |  |  | 2025-06-27
38752 | 72047 | Candu | 8 | RT38-16300-024-000-0000-000-01-GA-C |  | Sanchia Bartley-Ndiaye | 2025-02-20 | 3 | CTI Cleaning Tool - Head | 2317 | RT98-87920-PN-R011 |  |  |  | 2025-06-27
38752 | 72048 | Candu | 4 | RT-87920-0355-01-GA-C |  | Sanchia Bartley-Ndiaye | 2025-02-20 | 4 | Vacuum Grease Cleaning Tool | 3497 | RT98-87920-PN-R011 |  |  |  | 2025-06-27
38754 | 72057 | ATS-Corp | 1 | MCR-15300-001-161000-01-GA-D | 6 | Scott Wilson | 2025-02-20 | 8~10 | CTSB Central Shaft stationary | 9125 | 87982- Rev.4 |  |  |  | 2025-04-25
38755 | 72061 | Kinectrics | 1 | NPD0059-DET-5407 |  | Jatin Munjal | 2025-02-21 | 30 | Sliding Bar 02 | 735 | 280099239 |  |  |  | 2025-04-04
38755 | 72066 | Kinectrics | 1 | NPD0059-WLD-6309-A,B,C,D | 1 | Jatin Munjal | 2025-02-21 | 80 | Parts for Bellows Weldment | 10881 | 280099239 |  |  |  | 2025-04-04
38756 | 72073 | Kinectrics | 2 | NPD0059-DET-6304 | 1 | Jatin Munjal | 2025-02-21 | 150 | H-Beam ( X Cost) | 4400 | 280099239 |  |  |  | 2025-04-04
38758 | 72083 | Candu | 3 | RT-88030-0300-01-GA-0 | 2 | Angelica de la Barrera | 2025-02-21 | 1 | Garter Spring Detection Tool | 52899.78 | RT79-88030-PN-R001-R.1 |  |  |  | 2025-07-21
38758 | 72084 | Candu | 4 | RT-88030-0063-01-GA-E | 1 | Angelica de la Barrera | 2025-02-21 | 2 | Single Spacer Drop off Tool | 23133.58 | RT79-88030-PN-R001-R.1 |  |  |  | 2025-07-21
38758 | 72278 | Candu | 2 | RT-88030-0250-1-GA-D |  | David Weldon | 2025-03-31 | 4 | Eddy Current Spacer Detection Trough | 5218 | RT79-88030-PN-R001-R.1 |  |  |  | 2025-07-21
38759 | 72085 | Candu | 3 | RT-88030-0300-01-GA-0 | 2 | Angelica de la Barrera | 2025-02-21 | 1 | Garter Spring Detection Tool | 52899.78 | RT98-88030-PN-R001- R.2 |  |  |  | 2025-07-21
38759 | 72086 | Candu | 6 | RT-88030-0063-01-GA-E | 1 | Angelica de la Barrera | 2025-02-21 | 2 | Single Spacer Drop off Tool | 23133.58 | RT98-88030-PN-R001- R.2 |  |  |  | 2025-07-21
38759 | 72279 | Candu | 2 | RT-88030-0250-1-GA-D |  | David Weldon | 2025-03-31 | 4 | Eddy Current Spacer Detection Trough | 5218 | RT98-88030-PN-R001- R.2 |  |  |  | 2025-07-21
38759 | 72459 | Candu | 2 | RT-88030-0310-1-GA-D |  | David Weldon | 2025-06-11 | 5 | Eddy Current Verification Bench | 8656 | RT98-88030-PN-R001- R.2 |  |  |  | 2025-08-27
38759 | 72460 | Candu | 2 | RT-88030-0021-01-GA-1 |  | David Weldon | 2025-06-11 | 6 | Tool Encoder Bracket Assy | 9903 | RT98-88030-PN-R001- R.2 |  |  |  | 2025-08-27
38764 | 72098 | Hybrid | 1 | NMP6-3B-Asy- R/W |  | John | 2025-02-24 | 3 | 4-Piston Inj Blk -r/w- WO#25-6945- Gateway |  | 19509 |  |  |  | 2025-03-24
C.O.D | 72113 | Metonic | 1 | Misc |  | Edwin | 2025-02-24 | 1 | Misc WJ Cutting |  | NPO |  |  |  | 2025-02-25
C.O.D | 72113 | Metonic | 1 | Misc |  | Edwin | 2025-05-02 | 2 | Front Left Upright |  | NPO |  |  |  | 2025-05-09
C.O.D | 72113 | Metonic | 1 | Misc |  | Edwin | 2025-05-03 | 3 | Front Right upright |  | NPO |  |  |  | 2025-05-09
C.O.D | 72113 | Metonic | 1 | Misc |  | Edwin | 2025-05-04 | 4 | Rear Left Upright |  | NPO |  |  |  | 2025-05-09
C.O.D | 72113 | Metonic | 1 | Misc |  | Edwin | 2025-05-05 | 5 | Rear Right Upright |  | NPO |  |  |  | 2025-05-09
C.O.D | 72113 | Metonic | 1 | EN-00403 |  | Edwin | 2025-05-06 | 6 | Motor Mount Sprocket |  | NPO |  |  |  | 2025-05-09
38776 | 72129 | Woodbridge | 3+3 | MZ2X2-D-N-S7N |  | James Kearns | 2025-02-28 | 1 | MZ2x2-D Inj- S7 Nozzles Tested | 590 | PD-20694 |  |  |  | 2025-03-14
38785 | 72139 | Candu | 1 | RT-88230-0245-01-GA-E |  | Angelica de la Barrera | 2025-03-04 | 1 | Large Template , MK TP-1A | 39444.42 | RT79-88230-PN-R012- R.2 |  |  |  | 2025-11-24
38785 | 72140 | Candu | 1 | RT-88230-0246-01-GA-E |  | Angelica de la Barrera | 2025-03-04 | 2 | Large Template , MK TP-1C | 38305.7 | RT79-88230-PN-R012- R.2 |  |  |  | 2025-11-24
38785 | 72141 | Candu | 1 | RT-88230-0247-01-GA-E |  | Angelica de la Barrera | 2025-03-04 | 3 | Large Template , MK TP-2A | 39684.13 | RT79-88230-PN-R012- R.2 |  |  |  | 2025-11-24
38785 | 72142 | Candu | 1 | RT-88230-0248-01-GA-E |  | Angelica de la Barrera | 2025-03-04 | 4 | Large Template , MK TP-2C | 39684.13 | RT79-88230-PN-R012- R.2 |  |  |  | 2025-11-24
38785 | 72143 | Candu | 1 | RT-88230-0249-01-GA-D |  | Angelica de la Barrera | 2025-03-04 | 5 | Small Template , MK TP-3A | 16803.5 | RT79-88230-PN-R012- R.2 |  |  |  | 2025-11-24
38785 | 72144 | Candu | 1 | RT-88230-0250-01-GA-D |  | Angelica de la Barrera | 2025-03-04 | 6 | Small Template , MK TP-3C | 17217.82 | RT79-88230-PN-R012- R.2 |  |  |  | 2025-11-24
38785 | 72145 | Candu | 1 | RT-88230-0251-01-GA-D |  | Angelica de la Barrera | 2025-03-04 | 7 | Small Template , MK TP-4A | 17288.48 | RT79-88230-PN-R012- R.2 |  |  |  | 2025-11-24
38785 | 72146 | Candu | 1 | RT-88230-0252-01-GA-D |  | Angelica de la Barrera | 2025-03-04 | 8 | Small Template , MK TP-4C | 15059.18 | RT79-88230-PN-R012- R.2 |  |  |  | 2025-11-24
38785 | 72147 | Candu | 2 | RT-88230-0200-01-GA-E |  | Angelica de la Barrera | 2025-03-04 | 9 | Upper Feeder Template Assy | 84206.32 | RT79-88230-PN-R012- R.2 |  |  |  | 2025-11-24
38790 | 72180 | Kinectrics | 4 | NPD0059-DET-6306 | 1 | Nitin Balyan | 2025-03-06 | 320 | Fastener Plate | 361 | 280099616 |  |  |  | 2025-05-29
38790 | 72181 | Kinectrics | 2 | NPD0059-DET-6307 |  | Nitin Balyan | 2025-03-06 | 330 | Mast Flange | 695 | 280099616 |  |  |  | 2025-05-29
38790 | 72183 | Kinectrics | 1 | NPD0059-DET-6313 |  | Nitin Balyan | 2025-03-06 | 350 | Flange Connector | 2172.18 | 280099616 |  |  |  | 2025-05-29
38790 | 72190 | Kinectrics | 3 | NPD0059-DET-6328 |  | Nitin Balyan | 2025-03-06 | 420 | Floating Thermocouple Mount Collet | 353 | 280099616 |  |  |  | 2025-05-29
38790 | 72200 | Kinectrics | 2 | NPD0059-DET-8017 |  | Nitin Balyan | 2025-03-06 | 520 | Plate 1-Lower Ins.ulator Plate- Fixed | 1150 | 280099616 |  |  |  | 2025-05-29
38790 | 72203 | Kinectrics | 2 | NPD0059-DET-8019 |  | Nitin Balyan | 2025-03-06 | 550 | Plate 1- Upper Insulator Plate- Floating | 1075 | 280099616 |  |  |  | 2025-05-29
38790 | 72205 | Kinectrics | 2 | NPD0059-DET-8022 |  | Nitin Balyan | 2025-03-06 | 570 | Plate 1- Lower Insulator Plate- Floating | 1150 | 280099616 |  |  |  | 2025-05-29
38790 | 72207 | Kinectrics | 2 | NPD0059-DET-8013 |  | Nitin Balyan | 2025-03-06 | 590 | Plate 1- Upper Insulator Plate- Fixed | 1150 | 280099616 |  |  |  | 2025-05-29
38799 | 72226 | Westinghouse | 2 | NTR-MU01-T3-164 | 0 | Naga Shanmugam | 2025-03-14 | 1 | Lead Screw | 4735 | 4500933778 |  |  |  | 2025-06-24
38804 | 72234 | Candu | 1 | RT-88230-0245-01-GA-E |  | Angelica de la Barrera | 2025-03-20 | 1 | Large Template , MK TP-1A | 39444.42 | RT98-88230-PN-R010 |  |  |  | 2025-11-24
38804 | 72235 | Candu | 1 | RT-88230-0246-01-GA-E |  | Angelica de la Barrera | 2025-03-20 | 2 | Large Template , MK TP-1C | 38305.7 | RT98-88230-PN-R010 |  |  |  | 2025-11-24
38804 | 72236 | Candu | 1 | RT-88230-0247-01-GA-E |  | Angelica de la Barrera | 2025-03-20 | 3 | Large Template , MK TP-2A | 39684.13 | RT98-88230-PN-R010 |  |  |  | 2025-11-24
38804 | 72237 | Candu | 1 | RT-88230-0248-01-GA-E |  | Angelica de la Barrera | 2025-03-20 | 4 | Large Template , MK TP-2C | 39684.13 | RT98-88230-PN-R010 |  |  |  | 2025-11-24
38804 | 72238 | Candu | 1 | RT-88230-0249-01-GA-D |  | Angelica de la Barrera | 2025-03-20 | 5 | Small Template , MK TP-3A | 16803.5 | RT98-88230-PN-R010 |  |  |  | 2025-11-24
38804 | 72239 | Candu | 1 | RT-88230-0250-01-GA-D |  | Angelica de la Barrera | 2025-03-20 | 6 | Small Template , MK TP-3C | 17217.82 | RT98-88230-PN-R010 |  |  |  | 2025-11-24
38804 | 72240 | Candu | 1 | RT-88230-0251-01-GA-D |  | Angelica de la Barrera | 2025-03-20 | 7 | Small Template , MK TP-4A | 17288.48 | RT98-88230-PN-R010 |  |  |  | 2025-11-24
38804 | 72241 | Candu | 1 | RT-88230-0252-01-GA-D |  | Angelica de la Barrera | 2025-03-20 | 8 | Small Template , MK TP-4C | 15059.18 | RT98-88230-PN-R010 |  |  |  | 2025-11-24
38804 | 72242 | Candu | 2 | RT-88230-0200-01-GA-E |  | Angelica de la Barrera | 2025-03-20 | 9 | Upper Feeder Template Assy | 84206.32 | RT98-88230-PN-R010 |  |  |  | 2025-11-24
38816 | 72264 | Candu | 1 | RT-87876-0414-01-GA-E | 0 | Angelica de la Barrera | 2025-03-27 | 1 | Debris Transfer Frame Adapter | 6638 | RT79-87876-PN-R004 |  |  |  | 2025-07-07
38816 | 72265 | Candu | 1 | RT-87876-0400-01-GA-D | 0 | Angelica de la Barrera | 2025-03-27 | 2 | Transfer Container Flask ( Tungsten) | 49476 | RT79-87876-PN-R004 |  |  |  | 2025-07-07
38821 | 72272 | ATS-Corp | 3 | 700567102 | AB | Dave Osmond | 2025-03-28 | 2 | Tool Body | 17726 | 88308- Rev.13 |  |  |  | 2025-06-17
38824 | 72276 | Candu | 5 | RT-87530-0112-1-GA-0 | 2 | Brandon Kwakye-Longdon | 2025-03-31 | 1 | Plunger Position Gauge Assy Tool | 3358 | RT98-87530-PN-R004 |  |  |  | 2025-06-13
38824 | 72277 | Candu | 5 | RT-87530-0116-1-GA-0 | 5 | Brandon Kwakye-Longdon | 2025-03-31 | 2 | Stem Position Gauge assy Tool | 3358 | RT98-87530-PN-R004 |  |  |  | 2025-06-13
38825 | 72280 | Candu | 1 | RT-87640-70300-000-1-GA-E | 0 | Brandon Kwakye-Longdon | 2025-04-01 | 1 | Mockup LWTF Trolley | 122666 | RT98-87590-PN-R007 |  |  |  | 2025-08-15
38828 | 72284 | ATS-Corp | 1 | MCR-15300-003-107000-00-GA-E | 2 | Justin LaFrance | 2025-04-03 | 1 | Camera Holder | 5657 | 88243- Rev.14 |  |  |  | 2025-06-20
38828 | 72286 | ATS-Corp | 1 | MCR-15300-003-102000-00-GA-C | 2 | Justin LaFrance | 2025-04-03 | 3 | Middle Vacuum Tube Weldment | 2317+5465 | 88243- Rev.14 |  |  |  | 2025-06-18
38828 | 72287 | ATS-Corp | 1 | MCR-15300-003-520000-01-GA-C | 6A | Justin LaFrance | 2025-04-03 | 4 | Tube Weldment- Telescopic Vacuum | 1985 | 88243- Rev.14 | 44573 | 1 | 52837 | 2025-06-17 | 2025-07-03 | 16
38828 | 72288 | ATS-Corp | 1 | MCR-15300-003-530000-01-GA-C | 5A | Justin LaFrance | 2025-04-03 | 5 | Tube Weldment-Telesocpic Vacuum | 1560 | 88243- Rev.14 | 44573 | 1 | 52837 | 2025-06-06 | 2025-07-03 | 27
38828 | 72289 | ATS-Corp | 1 | MCR-15300-003-115000-01-GA-C | 5A | Justin LaFrance | 2025-04-03 | 6 | Vacuum Tube Weldment | 1760 | 88243- Rev.14 | 44573 | 1 | 52837 | 2025-06-06 | 2025-07-03 | 27
38828 | 72290 | ATS-Corp | 1 | MCR-15300-003-110004-01-DD-C | 6 | Justin LaFrance | 2025-04-03 | 7 | Vacuum Tube With Flange | 1846 | 88243- Rev.14 |  |  |  | 2025-06-06
38833 | 72295 | Candu | 3 | 59RF-79113-9093-1-DD-B |  | Gregory Lopez | 2025-04-07 | 1 | Beam LWTF Spreader Beam | 8651 | RT79-79113-PN-R001-R.1 |  |  |  | 2025-06-23
38835 | 72297 | Bombardier | 15 | Sketch |  | Nesha | 2025-04-08 | 1 | BA Trench Cover | [5 empty] | 2025-04-28
38842 | 72309 | ATS-Corp | 1 | NK38-DRAW-31935-10410-0001 | 1 | Dave Osmond | 2025-04-21 | 1 | Floor Plate ( 102544) | 22964 | 88454-Rev.2 | 44573 | 1 | 52838 | 2025-06-19 | 2025-07-03 | 14
38845 | 72317 | Candu | 4 | 147-31972-0153-01-DD-B | 2 | Cindy Weng- TMR | 2025-04-21 | 1 | Drive & Index Motor Housing | 8442 | 147-31972-PN-R072 |  |  |  | 2025-08-14
38845 | 72318 | Candu | 4 | 147-31972-0163-01-DD-C | 2 | Cindy Weng- TMR | 2025-04-21 | 2 | Motor Drive Couplet | 1770 | 147-31972-PN-R072 |  |  |  | 2025-08-14
38845 | 71319 | Candu | 4 | 147-31972-0181-01-DD-C | 2 | Cindy Weng- TMR | 2025-04-21 | 3 | Ball Joint Socket | 2277 | 147-31972-PN-R072 |  |  |  | 2025-08-14
38845 | 72320 | Candu | 4 | 147-31972-0182-01-DD-C | 2 | Cindy Weng- TMR | 2025-04-21 | 4 | Ball Joint Knuckle | 1596 | 147-31972-PN-R072 |  |  |  | 2025-08-14
38845 | 72321 | Candu | 4 | 147-31972-0241-01-DD-C | 3 | Cindy Weng- TMR | 2025-04-21 | 5 | Push Tube Ball Joint Knuckle | 1596 | 147-31972-PN-R072 |  |  |  | 2025-08-14
38845 | 72322 | Candu | 4 | 147-31972-0242-01-DD-C | 3 | Cindy Weng- TMR | 2025-04-21 | 6 | Ball Joint Socket | 2752 | 147-31972-PN-R072 |  |  |  | 2025-08-14
38846 | 72324 | Candu | 2 | RT-87250-0700-01-GA-E | 0 | Sanchia Bartley-Ndiaye | 2025-04-22 | 1 | Carriage Mock-up HWT | 77892 | RT79-87250-PN-R004 |  |  |  | 2025-08-29
38848 | 72326 | DJ Ind. | 1 | Sample |  | Chris Morrison | 2025-04-23 | 1 | Valve to repair Worn Areas & Chrome | [5 empty] | 2025-05-02
38848 | 72327 | DJ Ind. | 1 | Sample |  | Chris Morrison | 2025-04-23 | 2 | Plunger Valve to Repair by Sleeve | [5 empty] | 2025-05-02
38848 | 72328 | DJ Ind. | 1 | Sample |  | Chris Morrison | 2025-04-23 | 3 | Hand Pump hone after chrome | [5 empty] | 2025-05-02
38853 | 72349 | ATS-Corp | 21 | NK38-DRAW-31935-10569-0001 | 0 | Dave Osmond | 2025-04-25 | 1 | Torsion Spring | 246- USD | 88439- Rev.1 |  |  |  | 2025-07-17
38861 | 72362 | Candu | 4 | RT-87110-0174-01-DD-2 |  | Sanchia Bartley-Ndiaye | 2025-04-29 | 1 | Ring Rolled Joint Centering Ring | 748 | RT79-87110-PN-R010 |  |  |  | 2025-05-30
38863 | 72364 | Kinectrics | 1 | NPD0059-7-WLD-1407 | 0 | Jatin Munjal | 2025-05-01 | 10 | Flange F/I Fit and Weld per Dwg | 7548 | 280101251 |  |  |  | 2025-05-30
38864 | 72365 | ATS-Corp | 1 | 700589434 | AD | Justin LaFrance | 2025-05-02 | 1 | North Sole Plate | 83423 | 88502- Rev.7 |  |  |  | 2025-09-01
38864 | 72366 | ATS-Corp | 1 | 700589302 | AD | Justin LaFrance | 2025-05-02 | 2 | South Sole Plate | 89264 | 88502- Rev.7 |  |  |  | 2025-09-01
38865 | 72367 | Candu | 4 | RT-87250-74016-000-1-GA-E | 5 | Angelica DeLa Barrera | 2025-05-02 | 1 | Pitch Yaw Mounting Frame Tool | 161870 | RT98-87000-PN-R012 |  |  |  | 2026-07-29
38865 | 72368 | Candu | 4 | RT-87250-74010-000-1-GA-E | 3 | Angelica DeLa Barrera | 2025-05-02 | 2 | Pitch Yaw Mounting Table | 181755 | RT98-87000-PN-R012 |  |  |  | 2026-07-29
38867 | 72373 | Candu | 3 | RT-87590-70000-000-1-GA-E | 4 | Sanchia Bartley-Ndiaye | 2025-05-05 | 1 | EFSF Removal Tool (RT-7591-000-PRT) | 785318 | RT98-87590-PN-R006 |  |  |  | 2026-10-09
38872 | 72380 | Kinectrics | 1 | K-402310-09-WLD-5300-004 | 0 | Craig Leung | 2025-05-08 | 10 | BL Mockup Elbolet Interface Plate | 7227 | 280101422 |  |  |  | 2025-06-05
38873 | 72381 | Candu | 1 | NK30-DCN-35385-0022-001 |  | Michael Timpano | 2025-05-09 | 1 | Cyl. Mtg Plate- F/I for Zinc Plating |  | 30-35385-PN-R007 |  |  |  | 2025-05-22
38873 | 72381 | Candu | 4 | NK30-DBN-35385-0023-001 |  | Michael Timpano | 2025-05-09 | 2 | Spacer Rod - F/I for Zinc Plating |  | 30-35385-PN-R007 |  |  |  | 2025-05-22
38873 | 72381 | Candu | 1 | NK30-DBN-35385-0025-001 |  | Michael Timpano | 2025-05-09 | 3 | Solid Ring- F/I for Zinc Plating |  | 30-35385-PN-R007 |  |  |  | 2025-05-22
38873 | 72381 | Candu | 1 | NK30-DBN-35385-0027-001 |  | Michael Timpano | 2025-05-09 | 4 | Cylinder Saddle - F/I for Zinc Plating |  | 30-35385-PN-R007 |  |  |  | 2025-05-22
38873 | 72381 | Candu | 1 | NK30-DCN-35385-0028-001 |  | Michael Timpano | 2025-05-09 | 5 | Split Ring- F/I for zinc Plating | LOT-420.00 | 30-35385-PN-R007 |  |  |  | 2025-05-22
38877 | 72386 | Westinghouse | 200 | EVR-MS01-T3-152E2 |  | Naga Shanmugam | 2025-05-12 | 1 | M10-1.5mm x 25mm Screw- Alloy 625 | 43.54 | 4500938848 |  |  |  | 2025-07-17
38879 | 72388 | Buffalo | 1 | 742637 | 5 | Jasmine Bergeron Leva | 2025-05-13 | 1 | Z-Axis Carriage- F/I Casting | 6860 | 211246771 |  |  |  | 2025-06-15
38885 | 72395 | Candu | 1 | RT-87630-71254-1000-1-GA-D | 2 | Ashna Irani-Kavasji | 2025-05-20 | 1 | VRS Manual Retrieval Tool | 146936 | RT79-87630-PN-R005 |  |  |  | 2025-08-27
38886 | 72396 | ATS-Corp | 1 | NK38-DRAW-31935-10445-0001 | 1 | Dave Osmond | 2025-05-20 | 1 | Anchor Plate | 79775 | 88485- Rev.5 |  |  |  | 2025-07-25
38886 | 72397 | ATS-Corp | 1 | NK38-DRAW-31935-10465-0001 | 0 | Dave Osmond | 2025-05-20 | 2 | Measurement Station Anchor Plt | 4810 | 88485- Rev.5 |  |  |  | 2025-07-25
38886 | 72398 | ATS-Corp | 1 | NK38-DRAW-31935-10491-0001 | 0 | Dave Osmond | 2025-05-20 | 3 | Center Rod -Anchor Plate | 5810 | 88485- Rev.5 |  |  |  | 2025-07-25
38886 | 72399 | ATS-Corp | 1 | NK38-DRAW-31935-10523-0001 | 0 | Dave Osmond | 2025-05-20 | 4 | RH Guide Strip | 2140 | 88485- Rev.5 |  |  |  | 2025-07-25
38886 | 72400 | ATS-Corp | 1 | NK38-DRAW-31935-10524-0001 | 0 | Dave Osmond | 2025-05-20 | 5 | Slide Bar | 7640 | 88485- Rev.5 |  |  |  | 2025-07-25
38886 | 72401 | ATS-Corp | 1 | NK38-DRAW-31935-10552-0001 | 0 | Dave Osmond | 2025-05-20 | 6 | Guide | 7215 | 88485- Rev.5 |  |  |  | 2025-07-25
38886 | 72402 | ATS-Corp | 1 | NK38-DRAW-31935-10572-0001 | 0 | Dave Osmond | 2025-05-20 | 7 | LH Guide Strip | 2140 | 88485- Rev.5 |  |  |  | 2025-07-25
38890 | 72406 | ATS-Corp | 1 | 700628267-F/I |  | Scott Wilson | 2025-05-22 | 1 | MF Heatsing Liner-F/I to Modify | 450 | 8423365- Rev.1 |  |  |  | 2025-06-11
38891 | 72407 | Candu | 2 | XX-35217-3-1-DD-D | 1 | Michael Timpao | 2025-05-22 | 1 | Deloro 60 Ring Only | 3373.5 | 79-35217-PN-R004 |  |  |  | 2025-09-19
38898 | 72422 | Candu | 1 | RT-79112-03000-01-GA-E | 0 | Sanchia Bartley-Ndiaye | 2025-05-26 | 1 | Small Waste Transfer Flask | 272363 | RT79-79112-PN-R002 |  |  |  | 2026-01-26
38899 | 72425 | Safran (Messier) | 1 | DSK30906G01-113 |  | Pablo Garcida | 2025-05-27 | 50 | Loading Block | 345 | 4590038355 | 44570 | 1 |  | 2025-06-24
38902 | 72430 | ATS-Corp | 1 | NK38-DRAW-31935-10359-0001 |  | Dave Osmond | 2025-05-30 | 1 | Table Shielding Plate ( 103420) | 8690 | 88808- Rev.4 |  |  |  | 2025-07-30
38902 | 72431 | ATS-Corp | 1 | NK38-DRAW-31935-10536-0001 |  | Dave Osmond | 2025-05-30 | 2 | Counter Balance W/ Lead Assy (100882) | 5187 | 88808- Rev.4 |  |  |  | 2025-07-30
38902 | 72431 | ATS-Corp | 1 | NK38-DRAW-31935-10538-0001 |  | Dave Osmod | 2025-05-30 | 3 | Counter Balance Weldment ( 103414) | 4397 | 88808- Rev.4 |  |  |  | 2025-07-30
38906 | 72438 | Candu | 3 | RT-87250-040-01-GA-E |  | Sanchia Bartley-Ndiaye | 2025-06-02 | 1 | Installation Worktable | 243730 | RT98-87250-PN-R007 |  |  |  | 2026-10-16
38906 | 72439 | Candu | 3 | RT-87250-70000-5000-1-GA-B |  | Sanchia Bartley-Ndiaye | 2025-06-02 | 2 | Inst. Worktable Support Frame | 62656 | RT98-87250-PN-R007 |  |  |  | 2026-10-16
38906 | 72440 | Candu | 4 | RT-87920-0303-01-GA-D |  | Sanchia Bartley-Ndiaye | 2025-06-02 | 3 | CT Shield Sleeve- Short | 31479 | RT98-87250-PN-R007 |  |  |  | 2026-10-16
38906 | 72441 | Candu | 6 | RT-87920-0051-01-DD-C |  | Sanchia Bartley-Ndiaye | 62/25 | 4 | Hook Assy For Extension Tool | 582 | RT98-87250-PN-R007 |  |  |  | 2026-10-16
38908 | 72443 | Candu | 1 | RT-87600-0403-1-DD-C | 1 | Cindy Weng- TMR | 2025-06-05 | 1 | Round Stud | 1928 | 216-02123-PN-T101 |  |  |  | 2025-07-06
38909 | 72444 | Candu | 8 | RT-87250-74017-002-1-DD-B |  | Cindy Weng- TMR | 2025-06-05 | 1 | Tooling Guide Pin | 235 | 216-02123-PN-T102 |  |  |  | 2025-07-02
38909 | 72445 | Candu | 4 | RT-87250-74017-044-1-DD-B |  | Cindy Weng- TMR | 2025-06-05 | 2 | Handle | 425 | 216-02123-PN-T102 |  |  |  | 2025-07-02
38909 | 72446 | Candu | 4 | RT-87250-74017-045-1-DD-B |  | Cindy Weng- TMR | 2025-06-05 | 3 | Pivot Block 0.50 x 1.25 x 3.0 | 297 | 216-02123-PN-T102 |  |  |  | 2025-07-02
38912 | 72451 | Candu | 1 | RT-87876-0049-01-DD-D | 1 | Cindy Weng- TMR | 2025-06-06 | 1 | Axial Vacuum Nozzle | 2330 | 216-02123-PN-T104 |  |  |  | 2025-07-04
38912 | 72452 | Candu | 2 | 21RT-87920-0453-002-DD-0 | 1 | Cindy Weng- TMR | 2025-06-06 | 2 | Sliding Pad- Item # 4 | 1942 | 216-02123-PN-T104 |  |  |  | 2025-07-04
38913 | 72453 | Safran (Messier) | 3 | DSK30901G04-101 |  | Pablo Gracida | 2025-06-06 | 10 | Striker Plate | 465 | 4590038422-Rev.1 |  |  |  | 2025-07-04
38913 | 72454 | Safran (Messier) | 1 | DSK30901G04-103 |  | Pablo Gracida | 2025-06-06 | 20 | Dome | 972+ 443.20 | 4590038422-Rev.1 |  |  |  | 2025-07-04
38914 | 72455 | ATS-Corp | 1+1 | 700540049 | AA | Scott Wilson | 2025-06-06 | 1 & 2 | Post Bearing Spacer | 5550 | 8451261- Rev.1 |  |  |  | 2025-07-25
38914 | 72456 | ATS-Corp | 2+2 | 700573391 | AA | Scott Wilson | 2025-06-06 | 3 | Coupling Housing | 7478 | 8451261- Rev.1 |  |  |  | 2025-08-06
38916 | 72458 | ATS Test | 1 | 700615075 | AA | Justin LaFrance | 2025-06-10 | 1 | Flowmeter Pipe Section | 1730 | 88028931- Rev.1 |  |  |  | 2025-07-02
38917 | 72461 | Candu | 2 | RT-88000-70164-107-1-DD-B |  | Cindy Weng- TMR | 2025-06-12 | 1 | Tag- Load Test | 87 | 216-02123-PN-T105 |  |  |  | 2025-08-26
38917 | 72462 | Candu | 1 | RT-88000-70164-038-1-GA-C |  | Cindy Weng- TMR | 2025-06-12 | 2~6 | Counterweight assy | 3739 | 216-02123-PN-T105 |  |  |  | 2025-08-26
38917 | 72463 | Candu | 1 | RT-88000-70164-030-1-GA-D |  | Cindy Weng- TMR | 2025-06-12 | 7~10 | PT Support Assy | 3421 | 216-02123-PN-T105 |  |  |  | 2025-08-26
38917 | 72464 | Candu | 2 | RT-88000-70164-106-1-DD-B |  | Cindy Weng- TMR | 2025-06-12 | 11 | Tag C of G | 87 | 216-02123-PN-T105 |  |  |  | 2025-08-26
38917 | 72465 | Candu | 2 | RT-88000-7164-105-1-DD-B |  | Cindy Weng- TMR | 2025-06-12 | 12 | Tag C of G | 87 | 216-02123-PN-T105 |  |  |  | 2025-08-26
38917 | 72466 | Candu | 2 | RT-88000-70164-104-1-DD-E |  | Cindy Weng- TMR | 2025-06-12 | 13 | Tag | 105 | 216-02123-PN-T105 |  |  |  | 2025-08-26
38917 | 72467 | Candu | 2 | RT-88000-70164-025-1-DD-D |  | Cindy Weng- TMR | 2025-06-12 | 14 | Sleeve Block | 391 | 216-02123-PN-T105 |  |  |  | 2025-08-26
38917 | 72468 | Candu | 1 | RT-88000-70164-020-1-DD-B |  | Cindy Weng- TMR | 2025-06-12 | 15 | Spacer | 103 | 216-02123-PN-T105 |  |  |  | 2025-08-26
38917 | 72469 | Candu | 1 | RT-88000-70164-018-1-DD-D |  | Cindy Weng- TMR | 2025-06-12 | 16 | Stiffener 1 | 1112 | 216-02123-PN-T105 |  |  |  | 2025-08-26
38917 | 72470 | Candu | 2 | RT-88000-70164-012-1-DD-D |  | Cindy Weng- TMR | 2025-06-12 | 17 | Block 12 | 391 | 216-02123-PN-T105 |  |  |  | 2025-08-26
38917 | 72471 | Candu | 1 | RT-88000-70164-019-1-DD-D |  | Cindy Weng- TMR | 2025-06-12 | 18 | Stiffener 2 | 762 | 216-02123-PN-T105 |  |  |  | 2025-08-26
38918 | 72472 | Buffalo | 1 | 3677249 | 2 | Jasmine Bergeron-Leva | 2025-06-12 | 1 | Motor Adapter Plate | 4435 | 211248489 |  |  |  | 2025-07-11
38919 | 72473 | Bombardier | 15 | Samples- F/I |  | Ann Nguyen/Carlton | 2025-06-16 | 1 | Small Buttons ( Busihng) For H/T |  |  | 44580 | 15 |  | 2025-06-20 | 2025-07-08 | 18
38921 | 72475 | EHV Power | 6 | 230819-EBA230-02 |  | Iilario Iacoucci | 2025-06-16 | 1 | "L" Type Angle- 102 x 76 x 6.4ft- l=908mm | 198 | 4074 |  |  |  | 2025-07-11
38921 | 72475 | EHV Power | 12 | 230819-EBA230-02 |  | Iilario Iacoucci | 2025-06-16 | 2 | "L" Type Angle- 51 x 51 6f.4 ft- l=876mm | 184 | 4074 |  |  |  | 2025-07-11
38921 | 72475 | EHV Power | 66 | 230819-EBA230-02 |  | Iilario Iacoucci | 2025-06-16 | 3 | "L" Type Angle- 102 x 76 x 6.4ft- l=102mm | 122 | 4074 |  |  |  | 2025-07-11
38921 | 72475 | EHV Power | 16 | 230819-EBA230-02 |  | Iilario Iacoucci | 2025-06-16 | 5 | "L" Type Angle- 64 x 64 x 6.4ft- l=914mm | 337 | 4074 |  |  |  | 2025-07-11
38921 | 72475 | EHV Power | 16 | 230819-EBA230-02 |  | Iilario Iacoucci | 2025-06-16 | 6 | "L" Type Angle- 64 x 64 x 6.4ft- l=800mm | 317 | 4074 |  |  |  | 2025-07-11
38921 | 72475 | EHV Power | lot | 230819-EBA230-02 |  | Iilario Iacoucci | 2025-06-16 | 7 | Hardware-HH bolts, Nuts, Washers -galv | 1579 | 4074 |  |  |  | 2025-07-11
38922 | 72477 | ABI Ltd | 1 | 4212B011 |  | Mani Muralidharan | 2025-06-17 | 10 | Drive Roller | 5144 | 4500012296-0 |  |  |  | 2025-07-07
38923 | 72478 | ATS-Corp | 1 | NK38-DRAW-31935-10461-0001 | 0 | Dave Osmond | 2025-06-17 | 1 | Probe Support Base Weldment | 1487 | 88706-Rev.7 |  |  |  | 2025-08-28
38923 | 72479 | ATS-Corp | 1 | NK38-DRAW-31935-10462-0001 |  | Dave Osmond | 2025-06-17 | 2 | Frame Weldment | 15184 | 88706-Rev.7 |  |  |  | 2025-08-28
38923 | 72480 | ATS-Corp | 1 | NK38-DRAW-31935-10464-0001 |  | Dave Osmond | 2025-06-17 | 3 | Probe Weldment | 4745 | 88706-Rev.7 |  |  |  | 2025-08-28
38923 | 72481 | ATS-Corp | 1 | NK38-DRAW-31935-10466-0001 |  | Dave Osmond | 2025-06-17 | 4 | Bundle Support Base Weldment | 2989 | 88706-Rev.7 |  |  |  | 2025-08-28
38923 | 72482 | ATS-Corp | 1 | NK38-DRAW-31935-10469-0001 |  | Dave Osmond | 2025-06-17 | 5 | Probe Guard Weldment | 4359 | 88706-Rev.7 |  |  |  | 2025-08-28
38923 | 72483 | ATS-Corp | 1 | NK38-DRAW-31935-10472-0001 |  | Dave Osmond | 2025-06-17 | 6 | Probe Holder Extension | 1789 | 88706-Rev.7 |  |  |  | 2025-08-28
38923 | 72484 | ATS-Corp | 1 | NK38-DRAW-31935-10489-0001 |  | Dave Osmond | 2025-06-17 | 7 | Upper Frame Weldment | 6307 | 88706-Rev.7 |  |  |  | 2025-08-28
38923 | 72485 | ATS-Corp | 1 | NK38-DRAW-31935-10490-0001 |  | Dave Osmond | 2025-06-17 | 8 | Bottom Frame Weldment | 13575 | 88706-Rev.7 |  |  |  | 2025-08-28
38925 | 72487 | Kinectrics | 1 | F/I Aliminum |  | Dean Moore | 2025-06-20 | 1 | Sheave Wheel- 2.45in, 860 c/w Brg | 2808.5 | 280102956 | 44556 | 1 | 52840 | 2025-06-23 | 2025-07-04 | 11
38926 | 72488 | ATS-Corp | 1 | 700460807 | AA | Scott Wilson | 2025-06-23 | 1 | Cable Reel Bracket Weldment | 1925 | 89053- Rev.1 |  |  |  | 2025-07-22
38926 | 72489 | ATS-Corp | 1 | 700465242 | AA | Scott Wilson | 2025-06-23 | 2 | Drive Weldment | 5970 | 89053- Rev.1 |  |  |  | 2025-07-25
38927 | 72490 | BWXT(GE) | 300 @ | X80-5212 |  | William Won | 2025-06-23 | 1~3 | Pinion G.01/ G.02 / G.03 | 3.76/2.97/2.86 | 721700 |  |  |  | 2025-08-29
38927 | 72490 | BWXT(GE) | 300 @ | X80-5212 |  | William Won | 2025-06-23 | 4~6 | Bearing G.01/ G.02/ G.03 | 3.91/3.23/2.97 | 721700 |  |  |  | 2025-08-29
38927 | 72490 | BWXT(GE) | 300@ | X80-5212 |  | William Won | 2025-06-23 | 7~10 | Brush- G.01 / G.02/ G.03 | 3.74/2.99/2.86 | 721700 |  |  |  | 2025-08-29
38928 | 72491 | BWXT Med | 1 | K129412-210- Option #2 |  | Melissa Garneau | 2025-06-24 | 1 | GR2 Titanium Heating Block | 2307 | 1114013 | 44579 | 1 | 52843 | 2025-08-15 | 2025-07-08 | -38
38929 | 72492 | ATS-Corp | 4 | 700614242 | AA | Justin LaFrance | 2025-06-24 | 1 | Piston Clamp Plate | 1940 | 83139- Rev.1 |  |  |  | 2025-07-21
38929 | 72493 | ATS-Corp | 2 | 700470628 | AA | Justin LaFrance | 2025-06-24 | 2 | Trough Section | 2118 | 83139- Rev.1 |  |  |  | 2025-07-21
38930 | 72495 | ATS-Corp | 1 | 700657767 | AA | Scott Wilson | 2025-06-26 | 1 | Box Slide | 9618 | 8451433- Rev.2 |  |  |  | 2025-08-06
38931 | 72496 | DJ Ind. | 2 | 66812-MD |  | Steve Davey | 2025-06-26 | 1 | Malomar Depositor Slide (Ertalyte) | 855 | 3739266 | 44572 | 2 | 52836 | 2025-07-17 | 2025-07-03 | -14
38932 | 72497 | BWXT(GE) | 170 | 208370-1 |  | William Won | 2025-06-26 | 1 | Housing | 26.31 | 721701 |  |  |  | 2025-10-21
38932 | 72498 | BWXT(GE) | 170 | 208380-1 |  | William Won | 2025-06-26 | 2 | Front Plate | 29.49 | 721701 |  |  |  | 2025-10-21
38932 | 72499 | BWXT(GE) | 350 | 208381-1 |  | William Won | 2025-06-26 | 3 | Rear Plate | 28.04 | 721701 |  |  |  | 2025-10-21
38932 | 72500 | BWXT(GE) | 170 | 208382-1 |  | William Won | 2025-06-26 | 4 | Middle Plate | 28.47 | 721701 |  |  |  | 2025-10-21
38932 | 72501 | BWXT(GE) | 350 | 460072-1 |  | William Won | 2025-06-26 | 5 | Retaining Ring | 1.88 | 721701 |  |  |  | 2025-10-21
38932 | 72502 | BWXT(GE) | 180 | 213025-1 |  | William Won | 2025-06-26 | 6 | Front Plate | 46.1 | 721701 |  |  |  | 2025-10-21
38932 | 72503 | BWXT(GE) | 180 | 213026-1 |  | William Won | 2025-06-26 | 7 | Housing | 64.59 | 721701 |  |  |  | 2025-10-21
38933 | 72504 | BWXT(GE) | 350 | 203346-1 |  | William Won | 2025-06-26 | 1 | Hub | 7.77 | 721704 |  |  |  | 2025-10-21
38933 | 72505 | BWXT(GE) | 670+710 | 205626-12 & 15 |  | William Won | 2025-06-26 | 2 & 9 | Mounting Plate | 7.65/ 8.30 | 721704 |  |  |  | 2025-10-21
38933 | 72506 | BWXT(GE) | 170 | 28369-1 |  | William Won | 2025-06-26 | 4 | End Cap | 22.85 | 721704 |  |  |  | 2025-10-21
38933 | 72507 | BWXT(GE) | 170 | 208374-1 |  | William Won | 2025-06-26 | 5 | Housing | 29.22 | 721704 |  |  |  | 2025-10-21
38933 | 72508 | BWXT(GE) | 340 | 208373-1 |  | William Won | 2025-06-26 | 6 | Standoff Post | 8.57 | 721704 |  |  |  | 2025-10-21
38933 | 72509 | BWXT(GE) | 690 | 208376-1 |  | William Won | 2025-06-26 | 7 | Brush Block Shaft | 6.65 | 721704 |  |  |  | 2025-10-21
38933 | 72510 | BWXT(GE) | 350 | 208377-1 |  | William Won | 2025-06-26 | 8 | Brush Block Shaft | 8.37 | 721704 |  |  |  | 2025-10-21
38933 | 72511 | BWXT(GE) | 1380+1380 | 205624-13 & 14 |  | William Won | 2025-06-26 | 10 & 12 | Spacer Round & Mounting Standoff Round | 4.80 /5.28 | 721704 |  |  |  | 2025-10-21
38933 | 72512 | BWXT(GE) | 1380 | 205065-1 |  | William Won | 2025-06-26 | 11 | Post | 4.56 | 721704 |  |  |  | 2025-10-21
38933 | 72513 | BWXT(GE) | 350 | 208371-1 |  | William Won | 2025-06-26 | 13 | Gearshaft | 15.9 | 721704 |  |  |  | 2025-10-21
38934 | 72514 | BWXT(GE) | 350 | 208375-1 |  | William Won | 2025-06-26 | 1 | Shaft | 38.93 | 721733 |  |  |  | 2025-10-21
38934 | 72515 | BWXT(GE) | 170 | 208372-1 |  | William Won | 2025-06-26 | 2 | Input Shaft | 66.05 | 721733 |  |  |  | 2025-10-21
38934 | 72516 | BWXT(GE) | 180 | 213747-1 |  | William Won | 2025-06-26 | 3 | Input Shaft | 72.33 | 721733 |  |  |  | 2025-10-21
38935 | 72517 | Candu | 3 | RT-87840-70000-1000-1-GA-B |  | Sanchia Bartley-Ndiaye | 2025-06-27 | 1 | CV FME Inspection Tool | 253143 | RT79-87840-PN-R002 |  |  |  | 2025-11-17
38936 | 72518 | Kinectrics KPN | 1 | NPD0059-7-WLD-2418 |  | LJUBO | 2025-07-02 | 10 | Spool 736 mm F/I mat'l for R/W | 3750 | 280102996 | 44575 | 1 | 52842 | 2025-06-30 | 2025-07-04 | 4
38936 | 72519 | Kinectrics KPN | 1 | NPD0059-7-WLD-2418 |  | LJUBO | 2025-07-02 | 20 | Spool 50mm F/I Mat'l for R/W | 3950 | 280102996 | 44575 | 1 | 52842 | 2025-06-30 | 2025-07-04 | 4
38937 | 72520 | Hunstville | 3 | MZ2x2-D-AI- R/W |  | Daryl Lockwood | 2025-07-03 | 1 | MZ2x2 Adjustable Injector F/I to Refurbish | [5 empty] | 2025-07-18
38937 | 72521 | Hunstville | 2 | MZ2x2-D-BV- R/W |  | Daryl Lockwood | 2025-07-03 | 2 | MZ2x2-D- Bypass Valve F/I to refurbish | [5 empty] | 2025-07-18
38937 | 72522 | Hunstville | 2 | MZ2x2-D- R/W |  | Daryl Lockwood | 2025-07-03 | 3 | MZ2x2-D- Injector - F/I to Refurbish | [5 empty] | 2025-07-18
38938 | 72523 | ATS-Corp | 4 | 700673679 | AA | Scott Wilson | 2025-07-03 | 1 | Handle Extension | 890 | 89130- Rev.2 |  |  |  | 2025-07-24
38938 | 72524 | ATS-Corp | 1 | 700543934- F/I |  | Scott Wilson | 2025-07-03 | 2 | T-Handle Wrench- Handle | 2450 | 89130- Rev.2 |  |  |  | 2025-07-25
38939 | 72525 | Kinectrics | 1 | NPD0059-4920-MCC |  | Paul Driedger | 2025-07-03 | 10 | Enclosure Cutouts- Sht # 1- F/I Mat'l | 950 | 280102819 |  |  |  | 2025-07-17
38939 | 72526 | Kinectrics | 1 | NPD0059-4920-MCC |  | Paul Driedger | 2025-07-03 | 20 | PSU Enclosure Cutouts Sht# 8- F/I Mat'l | 850 | 280102819 |  |  |  | 2025-07-17
38939 | 72527 | Kinectrics | 1 | NPD0059-4921-RIO |  | Paul Driedger | 2025-07-03 | 30 | Enclosure Back Plate- Sht # 1 F/I Mat'l | 975 | 280102819 |  |  |  | 2025-07-17
38939 | 72528 | Kinectrics | 1 | NPD0059-4921-RIO |  | Paul Driedger | 2025-07-03 | 40 | Enclosure Back Plate- Sht # 2 F/I Mat'l | 200 | 280102819 |  |  |  | 2025-07-17
38939 | 72529 | Kinectrics | 1 | NPD0059-DET-2114 |  | Paul Driedger | 2025-07-03 | 50 | Add cut-outs per R01 Dwg F/I Mat'l | 175 | 280102819 |  |  |  | 2025-07-17
38939 | 72530 | Kinectrics | 4 | NPD0059-GA-4920 |  | Paul Driedger | 2025-07-03 | 60 | Heater PSU Mtg Plate ( new) | 455 | 280102819 |  |  |  | 2025-07-17
38940 | 72531 | ComEnCo | 2 | 91592C03 |  | Keith Hou | 2025-07-03 | 1 | Burner End Plates R/w | 175 | 91614-004 | 44578 | 2 | 52839 | 2025-07-08 | 2025-07-08 | 0
38941 | 72532 | Bombardier | 3+2 | NPN |  | Tony Mazza | 2025-07-03 | 1 | Slotted & Drill Bushing |  |  | 44576 | 5 |  | 2025-07-07 | 2025-07-07 | 0
38942 | 72533 | Husky | 2 | 2604680 | 0 | Jasmine Bergeron-Leva | 2025-07-04 | 1 | Leveling Bar | 3890 | 211249978 |  |  |  | 2025-08-12
38943 | 72534 | Candu | 1 | RT-87920-74245-034-1-DD-B | 0 | Cindy Weng- TMR | 2025-07-04 | 1 | Front Tube Support Retainer | 105 | 216-02123-PN-T110 |  |  |  | 2025-08-15
38943 | 72535 | Candu | 1 | RT-87920-74245-032-1-DD-B | 0 | Cindy Weng- TMR | 2025-07-04 | 2 | Front Tube Support | 450 | 216-02123-PN-T110 |  |  |  | 2025-08-15
38943 | 72536 | Candu | 1 | RT-87920-74245-033-1-DD-B | 0 | Cindy Weng- TMR | 2025-07-04 | 3 | Front Support Screw Retainer | 105 | 216-02123-PN-T110 |  |  |  | 2025-08-15
38943 | 72537 | Candu | 2 | RT-87920-74245-030-1-DD-B | 1 | Cindy Weng- TMR | 2025-07-04 | 4 | Front Support Pivot Base | 494 | 216-02123-PN-T110 |  |  |  | 2025-08-15
38943 | 72538 | Candu | 1 | RT-87920-74245-029-1-DD-B | 0 | Cindy Weng- TMR | 2025-07-04 | 5 | Front Support Spacer | 187 | 216-02123-PN-T110 |  |  |  | 2025-08-15
38943 | 72539 | Candu | 1 | RT-87920-74245-028-1-DD-B | 0 | Cindy Weng- TMR | 2025-07-04 | 6 | Base Plate | 277 | 216-02123-PN-T110 |  |  |  | 2025-08-15
38943 | 72540 | Candu | 1 | RT-87920-74245-031-1-DD-B | 1 | Cindy Weng- TMR | 2025-07-04 | 7 | Screw Pivot | 704 | 216-02123-PN-T110 |  |  |  | 2025-08-15
38943 | 72541 | Candu | 1 | RT-87920-74245-048-1-DD-B | 0 | Cindy Weng- TMR | 2025-07-04 | 8 | Coupling | 3149 | 216-02123-PN-T110 |  |  |  | 2025-08-15
38943 | 72542 | Candu | 1 | RT-87920-74245-047-1-DD-B | 0 | Cindy Weng- TMR | 2025-07-04 | 9 | Front Support Spacer | 277 | 216-02123-PN-T110 |  |  |  | 2025-08-15
38943 | 72543 | Candu | 1 | RT-87920-74245-024-1-DD-B | 2 | Cindy Weng- TMR | 2025-07-04 | 10 | Split Collar | 975 | 216-02123-PN-T110 |  |  |  | 2025-08-15
38944 | 72544 | Kinectrics | 1 | K-940121-DET-6001 | 1 | Ljubo Djordjic | 2025-07-04 | 10 | Enclosure F/I to Modify | 450 | 280102919 | 44581 | 1 | 52841 | 2025-07-08 | 2025-07-08 | 0
38945 | 72545 | Bombardier | 1 | Sketch |  | Tony Mazza | 2025-07-04 | 1 | Titanium Test Piece |  |  | 44577 | 1 |  | 2025-07-07 | 2025-07-07 | 0
38946 | 72546 | Safran (Messier) | 1 | CAT5880-2 |  | Pablo Gracida | 2025-07-07 | 10 | LG Handling Dolly | 42460 | 7000543134- Rev.1 |  |  |  | 2025-09-23
38947 | 72547 | Hybrid | 1 | NMP6-3B-Asy-R/W |  | John | 2025-07-11 | 1 | 4-Pis. Inj.Blk-R/W- WO#25-7006- Kyushu |  | 19603 |  |  |  | 2025-07-30
38947 | 72548 | Hybrid | 1 | ALTRIM-HFH R/W |  | John | 2025-07-11 | 2 | Atrim HFH-R/W- WO#25-7020- Blenheim - 1.25mm |  | 19603 |  |  |  | 2025-07-30
38947 | 72549 | Hybrid | 1 | ALTRIM-HFH- R/W |  | John | 2025-07-11 | 3 | Altrim HFH-R/W- WO#25-7075- Fremont - 1.25mm |  | 19603 |  |  |  | 2025-07-30
38948 | 72550 | Hybrid | 1 | NMP6-3B-Asy-R/W |  | John | 2025-07-11 | 1 | 4-Pis. Inj.Blk-R/W- WO#25-7090- Fremont |  | 19603 |  |  |  | 2025-07-30
38948 | 72551 | Hybrid | 1 | ALTRIM-HFH R/W |  | John | 2025-07-11 | 2 | Atrim HFH-R/W- WO#25-7091- Fremont - 1.25mm |  | 19603 |  |  |  | 2025-07-30
38948 | 72552 | Hybrid | 1 | ALTRIM-HFH R/W |  | John | 2025-07-11 | 3 | Atrim HFH-R/W- WO#25-7108- Guangzhou- 1.25mm |  | 19603 |  |  |  | 2025-07-30
38949 | 72553 | Hybrid | 1 | ALTRIM-HFH R/W |  | John | 2025-07-11 | 1 | Atrim HFH-R/W- WO#25-7109- Guangzhou - 1.25mm |  | 19603 |  |  |  | 2025-07-30
38949 | 72554 | Hybrid | 1 | NMP6-3B-Asy-R/W |  | John | 2025-07-11 | 2 | 4-Pis. Inj.Blk-R/W-WO#25-7110-Guangzhou |  | 19603 |  |  |  | 2025-07-30
38949 | 72555 | Hybrid | 1 | ALTRIM-HFH R/W |  | John | 2025-07-11 | 3 | Atrim HFH-R/W- WO#25-7111- Anjo- 0.85mm |  | 19603 |  |  |  | 2025-07-30
38950 | 72556 | M.D.A | 1 | 4038371 |  | Madhu Ragavan Mani | 2025-07-11 | 1 | Frame Assembly | 4475 | PO1020373 |  |  |  | 2025-08-26
Link To Parts Shipped1
Print Stamps
New MP On 11"x17"
Highlight P# to Start
Create A New JOB
New MP On 8.5"x11"
Highlight P# to Start
Check Existing MP with
Part Number
Add Comments
in Active Cell
MHI
BUSHINGS
Past DUE
Print Labels
Kinectrics
Order Entry Export
Fix Listed Problems
Remove Shipped Parts
Note on B3: MP:
Note on L7: Problems with material used- When BWXT inspected parts cacked. Olivier need to find out next steps. Order on HOLD
Note on E14: Lester reached out to Bobby about getting updated drawing since Nov-21-23. we keep reminding Bobby , but we have not seen any new Drawing. Bobby keeps stating he's working on it.
Note on E16: SNC- provided the Toggle Clamp but did not fit on the existing Block RTD made. June-5-2024 Lester sent in a DDR requesting to open slot on block to accommodate the Toggle Clamp provided. Still Waiting for Approval
Note on L18: This order will be tracked -thru new Process Job Doc's Feb-8-2024 In May- Lester revised welding procedure an MITP Still waitng for approveal. Lester reached out on June-7-2024
Note on E20: F/I material received June-12-25
Note on L29: Feb-13-2025- Lester Submitted Procedures
Note on L35: Romania
Note on L36: Romania
Note on B37: assseml
Note on L37: Romania
Note on L38: Romania
Note on L39: Romania
Note on L40: Romania
Note on L41: Romania
Note on L42: Romania
Note on L43: Romania
Note on L45: Romania
Note on L46: Romania
Note on L47: Romania
Note on L48: Romania
Note on L49: Romania
Note on L50: Romania
Note on L51: Romania
Note on L52: Romania
Note on L53: Romania
Note on L54: Romania
Note on L55: Romania
Note on L56: Romania
Note on L57: Romania
Note on L58: Romania
Note on L59: Romania
Note on L60: Romania
Note on L62: Romania
Note on P64: Jan-23-25 ; Original Delv Date was Feb-28-25- Inspection Probe expected back from Eddyfi on -March-7/25- Gus said we need a couple of days for assy- Hence New Delivery date of March-14-2025- Emailed to Laila Jan-23-25. MARCH-6-25- New Updated delivery from Eddifi from March-7 to March-14-2025 hence pushing the delivery out by another week. March-13-25- Jude received e-mail from Eddyfi stating 1 piece is ready, but the second piece will be delayed by 8-9 Weeks as they waiting for parts to complete the assembly
Note on L66: Romania New Rev.1 Added to capture BOM It.9 & 15 RT-88000-78530-000-1-GA-E-Shaft Asy RT-88000-78510-000-1-ga-D- PT Straigt Tool
Note on L67: Romania
Note on L68: Romania
Note on L69: Romania
Note on L70: Romania
Note on D72: was previously 168000 changed Dec-12-20241-120,000pc mar-17-25- 4500 pcs Mar-20-25- 4500 pcs April-14-25- 9,000 pcs may-6-25- 12,000 pcs May-20-25 12,000 pcs June-1-25 6,000 pcs
Note on M72: MP: PS# 44245 7500 pcs PS# 44285 4500 pcs PS# 44310 4500 pcs PS# 44334 4500 pvd PS# 44386 9000 pcs PS# 44449 12000 pcs PS# 44481 12000 pcs PS# 44530 6000 pcs
Note on N72: MP: 7500 pcs 4500 pcs 4500 pcs 4500 pcs 12000 pcs 12000 pcs 6000 pcs
Note on O72: MP: Inv 52535 7,500 pcs 02/19/25 Inv 52579 4,500 pcs 03/06/25 Inv 52600 4,500 pcs 03/17/25 Inv 52621 4,500 pcs 03/20/25 Inv 52669 9,000 pcs 04/14/25 Inv 52731 12,000 pcs 05/06/25 Inv 52744 12,000 pcs 05/20/25 Inv 52800 6,000 psc 06/11/25
Note on Q72: 7500 pcs shipd 02/19/25 4500 pcs shipd 03/07/25 4500 pcs shipd 03/17/25 4500 pcs shipd 03/20/25 12000 pcs shipd 05/06/25 12000 pcs shipd 05/20/25 6000-pcs shipd 6/11/25
Note on D73: was previousl 32,000 changed to 81000 dec-12-2024 3000- pcs Shipped-2/18/24 6000-pcs Shipd- Jan-8-25 6000- pcs Shipd- Feb-4-2025 4500-pcs Shipd- Feb-25-25 3000- pcs shipd may-6-25 3000-pcs shipd May-20-25
Note on M73: PS# 44126 3000-pcs PS# 44151 6000-pcs PS# 44215 6000 pcs PS# 44255 4500 pcs PS# 44449 3000 pcs PS# 44481 3000 pcs
Note on N73: 3000 pcs 6000 pcs 6000- pcs 4500 pcs 3000 pcs 3000 pcs
Note on O73: MP: Inv 52443 3,000 pcs 12/18/24 Inv 52463 6,000 pcs 01/08/25 Inv 52514 6,000 pcs 02/04/25 Inv 52551 4,500 pcs 02/25/25 Inv 52731 3,000 pcs 05/06/25 Inv 52744 3,000 pcs 05/20825
Note on Q73: 3000- pcs shipped 12/18/24 6000-pcs shipped 01/08/25 6000- pcs shipped 02/04/25 4500- pcs shipped 02/25/25 3000- pcs shipped 05/06/25 3000- pcs shipped 05/20/25
Note on L75: Romania new PO Rev.1 Recvd jan-31-25 to include Yoke pin replacement tool
Note on P75: pushed out the Date to March-11-2025
Note on L76: Romania
Note on L77: Romania
Note on L78: Romania
Note on L79: Romania
Note on L80: Romania
Note on L81: Romania
Note on L82: Romania
Note on L83: Romania
Note on L84: Romania
Note on L85: Romania
Note on L87: Qinshan- original PO Recvd Jan-7-2025- Same as J# 71669 for Fro Romania
Note on L89: Romania
Note on L94: Qinshan
Note on L95: Qinshan
Note on L96: Qinshan
Note on L97: Qinshan
Note on L98: Qinshan
Note on L99: Qinshan
Note on L100: Qinshan
Note on L101: Qinshan
Note on L102: Qinshan
Note on L103: Qinshan
Note on L104: Qinshan
Note on L105: Qinshan
Note on L106: Qinshan
Note on L107: Qinshan
Note on L108: Qinshan
Note on L109: Qinshan
Note on L111: Qinshan
Note on P111: Original PO Date Was March-28-2024, Changed to April-4-25 Due to Christmas Shutdown
Note on F117: New Rev.2 recvd May-22-25- Confirmation to proceed per Quote LP-250522-Rev.1
Note on K117: Additional Cost for Rev.2 $ 778 each July-4-25- approval of Quote # LP-250620 Additiona cost for BOM # 11 Starette 674-4 being obsolete
Note on L117: Romania
Note on P117: Original PO Date Was April-11-25, but revised to April-22-25 due to Christmas Shutdown. May-23-25- New Quote LP-250525- Rev.1 Accepted for additional items with a 8-10 Weeks Delivery
Note on L119: Romania
Note on L120: Romania
Note on D121: Qty increased per e-mail from Laila June-4-2025- and PO Rev.1 June-6-25- AS per conference Sherry said the QTY on the BOM it#7 only showed 1-pcs but in fact they require 2- pcs per each assy
Note on L121: Romania
Note on L123: Romania
Note on K126: MP: Original Cost $ 19,076 + 4,444
Note on L126: Qinshan New PO Rev.1 Recvd May-30-25
Note on L128: Qinshan
Note on L129: Qinshan
Note on L130: Qinshan
Note on L131: Qinshan
Note on L132: Qinshan
Note on L133: Qinshan
Note on L134: Qinshan
Note on L135: Qinshan
Note on L136: Qinshan
Note on L137: Qinshan
Note on L138: Qinshan
Note on L140: Qinshan
Note on L150: Qinshan New Rev.1 Recvd June-19/25
Note on L151: Qinshan
Note on D152: Qty increased per e-mail from Laila June-4-2025- Change order to follow June-6-25- AS per conference Sherry said the QTY on the BOM it#7 only showed 1-pcs but in fact they require2- pcs per each assy
Note on L152: Qinshan
Note on L156: Qinshan
Note on L157: Qinshan
Note on L158: Qinshan
Note on L159: Qinshan
Note on F165: New Rev 01 Recvd June-6-25
Note on L167: Romania
Note on L168: Romania
Note on L169: Romania
Note on L171: Qinshan- New Rev.2- Revcd June-11-25
Note on L172: Qinshan
Note on L173: Qinshan
Note on C180: made for TMU , but Metonics will be paying per Olivier May-2-25
Note on K188: new pricing reflects discount given for both RT79 & RT 98 projects
Note on L188: Romania
Note on P188: Original PO Date was Oct-17-2025, but recvd PO Rev.2- on Mar-19-2025- added RT 98 PO with discounts so the delivery date updated to Nov-24-25
Note on L189: Romania
Note on P189: Original PO Date was Oct-17-2025, but recvd PO Rev.2- on Mar-19-2025- added RT 98 PO with discounts so the delivery date updated to Nov-24-25
Note on L190: Romania
Note on P190: Original PO Date was Oct-17-2025, but recvd PO Rev.2- on Mar-19-2025- added RT 98 PO with discounts so the delivery date updated to Nov-24-25
Note on L191: Romania
Note on P191: Original PO Date was Oct-17-2025, but recvd PO Rev.2- on Mar-19-2025- added RT 98 PO with discounts so the delivery date updated to Nov-24-25
Note on L192: Romania
Note on P192: Original PO Date was Oct-17-2025, but recvd PO Rev.2- on Mar-19-2025- added RT 98 PO with discounts so the delivery date updated to Nov-24-25
Note on L193: Romania
Note on P193: Original PO Date was Oct-17-2025, but recvd PO Rev.2- on Mar-19-2025- added RT 98 PO with discounts so the delivery date updated to Nov-24-25
Note on L194: Romania
Note on P194: Original PO Date was Oct-17-2025, but recvd PO Rev.2- on Mar-19-2025- added RT 98 PO with discounts so the delivery date updated to Nov-24-25
Note on L195: Romania
Note on P195: Original PO Date was Oct-17-2025, but recvd PO Rev.2- on Mar-19-2025- added RT 98 PO with discounts so the delivery date updated to Nov-24-25
Note on L196: Romania
Note on P196: Original PO Date was Oct-17-2025, but recvd PO Rev.2- on Mar-19-2025- added RT 98 PO with discounts so the delivery date updated to Nov-24-25
Note on F198: New Rev 01 Recvd June-6-25
Note on E200: Previously Quoted and McMaster # 9056K87 was supposed to be supplied F/I by Kinectrics, but on June-9-2025 Phone Conversation Paul D. wanted RTD to supply the Mcmaster Part, at an additional cost of $ 431.18 as per Steve
Note on K209: new pricing reflects discount given for both RT79 & RT 98 projects
Note on L209: Qinshan
Note on P209: Original PO Date was Oct-17-2025, but recvd PO Rev.2- on Mar-19-2025- added RT 98 PO with discounts so the delivery date updated to Nov-24-25
Note on L210: Qinshan
Note on P210: Original PO Date was Oct-17-2025, but recvd PO Rev.2- on Mar-19-2025- added RT 98 PO with discounts so the delivery date updated to Nov-24-25
Note on L211: Qinshan
Note on P211: Original PO Date was Oct-17-2025, but recvd PO Rev.2- on Mar-19-2025- added RT 98 PO with discounts so the delivery date updated to Nov-24-25
Note on L212: Qinshan
Note on P212: Original PO Date was Oct-17-2025, but recvd PO Rev.2- on Mar-19-2025- added RT 98 PO with discounts so the delivery date updated to Nov-24-25
Note on L213: Qinshan
Note on P213: Original PO Date was Oct-17-2025, but recvd PO Rev.2- on Mar-19-2025- added RT 98 PO with discounts so the delivery date updated to Nov-24-25
Note on L214: Qinshan
Note on P214: Original PO Date was Oct-17-2025, but recvd PO Rev.2- on Mar-19-2025- added RT 98 PO with discounts so the delivery date updated to Nov-24-25
Note on L215: Qinshan
Note on P215: Original PO Date was Oct-17-2025, but recvd PO Rev.2- on Mar-19-2025- added RT 98 PO with discounts so the delivery date updated to Nov-24-25
Note on L216: Qinshan
Note on P216: Original PO Date was Oct-17-2025, but recvd PO Rev.2- on Mar-19-2025- added RT 98 PO with discounts so the delivery date updated to Nov-24-25
Note on L217: Qinshan
Note on P217: Original PO Date was Oct-17-2025, but recvd PO Rev.2- on Mar-19-2025- added RT 98 PO with discounts so the delivery date updated to Nov-24-25
Note on F222: New Rev. AB recvd June-27-25
Note on M222: 2-pcs PS# 44584
Note on N222: 2- pcs shipped
Note on Q222: 2-pcs - ship'd July-11-25
Note on L224: Qinshan same as 71632-71633
Note on P229: Delivery Dates Changed by PO Rev.14 recvd May28/25
Note on K230: Added Cost for Leak Testing
Note on L236: Romania
Note on L249: Romania
Note on F261: New Rev AC recvd- May-9-2025 New Rev AD Recvd- May-13-25
Note on L261: New Terms Negotiated by Olivier 30%- With Order $ 51,806.10 30%- Net 30 Days $ 51,806.10 40%- Upon delivery / Net 60 day
Note on O261: MP: 30 % order Inv 52721 5/6/25
Note on F262: New Rev.AC recvd May-9-2025 New Rev AD- Recve May-13-25
Note on L264: I submitted all drawings for this order May-22-25- Olivier asked Sam to reprint larger drawings and restamp
Note on L267: I submitted All Drawing for this order May-22-25- Olivier asked Sam to reprint larger drawings and re-stamp
Note on E277: New Dwg Received May-28-25
Note on L277: June-24-25- Supplier shipped product Via DHL who's on Strike and shipment is in Limbo ?
Note on L281: Romania
Note on F283: New Rev.1 recvd May-27-25
Note on L283: New Rev.5 PO Recvd May-26-25
Note on E293: Dwg for Ring Only NK30-DCN-35317-0009-001- Rev.01
Note on L295: Romania
Note on L299: New Rev.4- Requesting C of C for purity of Lead pour
Note on L303: Qinshan
Note on L308: TMR-2025-0054
Note on L310: TMR-2025-0057
Note on L314: TMR-2025-0048
Note on E317: on HOLD per Steve for revised PO June-9-25
Note on L317: Junr-10-25- Original Drawing and document misplaced by Steve- Re-issued again SECOND ISSUE
Note on E318: approval received to proceed with Revised Pricing June-9-2025 for $ 443.20
Note on K318: Steve Forgot to add the cost of matarial $ 443.20 - E-mailed to Pablo
Note on L325: TMR-2025-0046
Note on Q368: Shipped Via Purolator# 3355584680861; p/u# CPU13042572
Note on L385: Parts made by Shiny Ref MQ250606001
Note on L396: Olivier getting these parts made by Shiny Tech REF: MQ2566002
Note on L400: Romania
Note on L425: TMR-2025-0067
Note on E426: Exceptions: Mat'l can be Acetal as previously accepted/ mfg
Note on E432: Can be made by RTD with information from Dobco- if required from Dobco would be 28 Weeks - and they might not make it
Note on F436: New Rev.1 recvd July-7-25